## instructions1
INSTRUCTIONS ON COMPLETION OF PROJECT STOCK TAKE TEMPLATE
1. All fields are mandatory and should be populated.
2. DO NOT EDIT the CONFIGURATION worksheet.
3. ONLY populate rows applicable in your respective Counties &Ward Location(s) and Hide the rest of the rows (DO NOT DELETE the Rows).
4. The scope of this exercise is projects started between the year 2013 and 30th June, 2024
5.Remember to SAVE the document after populating the required details in the worksheet.

## Project Stocktaking Template
S/No. | Project Name/Title | Project Description | Project Goal/Objective | Project Output | Project Code (Budget line) | Budget Item Name | Sub-County | Ward | Geographic Location (Latitude & Longitude) | Sector/ Vote Name | Department, Directorate, Units, Agencies | Implementing Department/Agency / Muncipalities | Date of Approval/Financial Approval | Project Start Date | Expected Project Completion Date | Actual Project Completion Date | Estimated Project Cost (Kshs.) | Approved Project Cost | Funds available in the specific year | Project Funding Source | If Development Partners, Please specify . | County Government component in the Project Cost (Kshs.) | Development Partner component in the Project Cost (Kshs.) | Total Disbursed Funds as at 30th June 2024 (Kshs.) | Percentage (%) Disbursed Amount = (Disbursed/ Approved) | Expenditure to date | Pending Bill/Outstanding commitment not paid but work done | Project Balance (Kshs.) i.e (Approved Project Cost - Disbursed Amount) | Project Status at the time of the Exercise (i.e Completed, Ongoing, Stalled) | % completion for ongoing/stalled projects | If Stalled, what is the percentage (%) completion at the time of stalling (Physical completion status) | If stalled give reasons; | Year the project stalled | Time required to complete the stalled project (in months) | Estimated cost required to complete the stalled project (in Kshs.) | Is the project still appering in the budget or is it still receiving funds in the annual budgets? (Yes/No) | Recommendation for the Stalled Project (Complete/ Cancel/ Defer) | Identify the Risks associated with the stalled/completed/ongoing project ie. (Contractual/legal/Financial/Environmental etc.) | Has this project been screened for Climate & Disaster Risks? Yes/No | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Environmental, Social, Occupational Health, Safety and gender risks | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Technical, Financial, and Economic Viability and a fesibility report been prepared? (yes/No) | If yes, what action has been taken to mitigate? IF Not, what is being used to measure viability of the project? Additionally, indicate immediate plans on when the screening and feasibility study will be undertaken | REMARKS | FY
PROJECT DETAILS | [6 empty] | PROJECT LOCATION |  |  | IMPLEMENTATION DETAILS | [6 empty] | FINANCIAL INFORMATION |  |  |  |  | DISBURSMENT |  |  |  | EXPENDITURE |  |  | PROJECT STATUS |  |  | ACTIONS FOR STALLED |  |  |  | RISKS AND RECOMMENDATIONS |  |  | CLIMATE & DISASTER RISK SCREENING |  | ENVIRONMENTAL , SOCIAL AND OCCUPATIONAL HEALTH, SAFETY AND GENDER SCREENING |  | TECHNICAL, FINANCIAL, AND ECONOMIC VIABILITY SCREENING |  | ADDITIONAL REMARKS
S/No. | Project Name/Title | Project Description | Project Goal/Objective | Project Output | Project Code (Budget line) | Budget Item Name | Sub-County | Ward | Geographic Location (Latitude & Longitude) | Sector/ Vote Name | Department, Directorate, Units, Agencies | Implementing Department/Agency / Muncipalities | Date of Approval/Financial Approval | Project Start Date | Expected Project Completion Date | Actual Project Completion Date | Estimated Project Cost (Kshs.) | Approved Project Cost | Funds available in the specific year | Project Funding Source | If Development Partners, Please specify . | County Government component in the Project Cost (Kshs.) | Development Partner component in the Project Cost (Kshs.) | Total Disbursed Funds as at 30th June 2024 (Kshs.) | Percentage (%) Disbursed Amount = (Disbursed/ Approved) | Expenditure to date | Pending Bill/Outstanding commitment not paid but work done | Project Balance (Kshs.) i.e (Approved Project Cost - Disbursed Amount) | Project Status at the time of the Exercise (i.e Completed, Ongoing, Stalled) | % completion for ongoing/stalled projects | If Stalled, what is the percentage (%) completion at the time of stalling (Physical completion status) | If stalled give reasons; | Year the project stalled | Time required to complete the stalled project (in months) | Estimated cost required to complete the stalled project (in Kshs.) | Is the project still appering in the budget or is it still receiving funds in the annual budgets? (Yes/No) | Recommendation for the Stalled Project (Complete/ Cancel/ Defer) | Identify the Risks associated with the stalled/completed/ongoing project ie. (Contractual/legal/Financial/Environmental etc.) | Has this project been screened for Climate & Disaster Risks? Yes/No | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Environmental, Social, Occupational Health, Safety and gender risks | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Technical, Financial, and Economic Viability and a fesibility report been prepared? (yes/No) | If yes, what action has been taken to mitigate? IF Not, what is being used to measure viability of the project? Additionally, indicate immediate plans on when the screening and feasibility study will be undertaken | REMARKS
1 | REFURBISHMENT OF NYAMIRALEVEL 4 HOSPITAL MAIN GATE CGN/149/2013-14 | Construction of Modern Gate ,security office and visitors,waiting area | Improved infrustructure | Modern Gate ,security office and visitors,waiting area | D5267 | Non-Residential buildings | Nyamira South | Township | N/A | Medical Services | Health Services | SONJE INVESTMENTS LTD | N/A | 2014-05-11 | 2015-05-03 | 2015-05-03 | 7680831.54 | 7680831.54 | N/A | CGN | N/A | 7680831.54 | 0 | 7680831.54 | 100% | 7680831.54 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2014/2015
2 | OUTPATIENT BLOCK AT NYABOGOYE HEALTH FACILITY NYCG/Q114/2014-2015 | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | Masaba North | Rigoma | N/A | Primary Health Care | Health Services | TAZAMA BUILDERS | N/A | 24/11/2015 | 20/01/2016 | 20/01/2016 | 3985551.2 | 3985551.2 | N/A | CGN | N/A | 3985551.2 | 0 | 3985551.2 | 100% | 3985551.2 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed, awaiting comissioning | 2015/2016
3 | OUTPATIENT BLOCK AT NYANGORI HEALTH FACILITY NYCG/Q115/2014-2015 | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | Masaba North |  | N/A | Primary Health Care | Health Services | STEM INVESTMENTS | N/A | 24/11/2015 | 20/01/2016 | 20/01/2016 | 3956006 | 3956006 | N/A | CGN | N/A | 3956006 | 0 | 3956006 | 100% | 3956006 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2015/2016
4 | MATERNITY BLOCK AT KIANGOSO HEALTH FACILITY NYCG/Q117/2014-2015 | Construction of a Maternity Block | Improved infrustructure | Complete Maternity Block | D5279 | Non-Residential buildings | MANGA | KEMERA | N/A | Primary Health Care | Health Services | NYANTURAGO CONST. & GEN CONTRACTORS. | N/A | 2015-10-11 | 2016-05-01 | 2016-05-01 | 3913504 | 3913504 | N/A | CGN | N/A | 3913504 | 0 | 3913504 | 100% | 3913504 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2015/2016
5 | MATERNITY BLOCK AT KIANUNGU HEALTH FACILITY NYCG/Q118/2014-2015 | Construction of a Maternity Block | Improved infrustructure | Complete Maternity Block | D5279 | Non-Residential buildings | MANGA | BOSAMARO | N/A | Primary Health Care | Health Services | AUTO STAR AGENCIES | N/A | 2015-10-11 | 2016-05-01 | 2016-05-01 | 3994261.6 | 3994261.6 | N/A | CGN | N/A | 3994261.6 | 0 | 3994261.6 | 100% | 3994261.6 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2015/2016
6 | MATERNITY BLOCK AT NYAIGESA HEALTH FACILITY NYCG/Q140/2014-2015 | Construction of a Maternity Block | Improved infrustructure | Complete Maternity Block | D5279 | Non-Residential buildings | NYAMIRA SOUTH | NYAMAIYA | N/A | Primary Health Care | Health Services | ENSOKO CONST. | N/A | 24/11/2015 | 17/03/2016 | 17/03/2016 | 3800803.8 | 3800803.8 | N/A | CGN | N/A | 3800803.8 | 0 | 3800803.8 | 100% | 3800803.8 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2015/2016
7 | MATERNITY BLOCK AT MOKOMONI HEALTH FACILITY NYCG/Q142/2014-2015 | Construction of a Maternity Block | Improved infrustructure | Complete Maternity Block | D5279 | Non-Residential buildings | BORABU | KIABONYORU | N/A | Primary Health Care | Health Services | JOPEKI CONST. CO. LTD | N/A | 22/12/2015 | 15/03/2016 | 15/03/2016 | 3806603.8 | 3806603.8 | N/A | CGN | N/A | 3806603.8 | 0 | 3806603.8 | 100% | 3806603.8 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2015/2016
8 | CONSTRUCTION OF MATERNITY BLOCK AT BOMBAGI HEALTH FACILITY NYCG/Q080/2015 - 2016 | Construction of a Maternity Block | Improved infrustructure | Complete Maternity Block | D5279 | Non-Residential buildings | NYAMIRA SOUTH | TOWNSHIP | N/A | Primary Health Care | Health Services | ENSON INVESTMENT | N/A | 19/4/2016 | 2016-04-10 | 2016-04-10 | 3800593 | 3800593 | N/A | CGN | N/A | 3800593 | 0 | 3800593 | 100% | 3800593 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2016/2017
9 | CONSTRUCTION OF OUT-PATIENT BLOCK AT RIAMONI HEALTH FACILITY NYCG/Q130/2015 - 2016 | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | MASABA NORTH | RIGOMA | N/A | Primary Health Care | Health Services | TREAMAOC (K) LTD | N/A | 19/4/2016 | 2016-04-10 | 2016-04-10 | 3850260 | 3850260 | N/A | CGN | N/A | 3850260 | 0 | 3850260 | 100% | 3850260 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2016/2017
10 | CONSTRUCTION OF OUT-PATIENT BLOCK AT TINDERETI HEALTH FACILITY NYCG/Q153/2015 - 2016 | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | BORABU | NYANSIONGO | N/A | Primary Health Care | Health Services | DENAMO GEN. SUPPLIERS LTD | N/A | 19/4/2016 | 2016-04-10 | 2016-04-10 | 3960200 | 3960200 | N/A | CGN | N/A | 3960200 | 0 | 3960200 | 100% | 3960200 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2016/2017
11 | CONSTRUCTION AND COMPLETION OF OPERATING THEATRE, X-RAY AND MATERNITY WARDS AT NYANSIONGO SUB-COUNTY HOSPITAL CGN/T074/2015-16 | CONSTRUCTION AND COMPLETION OF OPERATING THEATRE, X-RAY AND MATERNITY WARDS AT NYANSIONGO SUB-COUNTY HOSPITAL | Improved infrustructure | COMPLETE OF OPERATING THEATRE, X-RAY AND MATERNITY WARDS AT NYANSIONGO SUB-COUNTY HOSPITAL | D5267 | Non-Residential buildings | BORABU | NYANSIONGO | N/A | Primary Health Care | Health Services | Sonje Investment LTD | N/A |  |  |  | 13586494 | 13586494 | N/A | CGN | N/A | 13586494 | 0 | 13586494 | 100% | 13586494 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2016/2017
12 | Construction and Completion of 80 Bed Amenity Block with ¦Doctor’s Plaza at Nyamira County Referral Hospital CGN/T075/2015-16 | Construction and Completion of 80 Bed Amenity Block with ¦Doctor’s Plaza at Nyamira County Referral Hospital | Improved infrustructure | Complete of 80 Bed Amenity Block with Doctor’s Plaza at Nyamira County Referral Hospital | D5267 | Non-Residential buildings | NYAMIRA SOUTH | TOWNSHIP | N/A | Medical Services | Health Services | SEAMAN Building & Civil Engineers | N/A |  |  |  | 142319154.2 | 142319154.2 | N/A | CGN | N/A | 142319154.2 | 0 | 142319154.2 | 100% | 142319154.2 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2016/2017
13 | CONSTRUCTION AND COMPLETION OF OPERATING THEATRE AT NYAMIRA COUNTY REFERRAL HOSPITAL CGN/T076/2015-16 | Construction and completion of 3 operating thearter rooms at NCRH | Improved infrustructure | Complete 3 operating thearter rooms at NCRH | D5267 | Non-Residential buildings | NYAMIRA SOUTH | TOWNSHIP | N/A | Medical Services | Health Services | KEGIMA CONGRETE WORKS LTD | N/A |  |  |  | 18154731 | 18154731 | N/A | CGN | N/A | 18154731 | 0 | 18154731 | 100% | 18154731 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2016/2017
14 | PROPOSED COMPLETION OF ESANI SUB COUNTY HOSPITAL STALLED STORY BUILDING NYCG/Q285/2015-16 | COMPLETION OF ESANI SUB COUNTY HOSPITAL STALLED STORY BUILDING | Improved infrustructure | COMPLETE OF ESANI SUB COUNTY HOSPITAL STORRIED BUILDING | D5267 | Non-Residential buildings | MASABA NORTH | RIGOMA | N/A | Medical Services | Health Services | MBOGO NYAGEKE TRANSPORTERS | N/A | 24/8/2016 | 16/12/2016 | 16/12/2016 | 3975262 | 3975262 | N/A | CGN | N/A | 3975262 | 0 | 3975262 | 100% | 3975262 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2016/2017
15 | CONSTRUCTION OF RIOTONYI OPD BLOCK NYCG/Q262/2015-2016 | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | BORABU |  | N/A | Primary Health Care | Health Services | TABSHA SUPPLIES & GEN. CONTRACTORS | N/A | 2016-05-07 | 2016-11-07 | 2016-11-07 | 3985286 | 3985286 | N/A | CGN | N/A | 3985286 | 0 | 3985286 | 100% | 3985286 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2016/2017
16 | PROPOSED COMPLETION KAMBINI OUTPAPIENT BLOCK NYCG/Q283/2015-2016 | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | MASABA NORTH | GESIMA | N/A | Primary Health Care | Health Services | MELBOUME ENGINEERING K. LTD | N/A | 24/5/2016 | 2016-11-24 | 2016-11-24 | 3943257 | 3943257 | N/A | CGN | N/A | 3943257 | 0 | 3943257 | 100% | 3943257 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2016/2017
17 | CONSTRUCTION OF NYAOBE HEALTH FACILITY NYCG/Q331/2015-2016 | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | NYAMIRA NORTH | BOKEIRA | N/A | Primary Health Care | Health Services | KESVIC CO. LTD | N/A | 19/8/2016 | 2017-02-19 | 2017-02-19 | 3890122.64 | 3890122.64 | N/A | CGN | N/A | 3890122.64 | 0 | 3890122.64 | 100% | 3890122.64 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2016/2017
18 | PROPOSED COMPLETION OF SERE OUTPAPIENT BLOCK NYCG/Q334/2015-2016 | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | NYAMIRA NORTH | 30SD | N/A | Primary Health Care | Health Services | NYAKONG WORKS LTD | N/A | 24/5/2016 | 2016-11-24 | 2016-11-24 | 3150000 | 3150000 | N/A | CGN | N/A | 3150000 | 0 | 3150000 | 100% | 3150000 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2016/2017
19 | PROPOSED COMPLETION OF NYAKEGOGI DISPENSARY NYCG/Q335/2015-2016 | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | MANGA | KEMERA | N/A | Primary Health Care | Health Services | ZAFO CONSTRUCTION CO. LTD | N/A | 24/8/2016 | 2017-02-24 | 2017-02-24 | 3890302.2 | 3890302.2 | N/A | CGN | N/A | 3890302.2 | 0 | 3890302.2 | 100% | 3890302.2 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2016/2017
20 | PROPOSED COMPLETION OF OUT PATIENT BLOCK GATUTA HEALTH CENTRE NYCG/Q440/2015-2016 | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | MANGA | MAGOMBO | N/A | Primary Health Care | Health Services | KEMCO GEN. CONSTRUCTION CO. LTD | N/A | 24/5/2016 | 2016-11-24 | 2016-11-24 | 3890900 | 3890900 | N/A | CGN | N/A | 3890900 | 0 | 3890900 | 100% | 3890900 | 0 | 0 | COMPLETE | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2016/2017
21 | Proposed Construction and Completion of Inpatient wards with operaing Theater block at Magwagwa Health Facility | Construction and Completion of Inpatient wards with operaing Theater block | Improved infrustructure | Complete Inpatient wards | D5279 | Non-Residential buildings | NYAMIRA NORTH | Magwagwa | N/A | Primary Health Care | Health Services | Gesure Building Contractors Limited | N/A | 28/06/2018 | 28/03/2019 | 28/03/2019 | 64551975.8 | 64551975.8 | N/A | CGN | N/A | 64551975.8 | 0 | 64551975.8 | 100% | 64551975.8 | 0 | 0 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2018/2019
22 | Proposed Construction and Completion of Inpatient wards at Manga Sub County Hospital | Construction and Completion of Inpatient wards | Improved infrustructure | Complete Inpatient wards | D5267 | Non-Residential buildings | MANGA | Manga | N/A | Medical Services | Health Services | Kombiro Building Compasny Limited | N/A | 28/06/2018 | 28/03/2019 | 28/03/2019 | 34237845 | 34237845 | 0 | CGN | N/A | 34237845 | 0 | 34237845 | 100% | 34237845 | 0 |  | Terminated | N/A | N/A |  |  |  |  | No |  | N/A | No | N/A | No | N/A | No | N/A | Awaiting re-tendering | 2018/2019
23 | Proposed Construction and Completion of Inpatient wards at Gesima Sub County Hospital | Construction and Completion of Inpatient wards | Improved infrustructure | Complete Inpatient wards | D5267 | Non-Residential buildings | MASABA NORTH | Gesima | N/A | Medical Services | Health Services | Melbourne Engeering (k)limited | N/A | 28/06/2018 | 28/03/2019 | 28/03/2019 | 34999235 | 34999235 | N/A | CGN | N/A | 34999235 | 0 | 34999235 | 100% | 34999235 | 0 | 0 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2018/2019
24 | Proposed Construction and Completion of Inpatient wards at Nyamusi Sub County Hospital | Construction and Completion of Inpatient wards | Improved infrustructure | Complete Inpatient wards | D5267 | Non-Residential buildings | NYAMIRA NORTH | Nyamusi | N/A | Medical Services | Health Services | Kotema Building Construction Limited | N/A | 28/06/2018 | 28/03/2019 | 28/03/2019 | 34865540 | 34865540 | 5000000 | CGN | N/A | 34865540 | 0 | 25200547.34 | 100% | 25200547.34 | 0 | 9359452.66 | Completed | N/A | N/A |  |  |  |  | No |  | N/A | No | N/A | No | N/A | No | N/A | At final stages of completion | 2018/2019
25 | Supply and Delivery of a Stand by Generator Set at Nyamira County Referral Hospital | Supply and installation of a Stand by Generator Set at Nyamira County Referral Hospital | Improved infrustructure | Stand by Generator installed at Nyamira County Referral Hospital | D5267 | Non-Residential buildings | NYAMIRA SOUTH | TOWNSHIP | N/A | Medical Services | Health Services | Shanice & Shanice Services Limited | N/A | 25/06/2018 | 25/12/2018 | 25/12/2018 | 9300000 | 9300000 | N/A | CGN | N/A | 9300000 | 0 | 9300000 | 100% | 9300000 | 0 | 0 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2018/2019
26 | Proposed Construction and Completion of Inpatient wards block at Nyabweri Health Facility | Construction and Completion of Inpatient wards | Improved infrustructure | Complete Inpatient wards | D5279 | Non-Residential buildings | NYAMIRA NORTH | Bomwagamo | N/A | Primary Health Care | Health Services | Samakim Construction and Services Trading Limited | N/A | 24/06/2019 | 24/06/2020 | 24/06/2020 | 13239878.08 | 13239878.08 | N/A | CGN | N/A | 13239878.08 | 0 | 13239878.08 | 100% | 13239878.08 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in Use | 2019/2020
27 | Costruction and Completion of twin staff house with two No.door pit latrine at Sere health facility | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | NYAMIRA NORTH |  | N/A | Primary Health Care | Health Services | Spearways Investments Limited | N/A | 21/05/2019 | 21/11/2019 | 21/11/2019 | 3836980 | 3836980 | N/A | CGN | N/A | 3836980 | 0 | 3836980 | 100% | 3836980 | 0 | 0 | On Going | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed | 2019/2020
28 | Costruction and Complition of twin staff house with two No.door pit latrine at Emenyenche health facility | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | MASABA NORTH | GESIMA | N/A | Primary Health Care | Health Services | Opal General Suppies Limited | N/A | 21/05/2019 | 21/11/2019 | 21/11/2019 | 3687645 | 3687645 | N/A | CGN | N/A | 3687645 | 0 | 1967035 | 53% | 1967035 | 0 | 1720610 | Stalled | 53% | 53% | Lack of budgetary allocation |  |  |  | No |  | N/A | No | N/A | No | N/A | No | N/A |  | 2019/2020
29 | Costruction and Complition of twin staff house with two No.door pit latrine at Kambini health facility | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | MASABA NORTH | GESIMA | N/A | Primary Health Care | Health Services | The Matric Management Consultants Company Limited | N/A | 21/05/2019 | 21/11/2019 | 21/11/2019 | 3518800 | 3518800 | N/A | CGN | N/A | 3518800 | 0 | 3518800 | 100% | 3518800 | 0 | 3518800 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A |  | 2019/2020
30 | Costruction and Complition of twin staff house with two No.door pit latrine at Kiangoso health facility | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | MANGA | KEMERA | N/A | Primary Health Care | Health Services | Afritex Kenya Limited | N/A | 21/05/2019 | 21/11/2019 | 21/11/2019 | 3840876 | 3840876 | N/A | CGN | N/A | 3840876 | 0 | 0 | 0% | 0 | 0 | 3840876 | Stalled | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Terminated due to land dispute | 2019/2020
31 | Costruction and Complition of twin staff house with two No.door pit latrine at Kenyamware health facility | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | MANGA | MAGOMBO | N/A | Primary Health Care | Health Services | Wywell Construction Limited | N/A | 21/05/2019 | 21/11/2019 | 21/11/2019 | 3,961,980,00 | 3,961,980,00 | N/A | CGN | N/A | 3,961,980,00 | 0 | 3,961,980,00 | 100% | 3,961,980,00 | #VALUE! | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A |  | 2019/2020
32 | Costruction and Complition of twin staff house with two No.door pit latrine at Kiangombe health facility | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | NYAMIRA NORTH | ITIBO | N/A | Primary Health Care | Health Services | Transbek Hoiding Limited | N/A | 21/05/2019 | 21/11/2019 | 21/11/2019 | 3574377.6 | 3574377.6 | N/A | CGN | N/A | 3574377.6 | 0 | 3574377.6 | 100% | 3574377.6 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Awaiting commissioning | 2019/2020
33 | Construction and Completion of maternity block at Motontera dispensary | Construction and Completion of maternity block at Motontera dispensary | Improved infrustructure | Complete maternity block at Motontera dispensary | D5279 | Non-Residential buildings |  |  | N/A | Primary Health Care | Health Services | Moiwa Youth Limited | N/A | 21/05/2019 | 21/11/2019 | 21/11/2019 | 3620684.8 | 3620684.8 | N/A | CGN | N/A | 3620684.8 | 0 | 3620684.8 | 100% | 3620684.8 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Complete and in use | 2019/2020
34 | Construction and completion of Maternity block at Orwaki Health Centre | Construction and completion of Maternity block at Orwaki Health Centre | Improved infrustructure | Complete of Maternity block at Orwaki Health Centre | D5279 | Non-Residential buildings | NYAMIRA NORTH |  | N/A | Primary Health Care | Health Services | Bestline International Limited | N/A | 21/03/2019 | 21/9/2019 | 21/9/2019 | 3505897 | 3505897 | N/A | CGN | N/A | 3505897 | 0 | 3505897 | 100% | 3505897 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Complete and in use | 2019/2020
35 | Construction and completion of twin staff house with two number door Pit latrine at Nyandoche Ibere Health Centre | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | BORABU | NYANSIONGO | N/A | Primary Health Care | Health Services | Oxley Kenya Limited | N/A | 21/03/2019 | 21/09/2019 | 21/09/2019 | 3840876 | 3840876 | N/A | CGN | N/A | 3840876 | 0 | 0 | 0% | 0 | 0 | 3840876 | Terminated | 10% | 10% | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Terminated due to poor workmanship | 2019/2020
36 | Construction and completion of OPD Block with Two number Pit latrine at Ribaita Health Centre | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | BORABU |  | N/A | Primary Health Care | Health Services | Forthright Engineering (K) Limited | N/A | 21/03/2019 | 21/09/2019 | 21/09/2019 | 3802665 | 3802665 | N/A | CGN | N/A | 3802665 | 0 | 3802665 | 100% | 3802665 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed awaiting reopening | 2019/2020
37 | Construction and completion of twin staff house with two number door pit latrine at Motagara Dispensary Centre | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | NYAMIRA SOUTH | Bosamaro | N/A | Primary Health Care | Health Services | Tati Holding Limited | N/A | 21/03/2019 | 21/09/2019 | 21/09/2019 | 3990155 | 3990155 | N/A | CGN | N/A | 3990155 | 0 | 2180815 | 55% | 2180815 | 0 | 1809340 | Stalled | 55% | 55% | Lack of budgetary allocation |  |  |  | No |  | N/A | No | N/A | No | N/A | No | N/A |  | 2019/2020
38 | Construction and completion of twin staff house with two number door pit latrine at Nyagacho | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings |  |  | N/A | Primary Health Care | Health Services | Melbourne Engineering(K) Limited | N/A | 2019-03-06 | 2020-03-03 | 2020-03-03 | 3986142.8 | 3986142.8 | N/A | CGN | N/A | 3986142.8 | 0 | 3986142.8 | 100% | 3986142.8 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in use | 2019/2020
39 | Construction and completion of twin staff house with two number door pit latrine at Nyamaiya Health Centre | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | NYAMIRA SOUTH | Nyamaiya | N/A | Primary Health Care | Health Services | Bamick Enterprises Limited | N/A | 21/03/2019 | 21/09/2019 | 21/09/2019 | 3334090 | 3334090 | N/A | CGN | N/A | 3334090 | 0 | 2703393 | 81% | 2703393 | 0 | 2083011 | Complete | 75% | 75% | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in use | 2019/2020
40 | Construction and completion of OPD with two number door pit latrine at Ikobe Health Centre | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | MANGA | Manga | N/A | Primary Health Care | Health Services | Sadelyx Suppliers Limited | N/A | 21/03/2019 | 21/09/2019 | 21/09/2019 | 3630486.8 | 3630486.8 | N/A | CGN | N/A | 3630486.8 | 0 | 3630486.8 | 100% | 3630486.8 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in use | 2019/2020
41 | Construction and completion of twin staff house with two number door pit latrine at Kianginda Health Centre | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | NYAMIRA SOUTH |  | N/A | Primary Health Care | Health Services | McFinley Healthcare Limited | N/A | 21/03/2019 | 21/09/2019 | 21/09/2019 | 3619200 | 3619200 | N/A | CGN | N/A | 3619200 | 0 | 3619200 | 100% | 3619200 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in use | 2019/2020
42 | Construction and completion of OPD Block with two number door pit latrine at Nyamwanga Health Centre | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | MANGA | MAGOMBO | N/A | Primary Health Care | Health Services | Allbright Limited | N/A | 21/03/2019 | 21/09/2019 | 21/09/2019 | 3524845.6 | 3524845.6 | N/A | CGN | N/A | 3524845.6 | 0 | 3524845.6 | 100% | 3524845.6 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in use | 2019/2020
43 | Proposed Construction of and Completion of OPD Block at Kenyamware Health Facility. | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | MANGA | Magombo | N/A | Primary Health Care | Health Services | Mukijo Investment Limited | N/A | 20/07/2020 | 20/11/2020 | 20/11/2020 | 3982658.4 | 3982658.4 | N/A | CGN | N/A | 3982658.4 | 0 | 2644744 | 66.4% | 2644744 | 0 | 1337914 | Stalled | 85% | 85% | Contractor abandoned site |  |  |  | No | Compete | Contractual | No | N/A | No | N/A | No | N/A |  | 2019/2020
44 | Proposed Construction and completion to OPD block with two no.door pit latrine at Esianyi Health F acility | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | NYAMIRA NORTH | Bokeira | N/A | Primary Health Care | Health Services | Offspace Constrution Limited | N/A | 20/07/2020 | 20/11/2020 | 20/11/2020 | 3999997.8 | 3999997.8 | N/A | CGN | N/A | 3999997.8 | 0 | 3999997.8 | 100% | 3999997.8 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A |  | 2019/2020
45 | Proposed Completion to Esani Sub County Hospital stalled story Building Phase4 | Proposed Completion to Esani Sub County Hospital stalled story Building Phase4 | Improved infrustructure | Complete Esani Sub County Hospital stalled story Building Phase4 | D5279 | Non-Residential buildings | MASABA NORTH | Gesima | N/A | Primary Health Care | Health Services | Bonbillia Enterprises | N/A | 18/05/2020 | 18/07/2020 | 18/07/2020 | 3982059.6 | 3982059.6 | N/A | CGN | N/A | 3982059.6 | 0 | 3982059.6 | 100% | 3982059.6 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A |  | 2019/2020
46 | Proposed Construction and Completion of Inpatient Wards at Amatierio Health Facility | Construction and Completion of Inpatient wards | Improved infrustructure | Complete Inpatient wards | D5279 | Non-Residential buildings | BORABU | Kiabonyoru | N/A | Primary Health Care | Health Services | Chacha Logostics and General Supplies Limited | N/A | 2020-12-08 | 2022-12-03 | 2022-12-03 | 14716807.2 | 14716807.2 | N/A | CGN | N/A | 14716807.2 | 0 | 14716807.2 | 100% | 14716807.2 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed awaiting commissioning | 2020/2021
47 | Proposed Construction and Completion of Inpatient Wards at Kiangoso Health Facility | Construction and Completion of Inpatient wards | Improved infrustructure | Complete Inpatient wards | D5279 | Non-Residential buildings | MANGA | Kemera | N/A | Primary Health Care | Health Services | Gianche Investments Limited | N/A | 2020-12-08 | 2022-12-03 | 2022-12-03 | 14567000 | 14567000 | N/A | CGN | N/A | 14567000 | 0 | 14567000 | 100% | 14567000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed awaiting commissioning | 2020/2021
48 | Proposed Construction and Completion of Out Patient Department and Inpatient Wards at Ekerenyo Health Facility | Construction and Completion of Inpatient wards | Improved infrustructure | Complete Inpatient wards | D5267 | Non-Residential buildings | NYAMIRA NORTH | Ekerenyo | N/A | Medical Services | Health Services | Shanice & Shanice Services Limited | N/A | 2020-12-08 | 2022-12-03 | 2022-12-03 | 34589321.4 | 34589321.4 | 5000000 | CGN | N/A | 34589321.4 | 0 | 12480341 | 36.1% | 12480341 | 0 | 22108980 | On Going | 47% | 47% | N/A | N/A | N/A | N/A | No | Compete | Contractual | No | N/A | No | N/A | No | N/A |  | 2020/2021
49 | Proposed Construction and Completion of Nyamira Eye Hospital Service Block at Nyamwetureko Health Facility | Proposed Construction and Completion of Nyamira Eye Hospital Service Block at Nyamwetureko Health Facility | Improved infrustructure | Complete Nyamira Eye Hospital Service Block at Nyamwetureko Health Facility | D5279 | Non-Residential buildings | NYAMIRA SOUTH | Bonyamatuta | N/A | Primary Health Care | Health Services | Shakwiti Limited | N/A | 2020-12-08 | 2022-12-03 | 2022-12-03 | 35104864 | 35104864 | 5000000 | CGN | N/A | 35104864 | 0 | 15127212 | 43.1% | 15127212 | 0 | 19977652 | On Going | 43% | 43% | Contractor abandoned site |  |  |  | No | Cancel | Contractual | No | N/A | No | N/A | No | N/A |  | 2020/2021
50 | Proposed Construction and Completion of Maternity Block at Mongoni Health Facility |  | Improved infrustructure |  | D5279 | Non-Residential buildings | MASABA NORTH | Rigoma | N/A | Primary Health Care | Health Services | Bevinah Investments Limited | N/A | 2020-12-08 | 2021-12-06 | 2021-12-06 | 3355732.5 | 3355732.5 |  | CGN | N/A | 3355732.5 | 0 | 3355732.5 | 100% | 3355732.5 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in use | 2020/2021
51 | Proposed Construction and Completion of Twin Staff House with two number door pit Latrine at Nyachonoria Health Facility | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | MASABA NORTH | Rigoma | N/A | Primary Health Care | Health Services | Maki & Sons Construction Company Limited | N/A | 2020-12-08 | 2021-12-06 | 2021-12-06 | 3486142.8 | 3486142.8 |  | CGN | N/A | 3486142.8 | 0 | 3486142.8 | 100% | 3486142.8 | 0 | 0 | Stalled | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A |  | 2020/2021
52 | Proposed Construction and Completion of Twin Staff House with two number door pit Latrine at Chaina Health Facility | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | NYAMIRA NORTH | Itibo | N/A | Primary Health Care | Health Services | Transbex Holdings Limited | N/A | 2020-12-08 | 2021-12-06 | 2021-12-06 | 3505363.2 | 3505363.2 |  | CGN | N/A | 3505363.2 | 0 | 2742246.89 | 78.2% | 2742246.89 | 0 | 763116 | On Going | 78% | 78% | Lack of budgetary allocation |  |  |  | No | Cancel | Contractual | No | N/A | No | N/A | No | N/A |  | 2020/2021
53 | Proposed Construction and Completion of Twin Staff House with two number door pit Latrine at Kahawa Health Facility | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | BORABU | Esise | N/A | Primary Health Care | Health Services | Walemafu Builders | N/A | 2020-12-08 | 2021-12-06 | 2021-12-06 | 3600986 | 3600986 |  | CGN | N/A | 3600986 | 0 | 1885781 | 52.3% | 1885781 | 0 | 1715205 | Stalled | 52.37% | 52.37% | Lack of budgetary allocation |  |  |  | No | Cancel | Contractual | No | N/A | No | N/A | No | N/A |  | 2020/2021
54 | Proposed Construction and Completion of Twin Staff House with two number door pit Latrine at Nyakeore Health Facility | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | NYAMIRA SOUTH | Bonyamatuta | N/A | Primary Health Care | Health Services | Spear ways Investment Limited | N/A | 2020-12-08 | 2021-12-06 | 2021-12-06 | 3441671.4 | 3441671.4 |  | CGN | N/A | 3441671.4 | 0 | 1894995 | 55.1% | 1894995 | 0 | 1546676 | Stalled | 55% | 55% | Lack of budgetary allocation |  |  |  | No | Cancel | Contractual | No | N/A | No | N/A | No | N/A |  | 2020/2021
55 | Proposed Construction and Completion of OPD Block with two number door pit Latrine at Bobembe Health Facility | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | NYAMIRA SOUTH | Bogichora | N/A | Primary Health Care | Health Services | Keyram Contractors Limited | N/A | 2020-12-08 | 2021-12-06 | 2021-12-06 | 3330402.8 | 3330402.8 |  | CGN | N/A | 3330402.8 | 0 | 3330402.8 |  | 3330402.8 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A |  | 2020/2021
56 | Proposed Construction and Completion of OPD Block with two number door pit Latrine at Nyaobe Health Facility | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | NYAMIRA NORTH | Bokeira | N/A | Primary Health Care | Health Services | Transfix Construction Limited | N/A | 2020-12-08 | 2021-12-06 | 2021-12-06 | 3575416.2 | 3575416.2 |  | CGN | N/A | 3575416.2 | 0 | 3575416.2 |  | 3575416.2 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A |  | 2020/2021
57 | Proposed Construction and Completion of OPD Block with two number door pit Latrine at Geseneno Health Facility | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | NYAMIRA SOUTH | Township | N/A | Primary Health Care | Health Services | Sanya Kenya Limited | N/A | 2020-12-08 | 2021-12-06 | 2021-12-06 | 3305162.8 | 3305162.8 |  | CGN | N/A | 3305162.8 | 0 | 3305162.8 |  | 3305162.8 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A |  | 2020/2021
58 | Proposed Construction and Completion of OPD Block with two No.door pit latrine at Ensakia Health Facility | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | BORABU | Esise | N/A | Primary Health Care | Health Services | Jakawi Supplies Limited | N/A | 24/06/2021 | 24/11/2021 | 24/11/2021 | 3799498.8 | 3799498.8 |  | CGN | N/A | 3799498.8 | 0 | 1947286 | 51.3% | 1947286 | 0 | 1852213 | On going | 75% | 75% | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A |  | 2020/2021
59 | Proposed Construction and Completion of OPD Block with two No.door pit latrine at Bomorito Health Facility | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | NYAMIRA SOUTH | Nyamaiya | N/A | Primary Health Care | Health Services | Kesvic Company Limited | N/A | 24/06/2021 | 24/11/2021 | 24/11/2021 | 3977834.88 | 3977834.88 |  | CGN | N/A | 3977834.88 | 0 | 3977834.88 |  | 3977834.88 | 0 | 0 | complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and awaiting commisioning | 2020/2021
60 | Proposed construction and completion of OPD Block with two No.door pit latrine at Nyanchoka Health Facility | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | NYAMIRA NORTH | Kiabonyoru | N/A | Primary Health Care | Health Services | Matacho Holdings Limited | N/A | 24/06/2021 | 24/11/2021 | 24/11/2021 | 3654423.4 | 3654423.4 |  | CGN | N/A | 3654423.4 | 0 | 3654423.4 |  | 3654423.4 | 0 | 0 | complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and awaiting commisioning | 2020/2021
61 | Proposed Construction and Completion of out patient block with two No. door pit latrine at Bobaracho haelth facility | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | NYAMIRA SOUTH | Bogichora | N/A | Primary Health Care | Health Services | Sadelyx Suppliers Limited | N/A | 24/06/2021 | 24/11/2021 | 24/11/2021 | 3999946.8 | 3999946.8 |  | CGN | N/A | 3999946.8 | 0 | 3999946.8 |  | 3999946.8 | 0 | 0 | complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and awaiting commisioning | 2020/2021
62 | Construction and Completion of Nyamira County Referral Hospital Covid 19 Isolation Complex | Construction and Completion of Nyamira County Referral Hospital Covid 19 Isolation Complex | Improved infrustructure | Complete of Nyamira County Referral Hospital Covid 19 Isolation Complex | D5267 | Non-Residential buildings | NYAMIRA SOUTH | Township | N/A | Medical Services | Health Services | Burhani Engineers Limited | N/A | 25/09/2020 | 25/09/2021 | 25/09/2021 | 95860834.37 | 95860834.37 | 3000000 | CGN | N/A | 95860834.37 | 0 | 46260484 |  | 46260484 | 0 | 49600350 | Terminated | 48% | 48% | Contractor sued County Government |  |  |  | No | Compete | Legal | No | N/A | No | N/A | No | N/A | Being re-tendered in FY 2025-26 | 2020/2021
63 | Renovation of Nyangena Health Facility | Renovation of Nyangena Health Facility | Improved infrustructure | Rehabilitated Nyangena Health Facility | D5279 | Non-Residential buildings | MANGA | Manga | N/A | Primary Health Care | Health Services | Ricc Rozzie Builders Limited | N/A | 28/05/2021 | 28/11/2021 | 28/11/2021 | 14323210 | 14323210 |  | THS-UCP | World Bank(THS-UCP) | 0 | 14323210 | 14323210 |  | 14323210 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in use | 2020/2021
64 | Renovation of Kenyenya Health Facility | Renovation of Kenyenya Health Facility | Improved infrustructure |  | D5279 | Non-Residential buildings | NYAMIRA SOUTH | Bonyamatuta | N/A | Primary Health Care | Health Services | Alic Builders Limited | N/A | 24/05/2021 | 24/12/2021 | 24/12/2021 | 13248360 | 13248360 |  | THS-UCP | World Bank(THS-UCP) | 0 | 13248360 | 13248360 |  | 13248360 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in use | 2020/2021
65 | Renovation of Magombo Health Facility | Renovation of Magombo Health Facility | Improved infrustructure |  | D5279 | Non-Residential buildings | MANGA | Magombo | N/A | Primary Health Care | Health Services | Magnifica Contractors Limited | N/A | 24/05/2021 | 24/12/2021 | 24/12/2021 | 11904540 | 11904540 |  | THS-UCP | World Bank(THS-UCP) | 0 | 11904540 | 11904540 |  | 11904540 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in use | 2020/2021
66 | Renovation of Kerobo Health Facility | Renovation of Kerobo Health Facility | Improved infrustructure |  | D5279 | Non-Residential buildings | NYAMIRA NORTH | Kiabonyoru | N/A | Primary Health Care | Health Services | Spearways Investment Limited | N/A | 24/05/2021 | 24/12/2021 | 24/12/2021 | 7925120 | 7925120 |  | THS-UCP | World Bank(THS-UCP) | 0 | 7925120 | 7925120 |  | 7925120 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in use | 2020/2021
67 | Renovation of Machururiati Health Facility | Renovation of Machururiati Health Facility | Improved infrustructure |  | D5279 | Non-Residential buildings | MASABA NORTH | Gesima | N/A | Primary Health Care | Health Services | Edono Kenya Limited | N/A | 24/05/2021 | 24/12/2021 | 24/12/2021 | 13550905 | 13550905 |  | THS-UCP | World Bank(THS-UCP) | 0 | 13550905 | 13550905 |  | 13550905 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in use | 2020/2021
68 | Renovation of Chepng'ombe Health Facility | Renovation of Chepng'ombe Health Facility | Improved infrustructure |  | D5279 | Non-Residential buildings | BORABU | Esise | N/A | Primary Health Care | Health Services | Glennsteam Engineering Works Limited | N/A | 2021-12-05 | 2021-12-11 | 2021-12-11 | 12005806 | 12005806 |  | THS-UCP | World Bank(THS-UCP) | 0 | 12005806 | 12005806 |  | 12005806 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in use | 2020/2021
69 | Rehabilitation of Drive Way and Parking at Nyamira County Referral Hospital | Rehabilitation of Drive Way (Cabros) and Parking at Nyamira County Referral Hospital | Improved infrustructure | Rehabilitated drive way with cabros | D5267 | Non-Residential buildings | NYAMIRA SOUTH | Township | N/A | Medical Services | Health Services | Interstate Company Limited | N/A | 24/05/2021 | 24/12/2021 | 24/12/2021 | 18126920 | 18126920 |  | THS-UCP | World Bank(THS-UCP) | 0 | 18126920 | 18126920 |  | 18126920 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed and in use | 2020/2021
70 | Completion of OPD block at Isoge Health Facility | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | BORABU | Esise | N/A | Primary Health Care | Health Services | Ikobex Company Limited | N/A | 2022-12-04 | 2022-12-10 | 2022-12-10 | 4998670 | 4998670 |  | CGN | N/A | 4998670 | 0 | 3499069 | 70% | 3499069 | 0 | 1499601 | On Going | 82% | 82% | Inadequate budgetary allocation |  |  |  | No | Compete | Contractual | No | N/A | No | N/A | No | N/A |  | 2021/2022
71 | Renovation of Mortuary and Installation of a New Cooling System at Nyamira County Referral |  | Improved infrustructure |  | D5267 | Non-Residential buildings | NYAMIRA SOUTH | Township | N/A | Medical Services | Health Services | Samodam Holdings Limited | N/A | 13/04/2022 | 13/10/2022 | 13/10/2022 | 9040205 | 9040205 |  | CGN | N/A | 9040205 | 0 | 5992480.7 | 66.2% | 5992480.7 | 0 | 3047724 | On Going | 98% | 98% | N/A | N/A | N/A | N/A | No | Compete | Contractual | No | N/A | No | N/A | No | N/A | Almost complete but in use | 2021/2022
72 | Construction and Completion of Outpatient Block at Nyamira County Industrial Park – Sironga |  | Improved infrustructure |  | D5279 | Non-Residential buildings | NYAMIRA SOUTH | Bogichora | N/A | Primary Health Care | Health Services | Jemocomm General Company Limited | N/A | 2023-07-06 | 2023-07-11 | 2023-07-11 | 4,475,868,80 | 4,475,868,80 |  | CGN | N/A | 4,475,868,80 | 0 | 3093741 | 65% | 3093741 | 0 | 1382125 | On Going | 90% | 90% | N/A | N/A | N/A | N/A | No | Compete | Contractual | No | N/A | No | N/A | No | N/A | Almost complete | 2023/2024
73 | Construction and Completion of Twin Staff House at Nyaigesa Health Facility | Construction and Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | NYAMIRA SOUTH | Nyamaiya | N/A | Primary Health Care | Health Services | Dorosem Construction Limited | N/A | 2023-07-06 | 2023-07-11 | 2023-07-11 | 4786403.6 | 4786403.6 |  | CGN | N/A | 4786403.6 | 0 | 2703393 | 56.5% | 2703393 | 0 | 2083011 | On Going | 75% | 75% | Contractor abandoned site |  |  |  | No | Compete | Contractual | No | N/A | No | N/A | No | N/A |  | 2023/2024
74 | Construction of Etono Health Centre Maternity Wards | Construction of Etono Health Centre Maternity Wards | Improved infrustructure | Comlete Maternity Wards | D5279 | Non-Residential buildings | NYAMIRA NORTH | Bomwagamo | N/A | Primary Health Care | Health Services | Mickyoung Investments Limited | N/A | 2024-04-09 | 2024-10-09 | 2024-10-09 | 4890330 | 4890330 |  | CGN | N/A | 4890330 | 0 | 2502530 | 51% | 2502530 | 0 | 2388300 | On Going | 51% | 51% |  |  |  |  | No | Compete | Contractual | No | N/A | No | N/A | No | N/A |  | 2023/2024
75 | Construction of Toilet and Refurbishing of Nyabonge Dispensary | Construction of Toilet and Refurbishing of Nyabonge Dispensary | Improved infrustructure | Refurbishes Nyabonge Dispensary | D5279 | Non-Residential buildings | NYAMIRA NORTH | Itibo | N/A | Primary Health Care | Health Services | Chamn Limited | N/A | 2024-05-06 | 2024-11-06 | 2024-11-06 | 4999999 | 4999999 |  | CGN | N/A | 4999999 | 0 | 4999999 | 100% | 4999999 | 0 | 0 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A |  | 2023/2024
76 | Construction of OPD at Biticha Morera Dispensary | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | MASABA NORTH | Rigoma | N/A | Primary Health Care | Health Services | D & O Solutions Limited | N/A | 2024-04-09 | 2024-10-09 | 2024-10-09 | 3189680 | 3189680 | 1000000 | CGN | N/A | 3189680 | 0 | 1900000 | 59.6% | 1900000 | 0 | 1289680 | On Going | 65% | 65% | Inadequate budgetary allocation |  |  |  | Yes | Compete | Contractual | No | N/A | No | N/A | No | N/A |  | 2023/2024
77 | Construction and Completion of Outpatient Block at Nyangoso Health Facility | Construction of OPD Block with 2 door pit latrine | Improved infrustructure | Complete OPD Block with 2 door pit latrine | D5279 | Non-Residential buildings | NYAMIRA SOUTH | Township | N/A | Primary Health Care | Health Services | Fampe Heritage Solutions Limited | N/A | 2024-04-30 | 2024-10-30 | 2024-10-30 | 4221850 | 4221850 |  | CGN | N/A | 4221850 | 0 | 0 | 0% | 0 | 0 | 4221850 | On Going | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Almost complete | 2023/2024
78 | Completion of Staff House and Fencing at Isicha Health Facility | Completion of twin staff house with two No.door pit latrine | Improved infrustructure | Complete twin staff house with two No.door pit latrine | D5279 | Non-Residential buildings | NYAMIRA NORTH | Kiabonyoru | N/A | Primary Health Care | Health Services | Kimoko Investments Limited | N/A | 2024-04-09 | 2024-10-09 | 2024-10-09 | 2499815 | 2499815 |  | CGN | N/A | 2499815 | 0 | 0 | 100% | 0 | 0 |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | No |  | N/A | No | N/A | No | N/A | No | N/A | Completed but not in use | 2023/2024
79 | Construction of 30No. vending platforms, supply, delivery, installation, testing and commissioning of 25No solar powered street lights in Keroka block B in Nyamira County | Construction of 30No. vending platforms, supply, delivery, installation, testing and commissioning of 25No solar powered street lights in Keroka block B in Nyamira County | Improved infrustructure | Complete 30No. vending platforms, supply, delivery, installation, testing and commissioning of 25No solar powered street lights in Keroka block B in Nyamira County | D5279 | Non-Residential buildings | MASABA NORTHRigoma |  | N/A | Lands, Housing, Physical Planning & Urban Development | Lands, Housing, Physical Planning & Urban Development |  | N/A | 10.04.2024 | 30.09.2025 | Ongoing | 20000000 | 20000000 |  | KUSP | World Bank | Nil | 20000000 | 20000000 | 100% |  | 0 |  | On Going |  |  | N/A | N/A | [12 empty] | 2024/2025
80 | Construction of roads, footpaths, storm water, drainage, public lighting, water,& sanitation and social amenities for Keroka block B settlement in Nyamira County | Construction of roads, footpaths, storm water, drainage, public lighting, water,& sanitation and social amenities for Keroka block B settlement in Nyamira County | Improved infrustructure | Complete roads, footpaths, storm water, drainage, public lighting, water,& sanitation and social amenities for Keroka block B settlement in Nyamira County | D5279 | Non-Residential buildings | MASABA NORTH | Rigoma | N/A | Lands, Housing, Physical Planning & Urban Development | Lands, Housing, Physical Planning & Urban Development |  | N/A | 10.04.2024 | 02.11.2025 | Ongoing | 84189603.32 | 84189603.32 |  | KUSP | World Banks | Nil | 84189603.32 | 84189603.32 | 100% |  | 0 |  | On Going |  |  | N/A | N/A | [12 empty] | 2024/2025
81 | Proposed construction and completion of Manga Stadium Sports/Football Pitch and Running Truck | Construction and completion of Manga Stadium Sports/Football Pitch and Running Truck | Improved infrustructure | Completed Stadium Sports/ Football Pitch and Running Truck at Manga | D5279 | Non-Residential buildings | MANGA | Manga | N/A | Gender, Youth, Sports and Culture | Gender, Youth, Sports and Culture |  | N/A | 20/05/2019 | 30/06/2023 | Stalled | 20301660.54 | 20301660.54 |  | GoK | N/A | 20301660.54 | 20301660.54 | 17375886 | 85.59% | 17375886 | [19 empty] | 2024/2025
82 | Construction and completion of ECDE Classroom at Kenyoro Primary in Esise Ward | Construction and completion of ECDE Classroom at Kenyoro Primary in Esise Ward | Improved infrustructure | Completed ECDE Classroom at Kenyoro Primary | D5280 | Non-Residential buildings | BORABU | Esise | N/A | Education, ICT and Vocational Training | Education, ICT and Vocational Training |  | N/A | 10-12-2024 | 10-06-2025 | Completed | 3999500 | 3999500 |  | GoK |  | 3999500 | N/A | [22 empty] | 2024/2025
83 | Construction and completion of ECDE Classroom at Ritibo Primary in Gesima Ward | Construction and completion of ECDE Classroom at Ritibo Primary in Gesima Ward | Improved infrustructure | Completed ECDE Classroom at Ritibo Primary | D5281 | Non-Residential buildings | MASABA NORTH | Gesima | N/A | Education, ICT and Vocational Training | Education, ICT and Vocational Training |  | N/A | 12-08-2024 | 11-01-2025 | Ongoing | 3498159.8 | 3498159.8 |  | GoK |  | 3498159.8 | N/A | [22 empty] | 2024/2025
84 | Construction and completion of ECDE Classroom at Omobiro Primary in Bokeira Ward | Construction and completion of ECDE Classroom at Omobiro Primary in Bokeira Ward | Improved infrustructure | Completed ECDE Classroom at Omobiro Primary | D5282 | Non-Residential buildings | NYAMIRA NORTH | Bokeira | N/A | Education, ICT and Vocational Training | Education, ICT and Vocational Training |  | N/A | 12-08-2024 | 11-01-2025 | Ongoing | 3498159.8 | 3498159.8 |  | GoK |  | 3498159.8 | N/A | [22 empty] | 2024/2025
85 | Construction and completion of ECDE Classroom at Simbauti Primary in Nyansiongo Ward | Construction and completion of ECDE Classroom at Simbauti Primary in Nyansiongo Ward | Improved infrustructure | Completed ECDE Classroom at Simbauti Primary | D5283 | Non-Residential buildings | BORABU | Nyansiongo | N/A | Education, ICT and Vocational Training | Education, ICT and Vocational Training |  | N/A | 21-06-2023 | 21-12-2023 | Ongoing | 3196922 | 3196922 |  | GoK |  | 3196922 | N/A | [22 empty] | 2024/2025
86 | Construction and completion of ECDE at Kenyoro Primary in Itibo Ward | Construction and completion of ECDE at Kenyoro Primary in Itibo Ward | Improved infrustructure | Completed ECDE Classroom at Kenyoro Primary | D5283 | Non-Residential buildings | NYAMIRA NORTH | Itibo | N/A | Education, ICT and Vocational Training | Education, ICT and Vocational Training |  | N/A | 2024-12-08 | 2025-11-01 | Ongoing | 3180190 | 3180190 |  | GoK | N/A | 3180190 | N/A | [22 empty] | 2024/2025
87 | Proposed Construction of water Tank & Distribution of water from Ribariri Water Project in Magwagwa Ward | Proposed Construction of water Tank & Distribution of water from Ribariri Water Project in Magwagwa Ward | Improved Water Supply | Water distributed | D5284 |  | NYAMIRA NORTH | Magwagwa |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation |  | N/A | 19.06.2025 | 18.12.2025 | 18.12.2025 | 4979053.27 | 4979053.27 |  | FLLoCa | World Bank | 0 | 4979053.27 | 4979053.27 | 100% | 4979053.27 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
88 | Proposed Equipping and Distribution of Tonga Omonuri Borehole in Nyamaiya Ward | Proposed Equipping and Distribution of Tonga Omonuri Borehole in Nyamaiya Ward | Improved Water Supply | Water distributed | D5285 |  | NYAMIRA NORTH | Nyamaiya |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation |  | N/A | 19.06.2025 | 18.12.2025 | 18.12.2025 | 3644966.42 | 3644966.42 |  | FLLoCa | World Bank | 0 | 3644966.42 | 3644966.42 | 100% | 3644966.42 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
89 | Proposed Rehabilitation of Obwari Borehole in Ekerenyo Ward | Proposed Rehabilitation of Obwari Borehole in Ekerenyo Ward | Improved Water Supply | Water distributed | D5286 |  | NYAMIRA NORTH | Ekerenyo |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation |  | N/A | 19.06.2025 | 18.12.2025 | 18.12.2025 | 1199225.16 | 1199225.16 |  | FLLoCa | World Bank | 0 | 1199225.16 | 1199225.16 | 100% | 1199225.16 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
90 | Proposed Rehabilitation of Nyangena Borehole in Bosamaro Ward | Proposed Rehabilitation of Nyangena Borehole in Bosamaro Ward | Improved Water Supply | Water distributed | D5287 |  | NYAMIRA NORTH | Bosamaro |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation |  | N/A | 19.06.2025 | 18.12.2025 | 18.12.2025 | 1496268.75 | 1496268.75 |  | FLLoCa | World Bank | 0 | 1496268.75 | 1496268.75 | 100% | 1496268.75 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
91 | Proposed Rehabilitation of Gesure Borehole in Manga Ward | Proposed Rehabilitation of Gesure Borehole in Manga Ward | Improved Water Supply | Water distributed | D5288 |  | NYAMIRA SOUTH | Manga |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation |  | N/A | 19.06.2025 | 18.12.2025 | 18.12.2025 | 1499995 | 1499995 |  | FLLoCa | World Bank | 0 | 1499995 | 1499995 | 100% | 1499995 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
92 | Proposed Construction and Protection of Water Springs in Itibo Ward | Proposed Construction and Protection of Water Springs in Itibo Ward | Improved Water Supply | Water distributed | D5289 |  | NYAMIRA NORTH | Itibo |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation |  | N/A | 19.06.2025 | 18.12.2025 | 18.12.2025 | 4944823 | 4944823 |  | FLLoCa | World Bank | 0 | 4944823 | 4944823 | 100% | 4944823 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
93 | Proposed Construction and Protection of Water Springs in Bokeira Ward | Proposed Construction and Protection of Water Springs in Bokeira Ward | Improved Water Supply | Water distributed | D5290 |  | NYAMIRA NORTH | Bokeira |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation |  | N/A | 19.06.2025 | 18.12.2025 | 18.12.2025 | 3955858.4 | 3955858.4 |  | FLLoCa | World Bank | 0 | 3955858.4 | 3955858.4 | 100% | 3955858.4 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
94 | Restoration of Gesebei dam | Restoration of Gesebei dam | Improved Water Supply | Water distributed | [5 empty] | Envirinment and Natural Resources | Envirinment and Natural Resources | Nuclear Vision Limited | N/A | 20.02.2025 | 08.09.2025 | 08.09.2026 | 4496928.67 | 4496928.67 |  | FLLoCa | World Bank | 0 | 4496928.67 | 4496928.67 | 100% | 4496928.67 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
95 | Construction of Kebirigo market Material recovery facility | Construction of Kebirigo market Material recovery facility | Waste Management | Managed Waste |  |  | NYAMIRA SOUTH | Bonyamatuta |  | Envirinment and Natural Resources | Envirinment and Natural Resources | Wycomilsa International Limited | N/A | 20.02.2025 | 25.08.2025 | 25.08.2025 | 1248998.39 | 1248998.39 |  | FLLoCa | World Bank | 0 | 1248998.39 | 1248998.39 | 100% | 1248998.39 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
96 | Construction of Keroka Material recovery facility | Construction of Keroka Material recovery facility | Waste Management | Managed Waste |  |  | MASABA | Rigoma |  | Envirinment and Natural Resources | Envirinment and Natural Resources | Didasky Limited | N/A | 20.02.2025 | 25.08.2025 | 25.08.2025 | 1240412.01 | 1240412.01 |  | FLLoCa | World Bank | 0 | 1240412.01 | 1240412.01 | 100% | 1240412.01 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
97 | Construction of Ikonge market Material recovery facility | Construction of Ikonge market Material recovery facility | Waste Management | Managed Waste |  |  | NYAMIRA NORTH | Ekerenyo |  | Envirinment and Natural Resources | Envirinment and Natural Resources | Fampe Heritage Building Solutions ltd | N/A | 20.02.2025 | 25.08.2025 | 25.08.2025 | 1249956.38 | 1249956.38 |  | FLLoCa | World Bank | 0 | 1249956.38 | 1249956.38 | 100% | 1249956.38 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
98 | Construction of Nyansiongo business centre Material recovery facility | Construction of Nyansiongo business centre Material recovery facility | Waste Management | Managed Waste |  |  | BORABU | Nyansiongo |  | Envirinment and Natural Resources | Envirinment and Natural Resources | Sajjoria Africa Limited | N/A | 26.03.2025 | 03.10.2025 | 03.10.2026 | 1245152.74 | 1245152.74 |  | FLLoCa | World Bank | 0 | 1245152.74 | 1245152.74 | 100% | 1245152.74 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
99 | Construction of Miruka market Material recovery facility | Construction of Miruka market Material recovery facility | Waste Management | Managed Waste |  |  | NYAMIRA SOUTH | Nyamaiya |  | Envirinment and Natural Resources | Envirinment and Natural Resources | Bosmak Investments Limited | N/A | 20.02.2025 | 25.08.2025 | 25.08.2025 | 1249860.56 | 1249860.56 |  | FLLoCa | World Bank | 0 | 1249860.56 | 1249860.56 | 100% | 1249860.56 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
100 | Construction of Kemera market Material recovery facility | Construction of Kemera market Material recovery facility | Waste Management | Managed Waste |  |  | NYAMIRA SOUTH | Kemera |  | Envirinment and Natural Resources | Envirinment and Natural Resources | Jutwine Auto Agencies Limited | N/A | 20.02.2025 | 25.08.2025 | 25.08.2025 | 1201412.72 | 1201412.72 |  | FLLoCa | World Bank | 0 | 1201412.72 | 1201412.72 | 100% | 1201412.72 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
101 | Establishment of Nyamira North sub county indigenous tree nursery | Establishment of Nyamira North sub county indigenous tree nursery | Afforestation | Afforestation |  |  | Nyamira North |  |  | Envirinment and Natural Resources | Envirinment and Natural Resources | Janyamosy General Supplies Limited | N/A | 20.02.2025 | 01.09.2025 | 01.09.2025 | 2990147.17 | 2990147.17 |  | FLLoCa | World Bank | 0 | 2990147.17 | 2990147.17 | 100% | 2990147.17 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
102 | Establishment of Nyamira South sub county indigenous tree nursery | Establishment of Nyamira South sub county indigenous tree nursery | Afforestation | Afforestation |  |  | Nyamira South |  |  | Envirinment and Natural Resources | Envirinment and Natural Resources | Samonya International Limited | N/A | 20.02.2025 | 01.09.2025 | 01.09.2025 | 2998397 | 2998397 |  | FLLoCa | World Bank | 0 | 2998397 | 2998397 | 100% | 2998397 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
103 | Establishment of Borabu sub county indigenous tree nursery | Establishment of Borabu sub county indigenous tree nursery | Afforestation | Afforestation |  |  | BORABU |  |  | Envirinment and Natural Resources | Envirinment and Natural Resources | Denoworks Company Limited | N/A | 20.02.2025 | 01.09.2025 | 01.09.2025 | 2998803.37 | 2998803.37 |  | FLLoCa | World Bank | 0 | 2998803.37 | 2998803.37 | 100% | 2998803.37 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
104 | Establishment of Masaba North sub county indigenous tree nursery | Establishment of Masaba North sub county indigenous tree nursery | Afforestation | Afforestation |  |  | Masaba North |  |  | Envirinment and Natural Resources | Envirinment and Natural Resources | Ombany International Limited | N/A | 26.03.2025 | 03.10.2025 | 03.10.2026 | 2998397 | 2998397 |  | FLLoCa | World Bank | 0 | 2998397 | 2998397 | 100% | 2998397 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
105 | Establishment of Manga sub county indigenous tree nursery | Establishment of Manga sub county indigenous tree nursery | Afforestation | Afforestation |  |  | MANGA |  |  | Envirinment and Natural Resources | Envirinment and Natural Resources | Bull Null Limited | N/A | 20.02.2025 | 01.09.2025 | 01.09.2026 | 2999116.66 | 2999116.66 |  | FLLoCa | World Bank | 0 | 2999116.66 | 2999116.66 | 100% | 2999116.66 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
106 | Construction of Nyamus market Material recovery facility | Construction of Nyamus market Material recovery facility | Waste Management | Managed Waste |  |  | NYAMIRA NORTH | Bokeira |  | Envirinment and Natural Resources | Envirinment and Natural Resources | Tononta Enterprises | N/A | 05.05.2025 | 08.12.2025 | 08.12.2026 | 1249544.75 | 1249544.75 |  | FLLoCa | World Bank | 0 | 1249544.75 | 1249544.75 | 100% | 1249544.75 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
107 | Ekegoro Borehole Water drilling and Casing project. | Ekegoro Borehole Water drilling and Casing project. | Improved Water Supply | Water distributed |  |  | NYAMIRA NORTH | Ekerenyo |  | Envirinment and Natural Resources | Envirinment and Natural Resources | Sleyworks Limited | N/A | 21.02.2025 | 25.08.2025 | 25.08.2026 | 2404970 | 2404970 |  | FLLoCa | World Bank | 0 | 2404970 | 2404970 | 100% | 2404970 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
108 | Equipping and Distribution of Ekegoro Borehole Project | Equipping and Distribution of Ekegoro Borehole Project | Improved Water Supply | Water distributed | [5 empty] | Envirinment and Natural Resources | Envirinment and Natural Resources | Kishor Group Limited | N/A | 26.03.2025 | 03.10.2025 | 03.10.2026 | 3999680 | 3999680 |  | FLLoCa | World Bank | 0 | 3999680 | 3999680 | 100% | 3999680 | NIL | NIL | Completed | 100% | [15 empty] | 2024/2025
109 | Proposed Rehabilitation of Kenyerere Borehole | Proposed Rehabilitation of Kenyerere Borehole | Improved Water Supply | Water distributed | [5 empty] | Envirinment and Natural Resources | Envirinment and Natural Resources | Ndubi Holdings Limited | N/A | 19.06.2025 | 19.12.2025 | 19.12.2025 | 1142942.78 | 1142942.78 |  | FLLoCa | World Bank | 0 | 1142942.78 | 1142942.78 | 100% | 1142942.78 | NIL | NIL | Completed | 100% | [15 empty] | 2025/2026
110 | Proposed Rehabilitation of Marani Borehole | Proposed Rehabilitation of Marani Borehole | Improved Water Supply | Water distributed | [5 empty] | Envirinment and Natural Resources | Envirinment and Natural Resources | Thosar (K) Ltd | N/A | 19.06.2025 | 19.12.2025 | 19.12.2025 | 1405181.4 | 1405181.4 |  | FLLoCa | World Bank | 0 | 1405181.4 | 1405181.4 | 100% | 1405181.4 | NIL | NIL | Completed | 100% | [15 empty] | 2025/2026
111 | REHABILITATION TO NYAMIRA SIDEWALK | [6 empty] | TOWNSHIP |  | Public Works | Public Works | RIANYAKANGI CONSTRUCTION |  | 30/1/2014 | 30/4/2014 |  | 6156120 | 1260000 |  | GOK | [8 empty] | STALLED | [16 empty] | 2013/2014
112 | REHABILITATION AND REPAIR OF KEROKA BUS PARK | [6 empty] | RIGOMA |  | Public Works | Public Works | BLUEHOUSE GENERAL |  | 30/1/2014 | 30/4/2014 |  | 15835160 | 15835160 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
113 | REHABILITATION AND REPAIR OF ACCESS ROAD PARKING | [6 empty] | TOWNSHIP |  | Public Works | Public Works | GRACAN CONSTRUCTION |  | 30/1/2014 | 30/4/2014 |  | 7338160 | 6402330 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
114 | COMPLETION OF NYAMIRA COUNTY COUNCIL PHASE - II | [6 empty] | TOWNSHIP |  | Public Works | Public Works | SAUMO ENTERPRISES |  | 29/4/2014 | 19/08/2014 |  | 18443043 | 18443043 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
115 | REHABILITATION AND MANTAINANCE OF RIONSONGO, NYAISA ,MOROMBA UR-32 | [6 empty] | MANGA |  | Public Works | Public Works | HABO VENTURES |  | 24/4/2014 | 24/7/2014 |  | 9483000 | 9344400 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
116 | AMAKARA,NYARONDE ,KONA C, RIAMANOTI- UR 52 | [6 empty] | NYANSIONGO |  | Public Works | Public Works | BARTUM ENTERPRISES |  | 24/4/2014 | 24/7/2014 |  | 9559560 | 9559560 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
117 | RIAMOSETI,RIOBWOCHA CONSTRUCTION & MAINTAINANCE (UR 23) | [6 empty] | MEKENENE |  | Public Works | Public Works | KAZIMOTO CONSTRUCTION LTD |  | 24/4/2014 | 24/7/2014 |  | 3331578 | 3245416.5 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
118 | MWONGORI MKRT,RIONSONGO ROAD UR-22 | [6 empty] | MEKENENE |  | Public Works | Public Works | KEYRAM CONTRACTORS LTD |  | 24/4/2014 | 24/7/2014 |  | 4603112 | 4484066 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
119 | GUCHA-MARIBA JUNC-NYASWAGO JUNC-AVACADO-MOKOMONI UR-62 | [6 empty] | KIABONYORU |  | Public Works | Public Works | HAVEPARCH |  | 24/4/2014 | 24/7/2014 |  | 9250860.8 | 9011614.4 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
120 | KIJAURI ROCHE -OMOKUA-MASIGE UR-51 | [6 empty] | NYANSIONGO |  | Public Works | Public Works | CHARWINS CO. LTD |  | 24/4/2014 | 24/7/2014 |  | 2694575.6 | 1007217.03 |  | GOK | [8 empty] | STALLED | [16 empty] | 2013/2014
121 | ETANGI-NYANSAKIA SDA/TBC-MEBENO PRY. SCHOOL-RIOMBATI JUCTN UR-43 | [6 empty] | ESISE |  | Public Works | Public Works | CITROLLAM CONTRACTORS |  | 24/4/2014 | 24/7/2014 |  | 11770080 | 11770080 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
122 | KEROKA-KIERIRA-RIKENYE UR-53 | [6 empty] | RIGOMA |  | Public Works | Public Works | VAMALUMBE INTERNATONAL LTD |  | 24/4/2014 | 24/7/2014 |  | 4972500 | 4799833.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
123 | KEROKA POSTA-NYASORE ACADEMY-METAMANYWA UR-55 | [6 empty] | RIGOMA |  | Public Works | Public Works | DAMSI INTERNATIONAL CO.LTD |  | 24/4/2014 | 24/7/2014 |  | 8430300 | 8430300 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
124 | KIENDEGE-CHARARA-NYAGECHECHE UR-28 | [6 empty] | KEMERA |  | Public Works | Public Works | VIGODA ENTERPRISES |  | 24/4/2014 | 24/7/2014 |  | 8302750 | 8302750 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
125 | KIENDEGE-NYACHICHI-OMOGONCHORO UR-29 | [6 empty] | KEMERA |  | Public Works | Public Works | ELIMAX ENTERPRISES LTD |  | 24/4/2014 | 24/7/2014 |  | 2345069 | 940663.6 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
126 | TOMBE-NYAGUKU-MIRIRI-GEKANO TBC UR-1 | [6 empty] | MAGOMBO |  | Public Works | Public Works | GESISI ENTERPRISES LTD |  | 24/4/2014 | 24/7/2014 |  | 6550984 | 6381562 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
127 | RIABICHANGA-RIANYABIO ROAD UR-2 | [6 empty] | MAGOMBO |  | Public Works | Public Works | NAKITONGO HARDWARE AND CONSTRUCTION |  | 24/4/2014 | 24/7/2014 |  | 4223096 | 4113877.1 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
128 | RIAKWORO-RISA ESANI-KEBUKO-GESABAKWA UR-6 | [6 empty] | GESIMA |  | Public Works | Public Works | ROREM CONTRACTORS |  | 24/4/2014 | 24/7/2014 |  | 2429620 | 2388878.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
129 | RITONGO-MATUTU-IRANYA UR-7 | [6 empty] | GESIMA |  | Public Works | Public Works | BREMA CONSTRUCTION CO.LTD |  | 24/4/2014 | 24/7/2014 |  | 9874242 | 9148689.67 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
130 | GEKANO TBC-KEGOGI TBC-NYAKEMOGWA SDA-ERONGE SDA UR-37 | [6 empty] | GACHUBA |  | Public Works | Public Works | REAMIC INVESTMENTS |  | 24/4/2014 | 24/7/2014 |  | 6760480 | 6585640.02 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
131 | MOTURUMESI-RIABAKA-GETENI-KEBOBA-KIOMOSO UR-38 | [6 empty] | GACHUBA |  | Public Works | Public Works | MANKONE CONSTRUCTION LTD |  | 24/4/2014 | 24/7/2014 |  | 2038198.07 | 1985410 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
132 | RIABOTO-BIGOGO UR-31 | [6 empty] | MANGA |  | Public Works | Public Works | MWANGOMA ENGINEERING CO. LTD |  | 24/4/2014 | 24/7/2014 |  | 5417000 | 4454405.18 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
133 | NYAKARANGA JUNC-KEBOBORA-NYAKARANGA PRI.-OMOBIRO UR-4 | [6 empty] | BOKEIRA |  | Public Works | Public Works | MAGINIFICA CONTRACTORS |  | 24/4/2014 | 24/7/2014 |  | 9861208.72 | 9004643.44 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
134 | ORWAKI BR-NYAMUSI-EGOTOTO UR-5 | [6 empty] | BOKEIRA |  | Public Works | Public Works | KEBSAN (K) LTD |  | 24/4/2014 | 24/7/2014 |  | 1670980 | 1627765 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
135 | EKONA-NYAGEKOBOKOBO-MAGENA MARABU-ESERETI-BISEMBE UR-19 | [6 empty] | MAGWAGWA |  | Public Works | Public Works | TAZAMA BUILDERS |  | 24/4/2014 | 24/7/2014 |  | 8098950 | 8167646.9 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
136 | MATORORA-ISINTA-CHINA-NYASIO-OMOKIRONDO UR-20 | [6 empty] | ITIBO |  | Public Works | Public Works | MARK & SONS CONSTRACTIONS CO.LTD |  | 24/4/2014 | 24/7/2014 |  | 8411972 | 8194421 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
137 | EKERENYO-KIEMUMA-NYAMEKO UR-40 | [6 empty] | EKERENYO |  | Public Works | Public Works | STEM INVESTMENT |  | 24/4/2014 | 24/7/2014 |  | 8212858 | 8212858 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
138 | NYANGOSO-NYAMIACHO-KIOGE MARKET-BOMBO CENTRAL-KEGOGI-NYAMONURI UR-16 | [6 empty] | BOMWAGAMO |  | Public Works | Public Works | WASTE LIFE CONSTRUCTIONS LTD |  | 24/4/2014 | 24/7/2014 |  | 7528342 | NIL |  | GOK | [8 empty] | STALLED | [16 empty] | 2013/2014
139 | MIRUKA-NYANDOCHE IBERE UR-18 | [6 empty] | NYAMAIYA |  | Public Works | Public Works | NRIASI |  | 24/4/2014 | 24/7/2014 |  | 9901891 | 2797699.2 |  | GOK | [8 empty] | STALLED | [16 empty] | 2013/2014
140 | BWONYANGI-IKONGE DISPENSARY-BONYAMORITO UR-34 | [6 empty] | BOGICHORA |  | Public Works | Public Works | SOFAMO ENTERPRISES LTD |  | 24/4/2014 | 24/7/2014 |  | 5258280 | 4745225 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
141 | GESERO-GESIAGA SEC-BOKAYA-EKERUBO-SIRONGA UR-8 | [6 empty] | BOSAMARO |  | Public Works | Public Works | AGAPE INVESTMENT |  | 24/4/2014 | 24/7/2014 |  | 6741618 | 6741618 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
142 | NYABITE-NYANGOSO-NYAIRICHA-BOBONDO-KEBIRIGO UR-50 | [6 empty] | TOWNSHIP |  | Public Works | Public Works | NYACHIT CONSTRUCTION AND SUPPLIERS |  | 24/4/2014 | 24/7/2014 |  | 10421208 | 9716642.22 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
143 | KEBIRIGO-KABATIA-RIAMASARE-BOKIMO-KENYENYA UR 11 | [6 empty] | BONYAMATUTA |  | Public Works | Public Works | INTERSPAN CONTRACTORS |  | 24/4/2014 | 24/7/2014 |  | 3339640 | 2869344 |  | GOK | [8 empty] | STALLED | [16 empty] | 2013/2014
144 | NYABITE-RANGENYO-NYAKUNGURU-BONYUNYU UR-17 | [6 empty] | NYAMAIYA |  | Public Works | Public Works | ROMACO ENTERPRISES LTD |  | 24/4/2014 | 24/7/2014 |  | 1443550 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
145 | GESONSO-NYANGOSO AND GESORE JUNC-BUNDO UR-47/48 | [6 empty] | TOWNSHIP |  | Public Works | Public Works | NANGOVE INTERNATIONAL |  | 24/4/2014 | 24/7/2014 |  | 5720656 | 1191600 |  | GOK | [8 empty] | STALLED | [16 empty] | 2013/2014
146 | NYACHURURU - NYANGENA-TBC UR 10 | [6 empty] | BOSAMARO |  | Public Works | Public Works | VIDIC LTD |  | 24/4/2014 | 24/7/2014 |  | 4949882.4 | 4591767.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
147 | NYAMOKERI–EMONGA UR 35 | [6 empty] | BOGICHORA |  | Public Works | Public Works | MOSBOKO CIVIL ENG LTD |  | 24/4/2014 | 24/7/2014 |  | 2876800 | 2846830 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
148 | KEBIRIGO-KABATIA-RIAMASARE-BOKIMO-KENYENYA-UR-11B | [6 empty] | BONYAMATUTA |  | Public Works | Public Works | HAMO CONSTRUCTIONS |  | 24/4/2014 | 24/7/2014 |  | 5459308 | 5292932 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
149 | MANGA STADIUM CGN/143/2013-14 | [6 empty] | MANGA |  | Public Works | Public Works | ELIMAX ENTERPRISES |  | 15/4/2015 | 15/12/2015 |  | 62393384 | 45019998 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
150 | PROPOSED SECURITY FENCE FOR GOVERNOR'S RESIDENCE | [6 empty] | TOWNSHIP |  | Public Works | Public Works | HYDROBUILD CONSTRUCTION |  | 20/6/2014 | 19/9/2014 |  | 13955960 | 10922328 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
151 | RIAGISEMBE FOOTBRIDGE CGN/T019/2014-2015 | [6 empty] | KITUTU MASABA SUB - COUNTY |  | Public Works | Public Works | BREMA CONSTRUCTION LTD |  | 28/7/2015 | 28/10/2015 |  | 4529034 | 4529034 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
152 | RIAGWARO FOOTBRIDGE CGN/T020/2014-2015 | [6 empty] | NORTH MUGIRANGO |  | Public Works | Public Works | SONJE INVESTMENTS LTD |  | 28/7/2015 | 28/10/2015 |  | 4259785.64 | 4259785.64 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
153 | KAAGWA FOOTBRIDGE CGN/T021/2014- 2015 | [6 empty] | BORABU |  | Public Works | Public Works | BOWMANS ENTERPRISES LTD |  | 28/7/2015 | 28/10/2015 |  | 5155199.5 | 5155199.5 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
154 | ITONGO SENGERA BOX CULVERT CGN/T022/2014-15 | [6 empty] | RIGOMA |  | Public Works | Public Works | AJAZI INVESTMENTS LTD |  | 28/7/2015 | 28/10/2015 |  | 7070061 | 7070061 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
155 | RIAPIMA BRIDGE AND APPROACH ROAD CGN/T023/2014-2015 | [6 empty] | BOGICHORA |  | Public Works | Public Works | MOCAM ROAD WORKS |  | 28/7/2015 | 28/10/2015 |  | 16457549.01 | 16457549.01 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
156 | RIASAGWE FOOTBRIDGE CGN/T024/2014-2015 | [6 empty] | WEST MUGIRANGO |  | Public Works | Public Works | ZABELLA GENERAL LIMITED |  | 28/7/2015 | 28/10/2015 |  | 4212014.752 | 4212014.75 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
157 | NYAMACHE MAYA BOX CULVERT CGN/T025/2014-15 | [6 empty] | TOWNSHIP |  | Public Works | Public Works | CANON ENTERPRISES LTD |  | 28/7/2015 | 28/10/2015 |  | 5344908 | 5344908 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
158 | CONSTRUCTION OF SEPTIC TANK, TOILET BLOCK AND GENERATOR HOUSE | [6 empty] | TOWNSHIP |  | Public Works | Public Works | HEMOOT CONSTRUCTION |  | 25/1/2016 |  |  | 5380776 | 3684894 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2014/2015
159 | MULTI-PURPOSE FIRE ENGINE TRUCK | [8 empty] | Public Works | Public Works | SUPPLIES BRANCH |  |  |  |  | 30162000 |  |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
160 | TERMINAL FACILITY AT KEBIRIGO CGN/T043/2014/2015 | [6 empty] | BONYAMATUTA |  | Public Works | Public Works | HAVEPARCH ENT. LTD |  | 2015-09-11 | 2016-01-02 |  | 9700476.6 | 9700475.74 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
161 | TERMINAL FACILTY AND BACKSTREET AT NYANSIONGO CGN/T044/2014/2015 | [6 empty] | NYANSIONGO |  | Public Works | Public Works | MANKONE CONSTRUCTION LTD |  | 2015-09-11 | 2016-01-02 |  | 4667174.16 | 4640718 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
162 | DEVELOPING AND UPGRADING OF CAR LOTS IN NYAMIRA COUNTY CGN/T045/2014-2015 | [6 empty] | TOWNSHIP |  | Public Works | Public Works | BOFLOS ENTERPRISES |  | 2015-09-11 | 2016-01-02 |  | 9768947.54 | 9765939.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
163 | CULVERTS AND DRAINAGE WORKS WITHIN NYAMIRA COUNTY CGN/T046/2014-2015 | [6 empty] | TOWNSHIP |  | Public Works | Public Works | SINCERE INVESTMENT |  | 2015-09-11 | 2016-01-02 |  | 9969272 | 3582091.6 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2014/2015
164 | BACKSTREET AT KEROKA IN NYAMIRA COUNTY CGN/T047/2014-2015 | [6 empty] | RIGOMA |  | Public Works | Public Works | SANMIC GENERAL CONSTRUCTION |  | 2015-09-11 | 2016-01-02 |  | 7375061.88 | 7375024.58 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
165 | EGESIERI-NYABITE-FLORIDA ROAD 1.5 Km. | [6 empty] | TOWNSHIP |  | Public Works | Public Works | JAMES MANYONI |  | 20/10/2015 |  |  | 2374785 | 2374785 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
166 | NYAMWETUREKO-BONDENI ROAD-BONYAMATUTA ROAD | [6 empty] | BONYAMATUTA |  | Public Works | Public Works | JANET KUMENDA |  | 20/10/2015 |  |  | 3015285 | 3015285 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
167 | NYABARA IBERE-BOKIMO ROAD-BONYAMATUTA ROAD 2.4Km | [6 empty] | BONYAMATUTA |  | Public Works | Public Works | JAMES MANYONI |  | 20/10/2015 |  |  | 1643400 | 1643400 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
168 | ERONGE-KENYERERE-KABAATIA ROAD 3.8 Km | [6 empty] | BONYAMATUTA |  | Public Works | Public Works |  |  | 20/10/2015 |  |  | 1369500 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2014/2015
169 | BUNDO-NYAIGESA-KEERA ROAD 4Km. | [6 empty] | BONYAMATUTA |  | Public Works | Public Works | RICHARD OKEYO |  | 20/10/2015 |  |  | 684750 | 684750 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2014/2015
170 | BOX CULVERT AT RIANGWENYI | [6 empty] | GESIMA |  | Public Works | Public Works | HEZRON OTWORI |  | 20/10/2015 |  |  | 1533220 | 1533220 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
171 | EBATE-ICHUNI TBC ROAD | [8 empty] | Public Works | Public Works |  |  | 14/12/2015 |  |  | 1585500 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2014/2015
172 | RIANYAMWEYA-DAMSIDE ROAD | [8 empty] | Public Works | Public Works |  |  | 14/12/2015 |  |  | 1356500 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2014/2015
173 | KEGINGA-RIONSONGO ROAD | [8 empty] | Public Works | Public Works | JANET KUMENDA |  | 14/12/2015 |  |  | 1598500 | 1598500 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2014/2015
174 | HIRE OF ROAD CONSTRUCTION EQUIPMENTS (EXECUVATORS) | [6 empty] | COUNTY-WIDE |  | Public Works | Public Works | MINISTRY OF TRANSPORT & MECHANICAL TRANSPORT FUND |  | 2016-08-06 |  |  | 25477500 | 25477500 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
175 | HIRE OF ROAD CONSTRUCTION EQUIPMENTS | [6 empty] | COUNTY-WIDE |  | Public Works | Public Works | MINISTRY OF TRANSPORT & MECHANICAL TRANSPORT FUND |  | 28/6/2016 |  |  | 124522500 | 124522500 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
176 | REPAIR & MAINTANANCE OF MOBAMBA CATHOLIC-BOMBWOBO-NYAKEMINCHA ROAD NYCG/KRB/Q310/2015-2016 | [6 empty] | BONYAMATUTA |  | Public Works | Public Works | HONET CO. LTD |  | 24/11/2016 | 22/6/2017 |  | 1, 997,995.60 | 1997995 |  | GRANT | [8 empty] | COMPLETE | [16 empty] | 2015/2016
177 | REPAIR & MAINTANANCE OF OTANYORE-ETONO-BONYUNYUNYCG/KRB/Q311/2015-2016 | [6 empty] | BOGICHORA |  | Public Works | Public Works | DENAM SERVICES |  | 24/11/2016 | 22/6/2017 |  | 1646051.6 | 1646051.6 |  | GRANT | [8 empty] | COMPLETE | [16 empty] | 2015/2016
178 | REPAIR & MAINTANANCE OF GESERO-NDURUMO ROAD NYCG/KRB/Q312/2015-2016 | [6 empty] | BOSAMARO |  | Public Works | Public Works | MWABO ELECTRO MECHANICAL LTD |  | 24/11/2016 | 22/6/2017 |  | 2, 523,593 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
179 | REPAIR & MAINTANANCE OF MIRUKA-ATEMOROADNYCG/KRB/Q313/2015-2016 | [6 empty] | NYAMAIYA |  | Public Works | Public Works | SPILWAY K.LTD |  | 24/11/2016 | 22/6/2017 |  | 2067111.9 | 2067111.9 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
180 | REPAIR AND MAINTANANCE OF CO-OP BANK-SEN. KEBASO SEC SCH ROADNYCG/KRB/Q314/2015-2016 | [6 empty] | TOWNSHIP |  | Public Works | Public Works | Hemoot Construction Ltd |  | 24/11/2016 | 22/6/2017 |  | 1, 425,848.00 | 1425848 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
181 | REPAIR AND MAINTANANCE OF IKONGE-NYAORA-NYAMEKOBO ROADNYCG/KRB/Q315/2015-2016 | [6 empty] | EKERENYO |  | Public Works | Public Works | Trial Zone Enterprises |  | 24/11/2016 | 22/6/2017 |  | 2083128 | 2088128 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
182 | REPAIR & MAINTANANCE OF EKERENYO-KEBABE-KANYANCHA-METHODIST CHURCH-OMWAMBA-RIAMEKI ROAD NYCG/KRB/Q316/2015-2016 | [6 empty] | ITIBO |  | Public Works | Public Works | SHAMEX CONSTRUCTION LTD |  | 24/11/2016 | 22/6/2017 |  | 2,081, 820.01 | 2081820.1 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
183 | REPAIR & MAINTANANCE OF ERONGE-KIOGE ROAD NYCG/KRB/Q317/2015-2016 | [6 empty] | BOMWAGAMO |  | Public Works | Public Works | SACHEM E.A LTD |  | 24/11/2016 | 22/6/2017 |  | 1615137.62 | 1615137.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
184 | REPAIR & MAINTANANCE OF KENYANSORO- MOKARATE-MOTEOMOKAMBA-RIKURUMA-NYABWARORO ROADNYCG/KRB/Q318/2015-2016 | [6 empty] | MAGWAGWA |  | Public Works | Public Works | AUTO STAR AGENCY |  | 24/11/2016 | 22/6/2017 |  | 2, 244,948.40 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
185 | REPAIR & MAINTANANCE OF GESURA-IYWERO BRIDGEROADNYCG/KRB/Q319/2015-2016 | [6 empty] | BOKEIRA |  | Public Works | Public Works | IKOBEX CO. LTD |  | 24/11/2016 | 22/6/2017 |  | 2859472.5 | 2859472.5 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
186 | REPAIR & MAINTANANCE OF RIAMBAKA- RIASAGWEROADNYCG/KRB/Q320/2015-2016 | [6 empty] | MEKENENE |  | Public Works | Public Works | HIMOFIX INVESTMENT LTD |  | 24/11/2016 | 22/6/2017 |  | 1, 737,426.25 | 1737426.25 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
187 | REPAIR & MAINTANANCE OF NYANSIONGO-RIAMOMANYI-SIMBAUT-TINDERET ROAD NYCG/KRB/Q321/2015-2016 | [6 empty] | NYANSIONGO |  | Public Works | Public Works | BHOPAL BUILDING AND CIVIL ENG .LTD |  | 24/11/2016 | 22/6/2017 |  | 1946630.8 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
188 | REPAIR & MAINTANANCE OF NYABIOTO-KIABONYORU-NDURUMO-ONYASWAMU ROAD NYCG/KRB/Q322/2015-2016 | [6 empty] | KIABONYORU |  | Public Works | Public Works | OTEX VENTURES LT |  | 24/11/2016 | 22/6/2017 |  | 2879999.88 | 2879999.88 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
189 | REPAIR & MAINTANANCE OF RIANYASANI-GESABAKWA-RIARATI ROAD NYCG/KRB/Q323/2015-2016 | [6 empty] | ESISE |  | Public Works | Public Works | MIMNET ENGINEERING WORKS LTD |  | 24/11/2016 | 22/6/2017 |  | 2125337.5 | 2125337.5 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
190 | REPAIR AND MAINTANANCE OF MOCHENWA SOCIETY-MOCHENWA DISP.-RIAMARANGA-MOCHENWA PRI SCH ROAD NYCG/KRB/Q324/2015-2016 | [6 empty] | GESIMA |  | Public Works | Public Works | SAUMO ENTERPRICES LTD |  | 24/11/2016 | 22/6/2017 |  | 2137228 | 2137227.5 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
191 | REPAIR AND MAINTANANCE OF RIYABE-KENYERERE TBC ROAD NYCG/KRB/Q325/2015-2016 | [6 empty] | RIGOMA |  | Public Works | Public Works | Jagera Construction Works Ltd |  | 24/11/2016 | 22/6/2017 |  | 2087170 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
192 | REPAIR AND MAINTANANCE OF GIRANGO CF JUNCTION-MASHAURI-RIANYASIMI- KEBIRICHI ROOCHE-RIAMOENGA-KEBOBA TBC-RIAMOSIGISI ROAD NYCG/KRB/Q326/2015-2016 | [6 empty] | GACHUBA |  | Public Works | Public Works | KEVISA CONSTRUCTION LTD |  | 24/11/2016 | 22/6/2017 |  | 2687306.4 | 2687306 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
193 | REPAIR AND MAINTANANCE OF,RIASTEPHENE-BOGWENDO SEC SCH-RIOKENDO ROAD | [6 empty] | MAGOMBO |  | Public Works | Public Works | SANMIC GEN.CONSTRUCTIONS |  | 24/11/2016 | 22/6/2017 |  | 2520680 | 2520680 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
194 | REPAIR AND MAINTANANCE OF NYAIKURO JUNCTION- GESURE ROAD NYCG/KRB/Q328/2015-2016 | [6 empty] | MANGA |  | Public Works | Public Works | REAMIC INVESTMENT CO. LTD |  | 24/11/2016 | 22/6/2017 |  | 2094305 | 2094304.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
195 | REPAIR AND MAINTANANCE OF OMOGONCHORO-KIOMAKONDO ROAD NYCG/KRB/Q329/2015-2016 | [6 empty] | KEMERA |  | Public Works | Public Works | KEYRAM CONTRACTORS LTD |  | 24/11/2016 | 22/6/2017 |  | 1789917.8 | 1789917 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
196 | PROVISION & SUPPLY OF MURRAM 16,700 METERS CUBIC NYCG/Q087/2016-2017 | [6 empty] | MAGWAGWA & MEKENENE |  | Public Works | Public Works | DEXTEROUS LIMITED |  | 20/11/2016 | 16/12/2016 |  | 3340000 | 3340000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
197 | PROVISION & SUPPLY OF MURRAM 16,900 METERS CUBIC NYCG/Q088/2016-2017 | [6 empty] | BOMWAGAMO & MEKENENE |  | Public Works | Public Works | BASECOM INTERNATIONAL LTD |  | 20/11/2016 | 16/12/2016 |  | 3464000 | 3464000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
198 | PROVISION & SUPPLY OF MURRAM 15,000 METERS CUBIC NYCG/Q089/2016-2017 | [6 empty] | BONYAMATUTA |  | Public Works | Public Works | ROPSONS GENERAL STORES |  | 20/11/2016 | 16/12/2016 |  | 3300000 | 3300000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
199 | PROVISION & SUPPLY OF MURRAM 20,000 METERS CUBIC NYCG/Q090/2016-2017 | [6 empty] | BOGICHORA |  | Public Works | Public Works | ENDONO KENYA LIMITED |  | 20/11/2016 | 16/12/2016 |  | 3900000 | 3900000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
200 | PROVISION & SUPPLY OF MURRAM 18,500 METERS CUBIC NYCG/Q091/2016-2017 | [6 empty] | GESIMA & RIGOMA |  | Public Works | Public Works | SAUMO ENTERPRISES |  | 20/11/2016 | 16/12/2016 |  | 3792500 | 3792500 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
201 | PROVISION & SUPPLY OF MURRAM 16,800 METERS CUBIC NYCG/Q092/2016-2017 | [6 empty] | GACHUBA AND MAGOMBO |  | Public Works | Public Works | BOFLOS ENTERPRISES |  | 20/11/2016 | 16/12/2016 |  | 3360000 | 3360000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
202 | PROVISION & SUPPLY OF MURRAM 16,500 METERS CUBIC NYCG/Q093/2016-2017 | [6 empty] | MANGA & TOWNSHIP |  | Public Works | Public Works | AUTOSTAR AGENCY |  | 20/11/2016 | 16/12/2016 |  | 3217500 | 3217500 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
203 | PROVISION & SUPPLY OF MURRAM 15,000 METERS CUBIC NYCG/Q094/2016-2017 | [6 empty] | ESISE |  | Public Works | Public Works | KWANYA INTERGLOBAL |  | 20/11/2016 | 16/12/2016 |  | 3000000 | 3000000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
204 | PROVISION & SUPPLY OF MURRAM 13,000 METERS CUBIC NYCG/Q095/2016-2017 | [6 empty] | NYAMAIYA |  | Public Works | Public Works | SONJE INVESTMENTS |  | 20/11/2016 | 16/12/2016 |  | 2795000 | 2795000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
205 | PROVISION & SUPPLY OF MURRAM 17,000 METERS CUBIC NYCG/Q096/2016-2017 | [6 empty] | EKERENYO AND BOKEIRA |  | Public Works | Public Works | HYMOFIX INVESTMENTS |  | 20/11/2016 | 16/12/2016 |  | 3400000 | 3400000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
206 | PROVISION & SUPPLY OF MURRAM 17,000 METERS CUBIC NYCG/Q097/2016-2017 | [6 empty] | BOSAMARO |  | Public Works | Public Works | TREAMOC KENYA LTD |  | 20/11/2016 | 16/12/2016 |  | 3434000 | 3434000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
207 | PROVISION & SUPPLY OF MURRAM 18,000 METERS CUBIC NYCG/Q098/2016-2017 | [6 empty] | KEMERA |  | Public Works | Public Works | SUMODAM GENERAL CONSTRUCTION |  | 20/11/2016 | 16/12/2016 |  | 3240000 | 3240000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
208 | PROVISION & SUPPLY OF MURRAM 13,500 METERS CUBIC NYCG/Q099/2016-2017 | [8 empty] | Public Works | Public Works | MASTERPIECE INVESTMENT |  | 20/11/2016 | 16/12/2016 |  | 2700000 | 2700000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
209 | PROVISION & SUPPLY OF MURRAM 11,000 METERS CUBIC NYCG/Q100/2016-2017 | [6 empty] | NYANSIONGO |  | Public Works | Public Works | GETARE GETS JOINT SUPPLIES |  | 20/11/2016 | 16/12/2016 |  | 2200000 | 2200000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
210 | HIRE OF ROAD CONSTRUCTION EQUIPMENTS | [6 empty] | COUNTY-WIDE |  | Public Works | Public Works | MINISTRY OF TRANSPORT & MECHANICAL TRANSPORT FUND |  | 13/12/2016 |  |  | 18389500 | 18389500 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
211 | HIRE OF ROAD CONSTRUCTION EQUIPMENTS | [6 empty] | COUNTY-WIDE |  | Public Works | Public Works | MINISTRY OF TRANSPORT & MECHANICAL TRANSPORT FUND |  | 19/01/2017 |  |  | 16610500 | 16610500 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
212 | HIRE OF ROAD CONSTRUCTION EQUIPMENTS | [6 empty] | COUNTY-WIDE |  | Public Works | Public Works | MINISTRY OF TRANSPORT & MECHANICAL TRANSPORT FUND |  | 2017-11-04 |  |  | 35000000 | 35000000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
213 | HIRE OF ROAD CONSTRUCTION EQUIPMENTS | [6 empty] | COUNTY-WIDE |  | Public Works | Public Works | MINISTRY OF TRANSPORT & MECHANICAL TRANSPORT FUND |  | 29/5/2017 |  |  | 22000000 | 22000000 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2016/2017
214 | KINENI BOREHOLE | [6 empty] | ESISE |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | AQUA SOFT DRILING LTD |  | 24/1/2014 | 16/5/2014 |  | 8100000 | 3200000 |  | GOK | [8 empty] | STALLED | [16 empty] | 2013/2014
215 | TENTE BOREHOLE | [6 empty] | TOWNSHIP |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | SOLAR WORLD |  | 30/1/2014 | 22/5/2014 |  | 5897904 | 5897904 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
216 | RIAGICHANA, RIAKIMAI, RIASIREMBE SPRINGS | [6 empty] | BOSAMARO |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | MARANI HOLDINGS |  | 2014-12-05 | 2014-12-07 |  | 933985.6 | 909330.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
217 | RIOTWORI SPRING | [6 empty] | NYANSIONGO |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | MARANI HOLDINGS |  | 2014-12-05 | 30/6/2014 |  | 234911.6 | 199280 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
218 | NYARONDE SPRING | [6 empty] | MEKENENE |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | KEBSAN KENYA LTD |  | 2014-12-05 | 2014-01-08 |  | 4699647.2 | 4176163.5 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
219 | MACHURIRIATI WATER SUPPLY | [6 empty] | RIGOMA |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | NORVEN INVESTMENT |  | 2014-12-05 | 15/9/2014 |  | 8854408 | 7901859.9 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
220 | KEBIRIGO WATER SUPPLY SCHEME | [6 empty] | NYAMAIYA |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | GETARE GETS |  | 2014-12-05 | 30/8/2014 |  | 6626666.1 | 6543780.7 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
221 | ESANI SPRING | [6 empty] | GESIMA |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | FIRMRISEBUIDING |  | 2014-12-05 | 15/9/2014 |  | 2045673 | 1830133.2 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
222 | MIRIRI BOREHOLE | [6 empty] | GACHUBA |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | JOSMO GENERAL |  | 2014-12-05 | 15/9/2014 |  | 6427243 | 6427243 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
223 | KEMERA WATER SPRING | [6 empty] | KEMERA |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | GEMO CONSTRUCTION LTD |  | 2014-12-05 | 30/8/2014 |  | 5462304.34 | 3660293 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
224 | ISINTA BOREHOLE | [6 empty] | ITIBO |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | TRIAL ZONE |  | 2014-12-05 | 15/9/2014 |  | 6823516 | 6645718.4 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
225 | IRINGAGRAVITY WATER SUPPLY | [6 empty] | MANGA |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | INOMAJ BUILDING |  | 2014-12-05 | 15/9/2014 |  | 7200497 | 6673525.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
226 | GACHUBARIGOMA LINES | [6 empty] | GACHUBA |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | ELIMAX ENTERPRISES |  | 2014-12-05 | 2014-12-07 |  | 7299420 | 6053000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
227 | RIAKIMANGA&AMAKARA SPRINGS | [6 empty] | NYANSIONGO |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | DENAMO GENEARL |  | 2014-12-05 | 2014-01-10 |  | 6956322 | 6464225.4 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
228 | NYAGWACHA SPRING WATER SUPPLY | [6 empty] | NYAMAIYA |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | MWAMOGUSII CONTRACTORS |  | 2014-12-05 | 15/9/2014 |  | 8753405.2 | 8629326.3 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
229 | KIANUNGU BOREHOLE WATER SUPPLY | [6 empty] | BOSAMARO |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | SAUMO ENTERPRISES |  | 2014-12-05 | 15/9/2014 |  | 6571350 | 6571135 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
230 | RIAMORURI WATER SUPPLY | [8 empty] | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | LINTOS AUTO |  | 2014-12-05 | 15/9/2014 |  | 7473575 | 7473575 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
231 | MANGA GIRLS WATER SUPPLY | [6 empty] | ESISE |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | NGISA CONSTRUCTION |  | 2014-12-05 | 2014-01-10 |  | 9310794 | 9065181.7 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
232 | EKERENYO SPRING | [6 empty] | EKERENYO |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | JEFF GEN. CONTRACTORS |  | 2014-12-05 | 15/9/2014 |  | 8987953 | 8856869.15 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
233 | GATUTA-NYAKOME SPRING | [6 empty] | MANGA |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | SPILLWAY KENYA LTD |  | 2014-12-05 | 30/8/2014 |  | 1690706 | 1690706 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
234 | RIARIECHI, RIASURE, RIOMENDA, OGANGO SPRINGS | [6 empty] | MANGA |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | ALDAN INTERNATIONAL |  | 2014-12-05 | 30/6/2014 |  | 5590530 | 5443215.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
235 | NYAMBUNWA , RIATANDI, RIOMARE WATER SUPPLY | [6 empty] | RIGOMA-GACHUBA |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | SANMIC GENERAL |  | 2014-12-05 | 30/6/2014 |  | 1180527 | 1009934.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
236 | KORONYA,NYABIGENA,MAGWAGWA, RIAKERANDI | [6 empty] | MAGWAGWA |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | REAMIC INVESTMENT |  | 2014-12-05 | 30/8/2014 |  | 5527461 | 5417893.85 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
237 | BOGWENDO BOREHOLE | [6 empty] | MAGOMBO |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | SOLAR WORLD E. A LTD |  | 2014-02-06 | 22/09/2014 |  | 7049190 | 7049190 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
238 | MATUNWA BOREHOLE | [6 empty] | ITIBO |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | BON BOREHOLE DRILLERS |  | 2014-02-06 | 22/09/2014 |  | 7135260 | 7003260 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
239 | MARINDI BOREHOLE | [6 empty] | BOGICHORA |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | BASIL DRILLING LTD |  | 30/12/2014 | 21/04/2015 |  | 7055460 | 6960500 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
240 | NYANGENA BOREHOLE | [6 empty] | BOSAMARO |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | WATER RESOURCE CO. |  | 30/12/2014 | 21/04/2015 |  | 7623522 | 7432932 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
241 | NYANGWARE BOREHOLE | [6 empty] | KIABONYORU |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | WATER RESOURCE CO. |  | 30/12/2014 | 21/04/2015 |  | 7552842 | 7535012 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
242 | OKANO BOREHOLE | [6 empty] | BOKEIRA |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | WATER RESOURCE CO. |  | 30/12/2014 | 21/04/2015 |  | 7559682 | 7536500 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
243 | OMOKIRONDO BOREHOLE | [6 empty] | ITIBO |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | SOLAR WORLD E. A LTD |  | 30/12/2014 | 21/04/2015 |  | 7745160 | 4334920 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
244 | EXTENSION OF WATER PIPELINE & STORAGE FACILITY AT KEBABE SECONDARY SCHOOL | [8 empty] | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | HYMOFIX INVESTMENTS |  | 30/3/2015 | 2015-12-05 |  | 1527900 | 1527900 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
245 | INTALLATION OF RAIN WATER HARVESTING FACILITY AT RIOMEGO SEC. SCH | [8 empty] | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | RIMOX LOGISTICS |  | 30/3/2015 | 27/4/2015 |  | 552720 | 552720 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
246 | COMPLETION OF KINENI BOREHOLE DRILLING CGN/T009/2014-2015 | [6 empty] | ESISE |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | SOLAR WORLD E.A LTD |  | 30/7/2015 | 2015-03-09 |  | 4475280 | 4475280 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
247 | SUPPLY AND INSTALLATION WATER PUMPS | [6 empty] | VARIOUS |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | DAVIS & SHIRTTLIFF |  | 22/5/2015 | 26/6/2015 |  | 5186209 | 4586553.1 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
248 | POWER CONNECTION FOR VARIOUS PROJECTS | [6 empty] | VARIOUS |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | nb |  |  |  |  | 2961470 | 2961470 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
249 | KIBWOGE POLYTECHNIC | [6 empty] | KEMERA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | GESURE BUILDING CONTRACTORS |  | 2014-05-06 | 2014-05-09 |  | 2251432.4 | 2251432.4 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
250 | MATONGO POLYTECHNIC | [6 empty] | MAGWAGWA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | BESTIN CONSTRUCTION LTD |  | 2014-12-06 | 15/9/2014 |  | 2366286.09 | 2366286.09 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
251 | MISAMBI POLYTECHNIC | [6 empty] | MAGWAGWA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | ABAMONS CONSTRUCTION LTD |  | 2014-12-06 | 15/09/2014 |  | 2410750.3 | 2410750.3 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
252 | KEGWANDA POLYTECHNIC | [6 empty] | RIGOMA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | GESISI ENTERPRISE |  | 2014-12-06 | 15/09/2014 |  | 2402844.9 | 2402844.9 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
253 | KENYERERE POLYTECHNIC | [6 empty] | MAGOMBO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | SHABEL CONTRACTORS |  | 2014-05-06 | 2014-05-09 |  | 2224659.6 | 2050659.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
254 | RITONGO POLYTECHNIC | [6 empty] | GESIMA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | ASSET CARE LTD |  | 2014-12-06 | 15/09/2014 |  | 2378551 | 356782.65 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
255 | BITICHA POLYTECHNIC | [6 empty] | RIGOMA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | FOBABUIDING& CIVIL ENGINEERING |  | 2014-12-06 | 15/09/2014 |  | 2347236.8 | 835815 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
256 | GESIMA POLYTECHNIC | [6 empty] | GESIMA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | MERIX AUTO CO. LTD |  | 2014-12-06 | 15/09/2014 |  | 2350053 | 1801120.6 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
257 | ST. STEPHEN EKERUBO POLYTECHNIC | [6 empty] | ITIBO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | SANYA KENYA LTD |  | 2014-12-06 | 15/09/2014 |  | 2188250.4 | 2188250.4 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
258 | ST. ELIZABETH EMBARO POLYTECHNIC | [6 empty] | RIGOMA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | STEM INVESTMENT |  | 2014-12-06 | 15/09/2014 |  | 2296481 | 2296481 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
259 | SAIGANGIYA POLYTECHNIC | [6 empty] | NYANSIONGO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | INOMAJI BUILDING |  | 2014-12-06 | 15/09/2014 |  | 2260538 | 2260538 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
260 | MONGORI POLYTECHNIC | [6 empty] | MEKENENE |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | GETARE GETS |  | 2014-12-06 | 15/09/2014 |  | 2343520.2 | 2343520.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
261 | ST. PETERS GETENI POLYTECHNIC | [6 empty] | RIGOMA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | SNAVES CIVIL ENG. |  | 2014-12-06 | 15/09/2014 |  | 2253659.6 | 2001774.3 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
262 | RITIBO POLYTECHNIC | [6 empty] | GESIMA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | DAMAROSE PRINTERS |  | 2014-12-06 | 15/09/2014 |  | 2238057.6 | 2238057.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
263 | NYAIRANG’A POLYTECHNIC | [6 empty] | EKERENYO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | INTERSTATE CO. LTD |  | 2014-12-06 | 15/09/2014 |  | 2227577.5 | 2226585.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
264 | NYAIKURO POLYTECHNIC | [6 empty] | MANGA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | FLOLIZZ CONTRACTORS LTD |  | 2014-05-06 | 5/9/014 |  | 2340578.4 | 2085491.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
265 | KIIOGOTWA POLYTECHNIC | [6 empty] | MANGA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | HARMONNET INVESTMENT CO. LTD |  | 2014-05-06 | 2014-05-09 |  | 2382519.6 | 1971849.1 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
266 | GESIGORO POLYTECHNIC | [6 empty] | BOKEIRA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | MOSBOKO CIVIL ENG. |  | 2014-12-06 | 15/09/2014 |  | 2224659 | 1801152.3 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
267 | BIGEGE POLYTECHNIC | [6 empty] | BOSAMARO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | DATABEL INTERNATIONAL |  | 2014-04-06 | 2014-04-09 |  | 2220599.6 | 1722592 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
268 | NASARI POLYTECHNIC | [6 empty] | ITIBO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | JOM GEN. CONTRACTORS |  | 2014-10-06 | 2014-10-09 |  | 2245597.6 | 1596450 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
269 | MORAKO II POLYTECHNIC | [6 empty] | MANGA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | LEVOS GEN. CONSTRUCTION LTD |  | 2014-05-06 | 2014-05-09 |  | 2,378, 551 | 1254274.94 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
270 | MONG’ONI POLYTECHNIC | [6 empty] | RIGOMA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | OMNYAKOMU ENGINEERING |  | 2014-12-06 | 15/09/2014 |  | 2227240.6 | 2006840.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
271 | MARIBA YOUTH POLYTECHNIC | [6 empty] | BOSAMARO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | TABSHA SUPPLIES & GEN CONTRACTORS |  | 2014-04-06 | 2014-04-09 |  | 2500994.8 | 2427926.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
272 | KIENDEGE YOUTH POLYTECHNIC | [6 empty] | GACHUBA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | BONYAMO CONSTRUCTION |  | 2014-05-06 | 2014-05-09 |  | 2473201.2 | 1736777.5 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
273 | BOBEMBE YOUTH POLYTECHNIC | [6 empty] | BOGICHORA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | NAKTONGO CONTRACTORS LTD |  | 2014-04-06 | 2014-04-09 |  | 2550271.6 | 2550271.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
274 | ST. ANDREWS KEREMA POLYTECHNIC | [6 empty] | KIABONYORU |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | PARKENG AGENCIES |  | 2015-11-03 | 2015-11-06 |  | 2565363.2 | 2565363.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
275 | KIBAARA PRIMARY ECD CLASSROOM | [6 empty] | BOMWAGAMO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | HENCHEN SERVICES LTD |  | 2014-12-06 | 15/09/2014 |  | 2714299.08 | 1501932.33 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
276 | MANGA DEB PRIMARY ECD CLASSROOM | [6 empty] | ESISE |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | ABAMONS CONST. LTD |  | 2014-12-06 | 15/09/2014 |  | 2812848.04 | 2812848.04 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
277 | MAKAIRO DEB PRIMARY ECD CLASSROOM | [6 empty] | BOGICHORA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | HONET CO. LTD |  | 2014-04-06 | 2014-04-09 |  | 2853981 | 2853981 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
278 | NYAKONGO PRIMARY ECD CLASSROOM | [6 empty] | MANGA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | GESUREBUIDING |  | 2014-05-06 | 2014-06-09 |  | 2735998.04 | 2735998.04 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
279 | KENYERERE ECD CLASSROOM | [6 empty] | MAGWAGWA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | JOAMA GEN. ENT LTD |  | 2014-09-09 | 2014-10-12 |  | 2751096.6 | 2751096.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
280 | NYANCHONORIA ECD CLASSROOM | [6 empty] | RIGOMA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | STARMACENT. LTD |  | 2014-12-06 | 2014-04-09 |  | 2978516 | 2978516 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
281 | GEKENDO DOK ECD CLASSROOM | [6 empty] | EKERENYO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | JOAH GEN. CONTRACTORS |  | 2014-12-06 | 15/09/2014 |  | 2714229.08 | 1044655.4 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
282 | NYAGACHO PRIMARY ECD CLASSROOM | [6 empty] | MEKENENE |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | BLUE HOUSE GEN. |  | 2014-12-06 | 15/09/2014 |  | 2823445.8 | 2664805.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
283 | GESORE PRIMARY ECD CLASSROOM | [6 empty] | TOWNSHIP |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | MASOOD CIVIL ENG. CO LTD |  | 22/2/2016 | 31/5/2016 |  | 2729130 | 1105886 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
284 | IBARA DOK PRIMARY ECD CLASSROOM | [6 empty] | KIABONYORU |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | GETARE GETS JOINT LTD |  | 2014-08-06 | 2014-04-09 |  | 2854394.9 | 2854394.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
285 | NYAKEORE PRIMARY ECD CLASSROOM | [6 empty] | BONYAMATUTA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | INTERSTATE CO. LTD |  | 2014-04-06 | 2014-04-09 |  | 2729017 | 2729017 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
286 | NYAUTUTU PRIMARY ECD CLASSROOM | [6 empty] | BOKEIRA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | STEM INVESTMENT LTD |  | 2014-12-06 | 15/09/2014 |  | 2853981 | 995860 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
287 | NYAMBOGO PRIMARY ECD CLASSROOM | [6 empty] | MAGOMBO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | ZABELA GENERAL LTD |  | 2014-05-06 | 2014-05-09 |  | 2853981 | 2853981 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
288 | MOTOMBEBA PRIMARY ECD CLASSROOM | [6 empty] | KEMERA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | MOSBOKO CIVIL ENG. LTD |  | 2014-05-06 | 2014-05-09 |  | 2747823 | 1709660.41 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
289 | GETAARI PRIMARY ECD CLASSROOM | [6 empty] | NYAMAIYA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | STRATEGY ENGINEERING |  | 2014-04-06 | 2014-04-09 |  | 2788413.88 | 2352972.42 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
290 | NYARONGE PRIMARY ECD CLASSROOM | [6 empty] | GESIMA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | KADESH CONSTRUCTION LTD |  |  |  |  | 2845288 | 2102723.76 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
291 | RIBAITA PRIMARY ECD CLASSROOM | [6 empty] | ESISE |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | JACERA CONSTRUCTION |  | 23/04/2015 | 27/7/2015 |  | 3037547 | 1119537.17 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
292 | NYAMAURO PRIMARY ECD CLASSROM | [6 empty] | ITIBO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | SACHEM E. A LTD |  | 2015-08-04 | 2015-09-07 |  | 2616013.44 | 2500013.44 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
293 | KUJA PRIMARY ECD CLASSROOM | [6 empty] | GACHUBA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | MONRIDGE CONSTRUCTION |  | 2015-06-04 | 27/07/2015 |  | 3075310.8 | 2980307.32 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
294 | NYACHURURU PRIMARY ECD | [6 empty] | BOSAMARO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | ZAMORI GEN. CONSTRUCTION |  | 15/4/2015 | 15/8/2015 |  | 3292694.8 | 2550926.22 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2013/2014
295 | INSTALLATION OF INTERNET (WIFI) | [6 empty] | VARIOUS |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | TELKOM KENYA |  | 20/5/2015 | 29/6/2015 |  | 2642905.64 | 2642905.64 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
296 | CONST. OF ECDE CENTRE AT NYANKONO PRI SCH. NYCG/Q168/2015-2016. | [6 empty] | MEKENENE |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Spearways Investment Ltd |  | 29/6/2016 | 18/01/2017 |  | 3563125.6 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
297 | CONST. OF ECDE CENTRE AT RIABAGAKA PRI SCH. NYCG/Q170/2015-2016 | [6 empty] | GACHUBA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Arcad Limited |  | 29/6/2016 | 18/01/2017 |  | 3944870 | 3950000 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
298 | CONST. OF ECDE CENTRE AT RIAKWORO PRI SCH. NYCG/Q171/2015-2016 | [6 empty] | GESIMA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Fikor Enterprises Company Ltd |  | 29/6/2016 | 18/01/2017 |  | 3919257 | 3594805.2 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
299 | CONST. OF ECDE CENTRE AT BITICHA PRI SCH.NYCG/Q173/2015-2016 | [6 empty] | RIGOMA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Besma Investments Limited |  | 29/6/2016 | 18/01/2017 |  | 3562792.4 | 3319742 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
300 | CONST. OF ECDE CENTRE AT EGETONTO PRI. SCH. NYCG/Q174/2015-2016 | [6 empty] | BOKEIRA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Canon Enterprises Ltd |  | 29/6/2016 | 18/01/2017 |  | 3914385.2 | 3914385 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
301 | CONST. OF ECDE CENTRE AT RIAGECHURE PRI. SCH. NYCG/Q175/2015-2016 | [6 empty] | MAGOMBO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Zabela General Limited |  | 29/6/2016 | 18/01/2017 |  | 3559953 | 3559953 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
302 | CONST. OF ECDE CENTRE AT NYAKENYOMISIA PRI. SCH. NYCG/Q176/2015-2016 | [6 empty] | MAGWAGWA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | SANYA K. LTD |  | 29/6/2016 | 18/01/2017 |  | 3511714.4 | 3242130.4 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
303 | CONST. OF ECDE CENTRE AT KEGINGA D.E.B PRI. SCH. NYCG/Q177/2015-2016 | [6 empty] | NYANSIONGO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Denamo General Suppliers Ltd |  | 29/6/2016 | 18/01/2017 |  | 3738622 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
304 | CONST. OF ECDE CENTRE AT RIANYAKANG’I PRI. SCH. NYCG/Q178/2015-2016 | [6 empty] | KIABONYORU |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Pegnya Construction Co. Ltd |  | 29/6/2016 | 18/01/2017 |  | 3701130.08 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
305 | CONST. OF ECDE CENTRE AT ITIBO PRI. SCH. NYCG/Q179/2015-2016 | [6 empty] | BOMWAGAMO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Jokenya East Africa Ltd |  | 29/6/2016 | 18/01/2017 |  | 3684571.8 | 3390420.45 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
306 | CONST. OF ECDE CENTRE AT NYAINOGWA PRI. SCH. NYCG/Q181/2015-2016 | [6 empty] | BONYAMATUTA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Sanromano Construction Co. Ltd |  | 29/6/2016 | 18/01/2017 |  | 3560538 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
307 | CONST. OF ECDE CENTRE AT GESENENO PRI. SCH. NYCG/Q182/2015-2016 | [6 empty] | TOWNSHIP |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Inonaji Building Contractors Limited |  | 29/6/2016 | 18/01/2017 |  | 3559953 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
308 | CONST. OF ECDE CENTRE AT EKERUBO GIETAI PRI. SCH. NYCG/Q183/2015-2016 | [6 empty] | ITIBO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Mocam Road Works Ltd |  | 29/6/2016 | 18/01/2017 |  | 3887491.8 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
309 | CONST. OF ECDE CENTRE AT KIAMOGAKI PRI. SCH. NYCG/Q184/2015-2016. | [6 empty] | EKERENYO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Ikobex Company Ltd |  | 29/6/2016 | 18/01/2017 |  | 3799371.2 | 3356674.6 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
310 | CONST. OF ECDE CENTRE AT MECHEO PRI. SCH. NYCG/Q185/2015-2016 | [6 empty] | ESISE |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Samco Limited |  | 29/6/2016 | 18/01/2017 |  | 3921160.7 | 1184069.68 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
311 | CONSTRUCTION OF A WORKSHOP AT MOBAMBA PRI. SCH. NYCG/Q196/2015-2016 | [6 empty] | BONYAMATUTA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Alexander James Africa Limited |  | 29/6/2016 | 18/01/2017 |  | 3800127.08 | 916179.52 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
312 | CONST. OF A WORKSHOP AT RIAMANOTI PRIM NYCG/Q198/2015-2016 | [6 empty] | NYANSIONGO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Wilstire Holdings Co. Ltd |  | 29/6/2016 | 18/01/2017 |  | . 2,630,068 | 1269936.22 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
313 | CONST. OF A WORKSHOP AT BOMONDO PRI. SCH. NYCG/Q200/2015-2016 | [6 empty] | TOWNSHIP |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Sonje Investments |  | 29/6/2016 | 18/01/2017 |  | 2714608.8 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
314 | CONST. ECDE CENTRE AT NYABWERI PRI. SCH. NYCG/Q230/2015-2016 | [6 empty] | BOMWAGAMO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Jagera Construction Co. Ltd |  | 29/6/2016 | 18/01/2017 |  | 3638792.4 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
315 | CONST. ECDE CENTRE AT RIANG’OMBE PRI. SCH. NYCG/Q231/2015-2016 | [6 empty] | ITIBO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Hydrobuild Construction Co. Ltd |  | 29/6/2016 | 18/01/2017 |  | 3947097 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
316 | CONST. ECDE CENTRE AT KEREMA PRI. SCH. NYCG/Q232/2015-2016 | [6 empty] | KIABONYORU |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Ecocare Holdings Limited |  | 29/6/2016 | 18/01/2017 |  | 3915786.48 | 3355468.03 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
317 | CONST. ECDE CENTRE AT NYATIENO PRI. SCH. NYCG/Q233/2015-2016 | [6 empty] | GESIMA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Sostoch Contractors |  | 29/6/2016 | 18/01/2017 |  | 3588808 | 1865361.2 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
318 | CONST. OF ECDE CENTRE AT NYAMOTENTEMI PRI. SCH. NYCG/Q256/2015-2016 | [6 empty] | BOGICHORA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Jarko Construction Co.Limited |  | 29/6/2016 | 18/01/2017 |  | 3555313 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
319 | CONST. OF ECDE CENTRE AT EKORO PRI. SCH. NYCG/Q258/2015-2016 | [6 empty] | BOSAMARO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Tekema Enterprises Limited |  | 29/6/2016 | 18/01/2017 |  | 3810727.6 | 3810527.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
320 | CONST. OF ECDE CENTRE AT NYAISA PRI. SCH. NYCG/Q259/2015-2016 | [6 empty] | MANGA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Studio Pixel Limited |  | 29/6/2016 | 18/01/2017 |  | 3925938.8 | 3207311.26 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
321 | CONST. OF ECDE CENTRE AT KERORA PRI. SCH. NYCG/Q260/2015-2016 | [6 empty] | KEMERA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Mashable Limited |  | 29/6/2016 | 18/01/2017 |  | 3915786.48 | 3697064.83 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
322 | CONST. OF ECDE CENTRE AT KEBUSE PRI. SCH. NYCG/Q263/2015-2016 | [6 empty] | ESISE |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Melbourne Engineering Works Ltd |  | 29/6/2016 | 18/01/2017 |  | 3907286 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
323 | CONST. OF A WORKSHOP AT RAITIGO YOUTH POLYTECHNICNYCG/Q265/2015-2016 | [6 empty] | ESISE |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Gesis Enterprises & Gen. Supplie Ltd |  | 29/6/2016 | 18/01/2017 |  | 2702220 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
324 | SUPPLY AND DELIVERY OF WORKSHOP TOOLS & EQUIPMENTS FOR POLYTECHNICS NYCG/Q267/2015-2016 | [8 empty] | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Boflos Enterprises Ltd |  |  |  |  | 6162600 | NIL |  | GOK | [25 empty] | 2015/2016
325 | LOCAL AREA NETWORK CONNECTION NYCG/Q271/2015-2016 | [6 empty] | TOWNSHIP |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Fikor Enterprises Ltd |  |  |  |  | 2940310 | 2940310 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
326 | PROVISION OF BULK SMS OVER INTERNET PROTOCOL NYCG/Q271.A/2015-2016 | [6 empty] | TOWNSHIP |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Airtel Kenya Ltd |  |  |  |  | 1999840 | 1999840 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
327 | CONST. OF A WORKSHOP AT MANG’ONG’O YOUTH POLYTECHNIC NYCG/Q261/2015-2016 | [6 empty] | NYAMAIYA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Matrics Management Consultants Ltd |  | 29/6/2016 | 18/01/2017 |  | 2708164 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
328 | CONST. OF ECDE CENTRE AT RANGENYO PRI SCH. NYCG/Q304/2015-2016 | [6 empty] | NYAMAIYA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Solar World E. A. Ltd |  | 29/6/2016 | 18/01/2017 |  | 3950000 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
329 | CONST. OF ECDE CENTRE AT MATERIO PRI SCH. NYCG/Q287/2015-2016 | [6 empty] | NYAMAIYA |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | Roystar (K) Ltd |  | 29/6/2016 | 18/01/2017 |  | 3600000.8 | NIL |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
330 | CONST. OF ETONO YOUTH POLYTECHNIC NYCG/Q264/2015-2016 | [6 empty] | BOMWAGAMO |  | Education, ICT and Vocational Training | Education, ICT and Vocational Training | JANCOM KENYA Ltd |  | 29/6/2016 | 18/01/2017 |  | 2706164 | 1768373.6 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
331 | PROPOSED COSTRUCTION AND COMPLETION OF HOME CRAFT CENTRE CGN/T083/2015-2016 | [8 empty] | Education, ICT and Vocational Training | Education, ICT and Vocational Training | GIANCE INVESTMENT LTD |  | 29/6/2016 | 18/01/2017 |  | 5019130 | 1344183.2 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2015/2016
332 | INSTALLATION OF HEALTH MANAGEMENT INFORMATION SYSTEM {HMIS} | [6 empty] | TOWNSHIP |  | Health Services | Health Services | AFRIDIGITEL |  | 2014-05-05 | 16/6/2015 |  | 5449500 | 5449500 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
333 | REHABILITATION OF LEVEL 4 HOSPITAL KITCHEN | [6 empty] | TOWNSHIP |  | Health Services | Health Services | MASTERPIECE INVESTMENT LTD |  | 2014-05-05 | 2014-04-11 |  | 26393010.2 | 13827136.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
334 | REHABILITATION OF LEVEL 4 HOSPITAL PLUMBING | [6 empty] | TOWNSHIP |  | Health Services | Health Services | FIRMRISE BUILDING CONTRACTORS |  | 2014-05-05 | 2014-05-09 |  | 14634490.4 | 14406712.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
335 | ESIENYI H/C | [6 empty] | BOKEIRA |  | Health Services | Health Services | JOM GENERAL |  | 30/05/2014 | 2014-04-09 |  | 3343967 | 3343967 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
336 | KAMBINI H/C | [6 empty] | GESIMA |  | Health Services | Health Services | GESISI ENTERPRISE |  | 29/05/2014 | 2014-04-09 |  | 2770520.02 | 2104690.1 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
337 | KENYORO H/C | [6 empty] | ITIBO |  | Health Services | Health Services | TRIAZONE |  | 30/05/2014 | 2014-04-09 |  | 3637582 | 1601149 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
338 | MOTAGARA H/C | [6 empty] | BOSAMARO |  | Health Services | Health Services | CLEOMARK EXCUVATORS |  | 2014-12-05 | 2014-12-09 |  | 3263207 | 3263207 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
339 | NYAGACHO H/C | [6 empty] | MEKENENE |  | Health Services | Health Services | KAZI MOTO |  | 2014-12-06 | 2014-12-09 |  | 2576058.4 | 1501208.72 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
340 | NYAIGUTA H/C | [6 empty] | GESIMA |  | Health Services | Health Services | STYPHILES |  | 29/05/2014 | 31/07/2014 |  | 2232500 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
341 | NYANCHONORIA H/C | [6 empty] | RIGOMA |  | Health Services | Health Services | STEM INVESTMENT |  | 29/05/2014 | 2014-04-09 |  | 1780136 | 711080 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
342 | NYANDOCHE IBERE H/C | [6 empty] | NYANSIONGO |  | Health Services | Health Services | JOME ENTERPRISE |  | 29/05/2014 | 2014-12-07 |  | 2797340 | 2797340 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
343 | NYANSABAKWA H/C | [6 empty] | NYAMAIYA |  | Health Services | Health Services | ASSOCIATED FIRM AGRO LTD |  | 2014-12-06 | 2014-12-09 |  | 2347352.8 | 2347352.34 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
344 | NYARONDE H/C | [6 empty] | NYANSIONGO |  | Health Services | Health Services | NYANTURAGO CONSTRUCTION |  | 2014-12-06 | 2014-12-09 |  | 2010744 | 1819146.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
345 | NYANSAGIO H/C | [6 empty] | NYAMAIYA |  | Health Services | Health Services | SACHEM CONSTRUCTION |  | 2014-12-06 | 2014-12-09 |  | 1820504 | 1140581.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
346 | ORWAKI H/C | [6 empty] | BOKEIRA |  | Health Services | Health Services | MACHINE ZONE LTD |  | 30/05/2014 | 2014-04-09 |  | 3304120 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
347 | RIGOMA H/C | [6 empty] | RIGOMA |  | Health Services | Health Services | BENTEL ENTERPRISES |  | 29/05/2014 | 2014-04-09 |  | 2412019.25 | 2050224.81 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
348 | RIKENYE H/C | [6 empty] | RIGOMA |  | Health Services | Health Services | BEN PHILIPS |  | 29/05/2014 | 31/07/2014 |  | 1995000 | 962220.58 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
349 | SERE H/C | [6 empty] | EKERENYO |  | Health Services | Health Services | HEARP |  | 30/05/2014 | 2014-04-09 |  | 3408056.8 | 1704028.4 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
350 | GIANCHORE H/C | [6 empty] | BOGICHORA |  | Health Services | Health Services | HONET LTD |  | 2014-12-06 | 2014-12-09 |  | 2411251.2 | 2411251.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
351 | RIANYAMBWEKE H/C | [6 empty] | BOMWAGAMO |  | Health Services | Health Services | GESURE BUILDERS |  | 30/05/2014 | 2014-04-09 |  | 3214870.4 | 3214870.4 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
352 | IKOBE H/C | [6 empty] | MANGA |  | Health Services | Health Services | NYAMIRA EXPRESS |  | 2015-08-04 | 2015-08-07 |  | 3587636.4 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
353 | KEGINGA DISP | [6 empty] | MEKENENE |  | Health Services | Health Services | FACELIFT ENTERPRISES |  | 2015-07-04 | 2015-07-07 |  | 3407088.2 | 3407088.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
354 | ENSOKO DISP | [6 empty] | ESISE |  | Health Services | Health Services | SACCI ENG LTD |  | 2015-07-04 | 2015-08-07 |  | 3777632.8 | 1305731.38 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
355 | COMPLETION OF STAFF HOUSE AT NYAKONGO DISP | [6 empty] | KIABONYORU |  | Health Services | Health Services | ROCKVIEW CONSTR |  | 2015-08-04 | 2015-08-07 |  | 3777632.8 | 3598795.42 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
356 | MOKOMONONI H/C | [6 empty] | KIABONYORU |  | Health Services | Health Services | INNOMAJ CONSTR |  |  |  |  | 3926368 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
357 | MOCHENWA H/C | [6 empty] | GESIMA |  | Health Services | Health Services | SAFAMO GENERAL |  | 2015-06-04 | 27/07/2015 |  | 3404031.6 | 3404580.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
358 | EMENYENCHE H/C | [6 empty] | GESIMA |  | Health Services | Health Services | GWAT INTERNATIONAL |  | 30/03/2015 | 22/6/2015 |  | 3742560 | 2535067.48 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
359 | RIGOKO DISP | [6 empty] | NYANSIONGO |  | Health Services | Health Services | MANMICH |  | 2015-07-04 | 2015-07-07 |  | 3864255 | 1170196.4 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
360 | MONGORISI DISP | [6 empty] | BOGICHORA |  | Health Services | Health Services | BLUE HOUSE GENERAL |  | 15/4/2015 | 15/08/2015 |  | 3709987.4 | 3709987.4 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
361 | GIRANGO DISP | [6 empty] | GACHUBA |  | Health Services | Health Services | BENKER HOLDINGS |  | 2015-06-04 | 27/07/2015 |  | 4118600 | 4118600 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
362 | TINDERETI DISP | [6 empty] | NYANSIONGO |  | Health Services | Health Services | TECHPAC BUSINESS TECHNOLOGY |  | 2015-07-04 | 2015-07-07 |  | 2276000 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
363 | RAITIGO DISP | [6 empty] | ESISE |  | Health Services | Health Services | KIGUNYA ENGINEERING |  | 2015-07-04 | 2015-07-07 |  | 1997800 | 1496091.44 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
364 | KIENDEGE DISP | [6 empty] | KEMERA |  | Health Services | Health Services | MAGNIFICA CONTRACTORS |  | 2015-08-04 | 2015-08-07 |  | 3892612 | 3697981.4 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
365 | ISOGE DISP | [6 empty] | ESISE |  | Health Services | Health Services | STROIKA |  | 2015-08-04 | 2015-08-07 |  | 3838242.8 | 3838242.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
366 | NYABWERI | [6 empty] | BOMWAGAMO |  | Health Services | Health Services | TRANSAPLA LTD |  | 29/05/2014 | 2014-03-09 |  | 2306149.6 | 2306149.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
367 | BOSIANGO | [6 empty] | BOSAMARO |  | Health Services | Health Services | ARAKO CONSTRUCTION |  | 2014-12-06 | 2014-12-09 |  | 2571372 | 1657060 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
368 | KIAMANYOMBA | [6 empty] | MAGWAGWA |  | Health Services | Health Services | BONYAMO CONSTR |  | 29/05/2014 | 2014-03-09 |  | 2186391.2 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
369 | MOSOBETI | [6 empty] | GESIMA |  | Health Services | Health Services | DAMAROSE PRINTERS |  | 29/05/2014 | 31/07/2014 |  | 2484946 | 2484946 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
370 | MOTONTERA | [6 empty] | NYAMAIYA |  | Health Services | Health Services | STRATEGY ENG |  | 2014-12-06 | 2014-12-09 |  | 2512560 | 1409724.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
371 | ENDIBA | [6 empty] | KIABONYORU |  | Health Services | Health Services | RIANYAKANGI |  | 29/05/2014 | 2014-12-08 |  | 2783014 | 2783014 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
372 | NYAKEGOGI | [6 empty] | KEMERA |  | Health Services | Health Services | NYAMERU ELECTRICAL |  | 2014-05-06 | 2014-05-09 |  | 2036414.8 | 2036414.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
373 | KERUMBE | [6 empty] | MEKENENE |  | Health Services | Health Services | MOSBOKO CIVIL ENG. |  | 2014-08-06 | 2014-12-09 |  | 3116324 | 2529059 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
374 | NYANKONO | [6 empty] | MEKENENE |  | Health Services | Health Services | JERAN GENERAL |  | 29/06/2014 | 2014-12-10 |  | 1562025 | 1562025 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
375 | RIAKINARO | [6 empty] | BONYAMATUTA |  | Health Services | Health Services | INOMAJ CONSTRUCTION |  | 2014-12-06 | 2014-12-09 |  | 2674542 | 1846781.48 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
376 | KENYENYA | [6 empty] | BONYAMATUTA |  | Health Services | Health Services | CMOS |  | 2014-12-06 | 2014-12-09 |  | 2519230 | 1536306.32 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
377 | NYAGANCHA | [6 empty] | GACHUBA |  | Health Services | Health Services | TOSACO HOLDINGS |  | 29/05/2014 | 31/07/2014 |  | 1627944 | 1248165.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
378 | MAGWAGWA | [6 empty] | MAGWAGWA |  | Health Services | Health Services | FOBA BUILDING |  | 29/05/2014 | 2014-03-09 |  | 2312518 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
379 | NYANGWETA | [6 empty] | BOSAMARO |  | Health Services | Health Services | ROYSTAR LTD |  | 2014-12-06 | 2014-12-09 |  | 2523660 | 2523660 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
380 | KEMUNCHUGU | [6 empty] | BOKEIRA |  | Health Services | Health Services | RIMOX LOGISTICS |  | 30/05/2014 | 2014-05-09 |  | 2602866.2 | 2576857.35 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
381 | KENYERERE | [6 empty] | BONYAMATUTA |  | Health Services | Health Services | OGEA CONSTRUCTION |  | 30/3/2015 | 22/6/2015 |  | 2228226 | 2228226 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
382 | ETURUNGI | [6 empty] | KIABONYORU |  | Health Services | Health Services | EXOTICA |  | 29/05/2014 | 2014-12-07 |  | 3417719 | 1741538.74 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
383 | IKONGE | [6 empty] | ITIBO |  | Health Services | Health Services | INTERSTATE LTD |  | 29/05/2014 | 2014-03-09 |  | 1414620 | 1354010 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
384 | MIRIRI | [6 empty] | GACHUBA |  | Health Services | Health Services | GESISI ENTERPRIS |  | 29/05/2014 | 2014-03-09 |  | 2233125.3 | 1775887.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
385 | MANGA SUB COUNTY | [6 empty] | MANGA |  | Health Services | Health Services | MBOGO TRANSPORTERS |  | 2014-05-06 | 2014-05-09 |  | 1946426 | 1946426 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
386 | MECHEO | [6 empty] | KIABONYORU |  | Health Services | Health Services | ASSET CARE LTD |  | 29/05/2014 | 12/7 2014 |  | 1267196 | 437436 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
387 | TING’A | [6 empty] | BOSAMARO |  | Health Services | Health Services | GETARE GETS JOINTS |  | 2014-12-06 | 2014-12-09 |  | 2492943.2 | 2492943.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
388 | TOMBE | [6 empty] | MANGA |  | Health Services | Health Services | MATUTA CONSTRUCTION |  | 2014-05-06 | 2014-05-09 |  | 1745901 | 609000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
389 | MAGOMBO GUCHA | [6 empty] | GACHUBA |  | Health Services | Health Services | CANON ENTERPERPRISES |  | 29/05/2014 | 31/07/2014 |  | 2257940 | 1722837 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
390 | ETONO | [6 empty] | BOMWAGAMO |  | Health Services | Health Services | KOPEK LTD |  | 30/05/2014 | 2014-04-09 |  | 2482670 | 1685403.5 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
391 | CHINA | [6 empty] | ITIBO |  | Health Services | Health Services | JOAH GEN CONTRACTORS |  | 29/05/2014 | 2014-03-09 |  | 2228493.4 | 1413819.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
392 | SIRATE | [6 empty] | MAGOMBO |  | Health Services | Health Services | KIANGO GEN SUPP |  | 2014-05-06 | 2014-05-09 |  | 1089738 | 1067942.34 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
393 | MAGOMBO H/C | [6 empty] | MAGOMBO |  | Health Services | Health Services | LIGLAS INVESTMENT |  | 05.06.2014 | 2014-05-09 |  | 1898293 | 1154379 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
394 | EKERENYO | [6 empty] | EKERENYO |  | Health Services | Health Services | DATABEL |  | 29/05/2014 | 2014-03-09 |  | 1313265 | 764398 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
395 | KIANGOSO DISP | [6 empty] | KEMERA |  | Health Services | Health Services | NYANTURAGO CONTRACTORS |  | 10.9.2014 | 2014-03-12 |  | 3334211.2 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
396 | KIOMARA DISP | [6 empty] | BOKEIRA |  | Health Services | Health Services | NYAMIMATT |  | 2015-09-04 | 2015-10-08 |  | 2824630.16 | 1602979.18 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
397 | BOGWENDO DISP | [6 empty] | MAGOMBO |  | Health Services | Health Services | LIDOM TRADING COMPANY |  | 2014-10-06 | 2014-10-09 |  | 1498673 | 1312861 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
398 | AMATERIO DISP | [6 empty] | KIABONYORU |  | Health Services | Health Services | KEBSAN KENYA LTD |  | 27/4/2015 | 27/7/2015 |  | 3146268 | 3145628 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
399 | NYABONGE DISP | [6 empty] | ITIBO |  | Health Services | Health Services | HUSTLERS SOLUTIONS |  | 2015-07-04 | 2015-07-07 |  | 2628861.6 | 1723579.04 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
400 | REFURBISHMENT OF NYAMIRALEVEL 4 HOSPITAL MAIN GATE CGN/149/2013-14 | [6 empty] | TOWNSHIP |  | Health Services | Health Services | SONJE INVESTMENTS LTD |  | 2014-05-11 | 2015-05-03 |  | 7680831.54 | 7680831.54 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
401 | REVERSE OSMOSIS WATER TREATMENT SYSTEM | [6 empty] | TOWNSHIP |  | Health Services | Health Services |  |  | 18/12/2014 | 26/2/2015 |  | 3350000 | 3350000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
402 | INSTALLATION OF ELECTRICAL CABLING IN THE NCH CT SCAN ROOM NYCG/Q04/ 2014-2015 | [6 empty] | TOWNSHIP |  | Health Services | Health Services | ZAMOGE GENERAL CONTRACTORS |  | 2014-10-12 | 14/01/2015 |  | 3091400 | 3091400 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
403 | NYAMWETUREKO H F NYCG/Q051/2014-2015 | [8 empty] | Health Services | Health Services | DANOKEM LTD |  | 15/6/2015 | 2015-10-08 |  | 2471298.8 | 2392140.4 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
404 | MEDICAL EQUIPMENTS AND TOOLS FOR CT SCAN ROOM. (Holley Cotec) | [6 empty] | TOWNSHIP |  | Health Services | Health Services | Holley Cotec |  | 2015-12-05 | 16/6/2015 |  | 735800 | 735800 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
405 | LABORATORY EQUIPMENTS ( Science Scope Ltd) | [6 empty] | TOWNSHIP |  | Health Services | Health Services | Science Scope Ltd |  | 25/9/2015 | 26/10/2015 |  | 1110000 | 1110000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
406 | LABORATORY EQUIPMENTS (Divine Agents) | [6 empty] | TOWNSHIP |  | Health Services | Health Services | Divine Agents |  | 2015-02-11 |  |  | 1055000 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
407 | LABORATORY EQUIPMENTS ( Crown Solutions) | [6 empty] | TOWNSHIP |  | Health Services | Health Services | Crown Solutions |  | 21/9/2015 | 21/10/2015 |  | 3615000 | 3616250 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
408 | LABORATORY EQUIPMENTS (Faram E. A Ltd) | [6 empty] | TOWNSHIP |  | Health Services | Health Services | Faram E. A Ltd |  | 23/9/2015 | 23/10/2015 |  | 10245880 | 9574146.21 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
409 | LABORATORY EQUIPMENTS (Holley Cotec) | [6 empty] | TOWNSHIP |  | Health Services | Health Services | Holley Cotec |  | 25/9/2015 |  |  | 930000 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
410 | LABORATORY EQUIPMENTS (Hass Scientific) | [6 empty] | TOWNSHIP |  | Health Services | Health Services | Hass Scientific |  | 25/9/2015 |  |  | 580000 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
411 | AMBULANCE | [6 empty] | TOWNSHIP |  | Health Services | Health Services | PHARMAKEN LTD |  |  |  |  | 8300000 | 8000000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
412 | THREATRE EQUIPMENT AND SURGICAL INSTRUMENTS ( Pulse Healthcare) | [6 empty] | TOWNSHIP |  | Health Services | Health Services | Pulse Healthcare |  | 25/9/2015 |  |  | 3350000 | 3350000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
413 | THREATRE EQUIPMENT AND SURGICAL INSTRUMENTS (Holley Cotec E. A) | [6 empty] | TOWNSHIP |  | Health Services | Health Services | Holley Cotec E. A |  | 25/9/2015 |  |  | 4962000 | 4962000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
414 | THREATRE EQUIPMENT AND SURGICAL INSTRUMENTS (Nairobi Enterprise) | [6 empty] | TOWNSHIP |  | Health Services | Health Services | Nairobi Enterprise |  | 25/9/2015 |  |  | 209800 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
415 | THREATRE EQUIPMENT AND SURGICAL INSTRUMENTS (Njimia Pharmaceuticals) | [6 empty] | TOWNSHIP |  | Health Services | Health Services | Njimia Pharmaceuticals |  | 25/9/2015 |  |  | 270000 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
416 | THREATRE EQUIPMENT AND SURGICAL INSTRUMENTS (Spenomatic Kenya Ltd) | [6 empty] | TOWNSHIP |  | Health Services | Health Services | Spenomatic Kenya Ltd |  | 25/9/2015 |  |  | 8500000 | 8500000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
417 | THREATRE EQUIPMENT AND SURGICAL INSTRUMENTS (A1 Healthcare Ltd) | [6 empty] | TOWNSHIP |  | Health Services | Health Services | A1 Healthcare Ltd |  | 25/9/2015 |  |  | 2196125 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
418 | INSTALLATION OF ELECTRICITY AT IGENA ITAMBE HEALTH FACILITY | [8 empty] | Health Services | Health Services | ROYSTAR KENYA LTD |  | 25/9/2015 |  |  | 593000 | 593000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
419 | TWO NO. DIALYSIS MACHINES (Crown Health Care) NYCG/Q135/2014 -2015 | [6 empty] | TOWNSHIP |  | Health Services | Health Services | Crown Health Care |  | 23/12/2015 | 22/01/2016 |  | 3,364,00 | 3364000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
420 | 26NO. INFUSION STANDS, 68NO. BEDSIDE LOCKERS 7 10NO. THEATRE BOOTS (Holley Cotec) NYCG/Q134/2014-2015 | [8 empty] | Health Services | Health Services | Holley Cotec |  | 29/9/2015 | 2015-03-11 |  | 1260000 | 1260000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
421 | OUTPATIENT BLOCK AT NYABOGOYE HEALTH FACILITY NYCG/Q114/2014-2015 | [8 empty] | Health Services | Health Services | TAZAMA BUILDERS |  | 24/11/2015 | 20/01/2016 |  | 3985551.2 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
422 | OUTPATIENT BLOCK AT NYANGORI HEALTH FACILITY NYCG/Q115/2014-2015 | [8 empty] | Health Services | Health Services | STEM INVESTMENTS |  | 24/11/2015 | 20/01/2016 |  | 3956006 | 2904006 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
423 | MATERNITY BLOCK AT KIANGOSO HEALTH FACILITY NYCG/Q117/2014-2015 | [6 empty] | KEMERA |  | Health Services | Health Services | NYANTURAGO CONST. & GEN CONTRACTORS. |  | 2015-10-11 | 2016-05-01 |  | 3913504 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
424 | MATERNITY BLOCK AT KIANUNGU HEALTH FACILITY NYCG/Q118/2014-2015 | [6 empty] | BOSAMARO |  | Health Services | Health Services | AUTO STAR AGENCIES |  |  |  |  | 3994261.6 | 3994261.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
425 | STAFF QUARTERS AND FENCING OF OGANGO HEALTH FACILITY NYCG/Q120/2014-2015 | [6 empty] | MANGA |  | Health Services | Health Services | ISANCHA CONST. CO. LTD. |  |  |  |  | 2440918.4 | 1647414.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
426 | MATERNITY BLOCK AT AMAIGA HEALTH FACILITY NYCG/Q123/2014-2015 | [8 empty] | Health Services | Health Services | TRUEBASE MULTISERVICES |  |  |  |  | 3955878 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
427 | RENOVATION WORKS IKOBE HEALTH FACILITY NYCG/Q124/2014-2015 | [6 empty] | MANGA |  | Health Services | Health Services | LOMAN GEN SUPPLIES. |  |  |  |  | 1771830 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
428 | NYAMIRA LEVEL 5 HOSPITAL CASUALITY BLOCK NYCG/Q125/2014-2015 | [6 empty] | TOWNSHIP |  | Health Services | Health Services | FIRMRISE BUILDING & CONST. CO LTD |  | 23/12/2015 | 16/3/2016 |  | 1255763 | 1255763.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
429 | NYAMIRA LEVEL 5 HOSPITAL MATERNITY BLOCK NYCG/Q136/2014-2015 | [6 empty] | TOWNSHIP |  | Health Services | Health Services | LINTOS AUTO AGENCIES |  | 22/12/2015 | 15/03/2016 |  | 3991937 | 3384769.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
430 | NYAMIRA LEVEL 5 HOSPITAL AMENITY BLOCK NYCG/Q137/2014-2015 | [6 empty] | TOWNSHIP |  | Health Services | Health Services | NYACHIT CONST. & SUPPLIES |  | 24/03/2016 | 17/03/2016 |  | 3887392 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
431 | MATERNITY BLOCK AT NYAIGESA HEALTH FACILITY NYCG/Q140/2014-2015 | [8 empty] | Health Services | Health Services | ENSOKO CONST. |  | 24/11/2015 | 17/03/2016 |  | 3800803.8 | 871421 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
432 | MATERNITY BLOCK AT MOKOMONI HEALTH FACILITY NYCG/Q142/2014-2015 | [6 empty] | KIABONYORU |  | Health Services | Health Services | JOPEKI CONST. CO. LTD |  | 22/12/2015 | 15/03/2016 |  | 3806603.8 | 3382490 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
433 | SUPPLY AND ISTALLATION OF SIGNAGE BOARDS AND SERVICE CHARTERS (Colom Two Thousand) | [6 empty] | VARIOUS PARTS |  | Health Services | Health Services | CALMO TWO THOUSDAND |  | 20/11/2015 | 25/12/2015 |  | 3000000 | 30000000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
434 | SUPPLY AND DELIVERY OF WATER PUMP NYCG/Q104/2015-2016 | [6 empty] | TOWNSHIP |  | Health Services | Health Services | HYMOFIX INVESTMENT |  |  |  |  | 1998000 | 1998000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
435 | SUPPLY AND DELIVERY OF MEDICAL RECORDS NYCG/Q152/2014 - 2015 | [8 empty] | Health Services | Health Services | DEFLOM ENTERPRISES |  |  |  |  | 1167000 | 10676000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
436 | CONSTRUCTION OF 2.NO PIT LATRINES AT MACHURURIATI DESPENSARY NYCG/Q008/2015 - 2016 | [6 empty] | RIGOMA |  | Health Services | Health Services | TREAMAOC LTD |  |  |  |  | 1052189.6 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
437 | CONSTRUCTION OF OUT-PATIENT BLOCK AT NYAGACHO HEALTH FACILITY NYCG/Q033/2015 - 2016 | [6 empty] | MEKENENE |  | Health Services | Health Services | KAZIMOTO COST. CO. LTD |  | 21/3/2016 | 2016-05-09 |  | 2529330 | 1960930.12 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
438 | CONSTRUCTION OF TOILET BLOCK AT NYAMAIRA LEVEL 4 HOSPITAL NYCG/Q049/2015 - 2016 | [6 empty] | TOWNSHIP |  | Health Services | Health Services | JERAN GEN CONTRACTORS |  | 21/3/2016 | 2016-05-09 |  | 3950020 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
439 | COMPLETION OF LABORATORY BLOCK AT MANGA SUB-COUNTY DIST. HOSPITAL NYCG/Q050/2015 - 2016 | [6 empty] | MANGA |  | Health Services | Health Services | KIADEMA CONST. |  | 21/3/2016 | 2016-05-09 |  | 2305627 | 2209742 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
440 | CONSTRUCTION OF MATERNITY BLOCK AT BOMBAGI HEALTH FACILITY NYCG/Q080/2015 - 2016 | [8 empty] | Health Services | Health Services | ENSON INVESTMENT |  | 19/4/2016 | 2016-04-10 |  | 3800593 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
441 | CONSTRUCTION OF OUT-PATIENT BLOCK AT RIAMONI HEALTH FACILITY NYCG/Q130/2015 - 2016 | [8 empty] | Health Services | Health Services | TREAMAOC (K) LTD |  | 19/4/2016 | 2016-04-10 |  | 3850260 | 3850260 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
442 | CONSTRUCTION OF OUT-PATIENT BLOCK AT TINDERETI HEALTH FACILITY NYCG/Q153/2015 - 2016 | [8 empty] | Health Services | Health Services | DENAMO GEN. SUPPLIERS LTD |  | 19/4/2016 | 2016-04-10 |  | 3960200 | 2394936 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
443 | CONSTRUCTION AND COMPLETION OF OPERATING THEATRE, X-RAY AND MATERNITY WARDS AT NYANSIONGO SUB-COUNTY HOSPITAL CGN/T074/2015-16 | [8 empty] | Health Services | Health Services | Sonje Investment LTD |  |  |  |  | 13586494 | 5219625.32 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
444 | Construction and Completion of 80 Bed Amenity Block with ¦Doctor’s Plaza at Nyamira County Referral Hospital CGN/T075/2015-16 | [6 empty] | TOWNSHIP |  | Health Services | Health Services | SEAMAN Building & Civil Engineers |  |  |  |  | 142319154.2 | 16201361.56 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
445 | CONSTRUCTION AND COMPLETION OF OPERATING THEATRE AT NYAMIRA COUNTY REFERRAL HOSPITAL CGN/T076/2015-16 | [6 empty] | TOWNSHIP |  | Health Services | Health Services | KEGIMA CONGRETE WORKS LTD |  |  |  |  | 18154731 | 6764958 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
446 | PROPOSED COMPLETION OF ESANI SUB COUNTY HOSPITAL STALLED STORY BUILDING NYCG/Q285/2015-16 | [8 empty] | Health Services | Health Services | MBOGO NYAGEKE TRANSPORTERS |  | 24/8/2016 | 16/12/2016 |  | 3975262 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
447 | PROPOSED DELIVERY, INSTALLATION, TESTING AND COMMISSIONONG OF WASHING MACHINES, TUMBLE DRYER AND COMMERCIAL IRONING MACHINE AT VARIOUS HOSPITALS CGN/T079/2015-2016 | [6 empty] | VARIOUS PARTS |  | Health Services | Health Services | G. NORTH & SONS LIMITED |  | 2016-01-09 | 29/11/2016 |  | 14665000 | 14665000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
448 | SUPPLY, DELIVERY, INSTALLATION, TESTING AND COMMISSIONING OF A 5-BED ICU UNIT AT NYAMIRA COUNTY REFERRAL HOSPITAL CGN/T080/2015-2016 | [6 empty] | TOWNSHIP |  | Health Services | Health Services | HOLLEY COTEC E.A LTD |  |  |  |  | 19311350 | 19308400 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
449 | SUPPLY & DELIVERY 5ICU VENTILATORS WITH TRAY, 5 PATIENT MONITOR, 5 INFUSION PUMP AND 5 SYRINGE PUMP, AT NYAMIRA COUNTY REFERRAL HOSPITAL CGN/T080/2015-2016 | [6 empty] | TOWNSHIP |  | Health Services | Health Services | FARAM E.A LTD |  |  |  |  | 434000 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
450 | SUPPLY & DELIVERY OF 2 SEMIFOWLER ELECTRIC BED, EMERGENCY/ANASTHESIA TRAY AND 10 I.V POLES AT NYAMIRA COUNTY REFERRAL HOSPITAL CGN/T080/2015-2016 | [6 empty] | TOWNSHIP |  | Health Services | Health Services | CROWN SOLUTIONS LTD |  | 24/8/2016 | 23/11/2016 |  | 5279000 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
451 | SUPPLY, DELIVERY, INSTALLATION, TESTING AND COMMISSIONING OF A MEDICAL OXYGEN GENERATING PLANT AT NYAMIRA COUNTY REFERRAL HOSPITAL CGN/T082/2015-2016 | [6 empty] | TOWNSHIP |  | Health Services | Health Services | CROWN SOLUTIONS LTD |  | 24/8/2016 | 23/11/2016 |  | 26000000 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
452 | SUPPLY OF MEDICAL EQUIPMENTS NYCG/Q246/2015-2016 | [8 empty] | Health Services | Health Services | HOLLEY COTEC E.A LTD |  | 24/8/2016 | 23/11/2016 |  | 2780000 | 2780000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
453 | CONSTRUCTION OF RIOTONYI OPD BLOCK NYCG/Q262/2015-2016 | [8 empty] | Health Services | Health Services | TABSHA SUPPLIES & GEN. CONTRACTORS |  | 2016-05-07 |  |  | 3985286 | 3985286 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
454 | PROPOSED CONSTRUCTION OF 2 NO. PIT LATRINES NYCG/Q279/2015-2016 | [8 empty] | Health Services | Health Services | KEBSAN KENYA LTD |  | 24/5/2016 |  |  | 1758281.6 | 1190421 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
455 | PROPOSED RENOVATION TO MCH TO HOUSE X-RAY AT GESIMA MODEL HEALTH CENTRE NYCG/Q282/2015-2016 | [8 empty] | Health Services | Health Services | EZECHE INVESTMENTS LIMITED |  | 24/5/2016 |  |  |  | 188790 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
456 | PROPOSED COMPLETION KAMBINI OUTPAPIENT BLOCK NYCG/Q283/2015-2016 | [8 empty] | Health Services | Health Services | MELBOUME ENGINEERING K. LTD |  | 24/5/2016 |  |  | 3943257 | 2553379.68 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
457 | CONSTRUCTION OF NYAKOE HEALTH FACILITY NYCG/Q331/2015-2016 | [8 empty] | Health Services | Health Services | KESVIC CO. LTD |  | 19/8/2016 |  |  | 3890122.64 | 3980284.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
458 | PROPOSED COMPLETION OF SERE OUTPAPIENT BLOCK NYCG/Q334/2015-2016 | [8 empty] | Health Services | Health Services | NYAKONG WORKS LTD |  | 24/5/2016 |  |  | 3150000 | 2958466.32 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
459 | PROPOSED COMPLETION OF NYAKEGOGI DISPENSARY NYCG/Q335/2015-2016 | [8 empty] | Health Services | Health Services | ZAFO CONSTRUCTION CO. LTD |  | 24/8/2016 |  |  | 3890302.2 | 3281280.98 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
460 | PROPOSED COMPLETION OF OUT PATIENT BLOCK GATUTA HEALTH CENTRE NYCG/Q440/2015-2016 | [8 empty] | Health Services | Health Services | KEMCO GEN. CONSTRUCTION CO. LTD |  | 24/5/2016 |  |  | 3890900 | 1554144.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
461 | PROPOSED RENOVATION TO MAIN BLOCK AT KIANUNGU HEALTH FACILITY NYCG/Q441/2015-2016 | [8 empty] | Health Services | Health Services | RIOMUSENDA CONST. CO LTD |  | 24/5/2016 |  |  | 1100000 | 1100000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
462 | PROPOSED RENOVATION OF MATERNITY BOCK AT GETIESI HEALTH FACILITY NYCG/Q442/2015-2016 | [8 empty] | Health Services | Health Services | GEOFAMA CONST. CO. LTD |  | 24/5/2016 |  |  | 3800699.4 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
463 | MAGWAGWA MARKET CGN/T031/2014-2015 | [6 empty] | MAGWAGWA |  | Land & Housing | Land & Housing | TELSHAN ENTERPRISES |  | 18/11/2015 | 2017-11-05 |  | 14615525.56 | 14615525.56 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
464 | IKONGE MARKET CGN/T032/2014-2015 | [6 empty] | TOWNSHIP |  | Land & Housing | Land & Housing | MASHABLE LIMITED |  | 19/11/2015 | 2017-12-05 |  | 10269278.16 | 10269278.16 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
465 | NYAMIRA COUNTY KIOSKIS CGN/T033/2014-2015 | [6 empty] | TOWNSHIP |  | Land & Housing | Land & Housing | SONJE INVESTMENT |  |  |  |  | 10607040 |  |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
466 | MAGOMBO MARKET CGN/T034/2014-2015 | [6 empty] | MAGOMBO |  | Land & Housing | Land & Housing | GIANCHE INVESTMENT |  | 19/11/2015 | 2016-12-05 |  | 10443931 | 10443391 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
467 | MOSOBETI MARKET CGN/T035/2014-2015 | [6 empty] | GESIMA |  | Land & Housing | Land & Housing | CLEROMARK EXCAVATORS CO. LTD |  | 19/11/2015 | 2016-12-05 |  | 19009211.16 | 13149349.19 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
468 | MOKOMONI MARKET CGN/T036/2014-2015 | [8 empty] | Land & Housing | Land & Housing | DAVKENN INVESTMENTS |  | 20/11/2015 | 13/5/2016 |  | 14632791 | 14632790 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
469 | REFURBSHMENT OF HOSPITAL STAFF QUARTERS | [6 empty] | TOWNSHIP |  | Land & Housing | Land & Housing | BAMPS ENTERPRISES |  | 19/6/2015 | 21/8/2015 |  | 2280000 | 2280000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
470 | RENOVATION OF OFFICE | [6 empty] | TOWNSHIP |  | Land & Housing | Land & Housing | TASLE SERVICES |  | 24/9/2015 | 19/11/2015 |  | 1537580 | 1537580 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
471 | CONSTRUCTION OF SEPTIC TANK AT NYAMIRA DISTRICT HOSPITAL STAFF QUARTERS | [6 empty] | TOWNSHIP |  | Land & Housing | Land & Housing | PARKENG AGENCIES |  | 24/09/2015 | 19/11/2015 |  | 1893584 | 1823024.05 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
472 | MOTOR CYCLE SHADE AT RAITIGO MKT NYCG/Q009/2015-2016 | [6 empty] | ESISE |  | Land & Housing | Land & Housing | Blue Chip Abasubati |  | 2016-10-02 | 23/3/2016 |  | 184954.8 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
473 | MOTOR CYCLE SHADES AT NYANDOCHE IBERE STAGE NYCG/Q010/2015-2016 | [6 empty] | NYANSIONGO |  | Land & Housing | Land & Housing | Johrobingham |  | 2016-10-02 | 23/3/2016 |  | 186092.7 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
474 | MOTOR CYCLE SHADE AT MABARIRI NYCG/Q013/2015-2016 | [6 empty] | BOMWAGAMO |  | Land & Housing | Land & Housing | Zantium Tech |  | 14/01/2016 | 25/2/2016 |  | 173944.13 | 173994.13 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
475 | MOTOR CYCLE SHADE AT ISINTA MKT NYCG/Q014/2015-2016 | [6 empty] | ITIBO |  | Land & Housing | Land & Housing | Alivas Holdings |  | 2016-12-01 | 23/2/2016 |  | 199868 | 199868 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
476 | MOTOR CYCLE SHADE AT EKERENYO STAGE NYCG/Q015/2015-2016 | [6 empty] | EKERENYO |  | Land & Housing | Land & Housing | Riomosenda Construction |  | 21/4/2016 | 2016-02-06 |  | 189613.6 | 189613 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
477 | MOTOR CYCLE SHADE AT IKONGE NYCG/Q015/2015-2016 | [6 empty] | EKERENYO |  | Land & Housing | Land & Housing | Ikobex Co. Ltd |  | 2016-12-01 | 23/2/2016 |  | 199868 | 199868 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
478 | MOTOR CYCLE SHADE AT MOTURUMESI NYCG/Q018/2015-2016 | [6 empty] | GACHUBA |  | Land & Housing | Land & Housing | Gennext Ltd |  | 2016-12-01 | 23/2/2016 |  | 198302 | 198302 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
479 | MOTOR CYCLE SHADE AT GIRANGO NYCG/Q018/2015-2016 | [6 empty] | GACHUBA |  | Land & Housing | Land & Housing | Dextetous Co. Ltd |  | 2016-12-01 | 23/2/2016 |  | 200868 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
480 | MOTOR CYCLE SHADE AT MABUNDU-BOBEMEBE JUNCTION NYCG/Q019/2015-2016 | [6 empty] | BOGICHORA |  | Land & Housing | Land & Housing | Levive Construction |  | 2016-12-01 | 23/2/2016 |  | 173363 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
481 | MOTOR CYCLE SHADE AT TINGA MKT NYCG/Q020/2015-2016 | [6 empty] | BOSAMARO |  | Land & Housing | Land & Housing | Eco-Care Ltd |  | 21/01/2016 | 2016-03-03 |  | 189207.6 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
482 | MOTOR CYCLE SHADE AT NYABITE NYCG/Q022/2015-2016 | [6 empty] | TOWNSHIP |  | Land & Housing | Land & Housing | Havepach |  | 2016-12-01 | 23/2/2016 |  | 174330.6 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
483 | MOTOR CYCLE SHADE AT NYAMIRA STAGE 1. NYCG/Q022/2015-2016 (Vemac) | [6 empty] | TOWNSHIP |  | Land & Housing | Land & Housing | Vemac Invest |  | 13/1/2016 | 24/2/2016 |  | 192554 | 192544 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
484 | MOTOR CYCLE SHADE AT NYAMIRA STAGE 2. NYCG/Q022/2015-2016 (Hemoot) | [6 empty] | TOWNSHIP |  | Land & Housing | Land & Housing | Hemoot Const. |  | 2016-08-01 | 19/2/2016 |  | 194532 | 194532 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
485 | MOTOR CYCLE SHADE AT KEMERA STAGE NYCG/Q023/2015-2016 | [6 empty] | KEMERA |  | Land & Housing | Land & Housing | Zamori Gen. |  | 2016-12-01 | 23/2/2016 |  | 185400 | 185400 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
486 | MOTOR CYCLE SHADE AT OMOGONHORO STAGE NYCG/Q023/2015-2016 | [6 empty] | KEMERA |  | Land & Housing | Land & Housing | Jamo Motores |  | 2016-12-01 | 23/2/2016 |  | 200868 | 200868 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
487 | MOTOR CYCLE SHADE AT RIKURUMA NYCG/Q025/2015-2016 | [6 empty] | MAGWAGWA |  | Land & Housing | Land & Housing | Richtech Ent. |  | 2016-08-01 | 19/2/2016 |  | 175055.6 | 175055 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
488 | MOTOR CYCLE SHADE AT MAGWAGWA MKT NYCG/Q025/2015-2016 | [6 empty] | MAGWAGWA |  | Land & Housing | Land & Housing | Sachem E. A Ltd |  | 2016-12-01 | 23/2/2016 |  | 198160 | 198160 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
489 | MOTOR CYCLE SHADE AT NYAMAIYA NYCG/Q026/2015-2016 | [6 empty] | NYAMAIYA |  | Land & Housing | Land & Housing | Jamo Propeties |  | 2016-12-01 | 23/2/2016 |  | 201040 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
490 | MOTOR CYCLE SHADES AT KONATE JUNCTION NYCG/Q027/2015-2016 | [6 empty] | BONYAMATUTA |  | Land & Housing | Land & Housing | Yunam Agencies |  |  |  |  | 199868 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
491 | MOTOR CYCLE SHADE AT KEBIRIGO MARKET NYCG/Q027/2015-2016 (Cmos ) | [6 empty] | BONYAMATUTA |  | Land & Housing | Land & Housing | CMOS Ent. |  | 2016-12-01 | 23/2/2016 |  | 174330.6 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
492 | MOTOR CYCLE SHADE AT NYAMUSI NYCG/Q028/2015-2016 | [6 empty] | BOKEIRA |  | Land & Housing | Land & Housing | Jom Gen. Cont |  | 14/1/2016 | 25/2/2016 |  | 199868 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
493 | MOTOR CYCLE SHADE AT MANGA MKT NYCG/Q009/2015-2016 | [6 empty] | ESISE |  | Land & Housing | Land & Housing | Diasa Gen. Suppliers |  | 23/3/2016 | 2016-04-05 |  | 174754 | 174754 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
494 | MOTOR CYCLE SHADE AT AMAKARA NYCG/Q010/2015-2016 | [6 empty] | NYANSIONGO |  | Land & Housing | Land & Housing | Eritech Enterprises |  | 22/3/2016 | 2016-03-05 |  | 179336 | 179336 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
495 | MOTOR CYCLE SHADE AT MWAMOGUSII JUNCTION NYCG/Q011/2015-2016 | [6 empty] | MEKENENE |  | Land & Housing | Land & Housing | Hest Holdings |  | 23/3/2016 | 2016-04-05 |  | 185778.6 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
496 | MOTOR CYCLE SHADE AT CHEBILAT NYCG/Q011/2015-2016 | [6 empty] | MEKENENE |  | Land & Housing | Land & Housing | Momisa Enterprises |  |  |  |  | 186051.7 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
497 | MOTOR CYCLE SHADE AT GESIMA MKT NYCG/Q012/2015-2016 | [6 empty] | GESIMA |  | Land & Housing | Land & Housing | Nivate Investment Limited |  | 15/4/2016 | 27/5/2016 |  | 178524 | 178524 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
498 | MOTOR CYCLE SHADE AT ESANI NYCG/Q012/2015-2016 | [6 empty] | GESIMA |  | Land & Housing | Land & Housing | Parkeng Agencies |  | 2016-12-04 | 24/5/2016 |  | 187061.6 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
499 | MOTOR CYCLE SHADE AT ERONGE NYCG/Q013/2015-2016 | [6 empty] | BOMWAGAMO |  | Land & Housing | Land & Housing | Associated Firm Agro Plant |  | 2016-12-04 | 24/5/2016 |  | 199647 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
500 | MOTOR CYCLE SHADE AT TOMBE JUNCTION NYCG/Q014/2015-2016 | [6 empty] | ITIBO |  | Land & Housing | Land & Housing | Dap-Del Chefta |  | 21/3/2016 | 2016-02-05 |  | 190672 | 190762 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
501 | MOTOR CYCLE SHADE AT YAYA CENTRA-NYARAMBA MKT NYCG/Q016/2015-2016 | [6 empty] | KIABONYORU |  | Land & Housing | Land & Housing | Winmu Agency |  | 22/3/2016 | 2016-03-05 |  | 199000.6 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
502 | MOTOR CYCLE SHADE AT ONSEKA JUNCTION-NYAWARE RD MOKOMONI MKT NYCG/Q016/2015-2016 | [6 empty] | KIABONYORU |  | Land & Housing | Land & Housing | Sanyakon (K) Ltd |  | 21/3/2016 | 2016-02-05 |  | 194938 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
503 | MOTOR CYCLE SHADE AT MAGOMBO MKT NYCG/Q017/2015-2016 | [6 empty] | MAGOMBO |  | Land & Housing | Land & Housing | Honet Co. Ltd |  | 23/3/2016 | 2016-04-05 |  | 182366 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
504 | MOTOR CYCLE SHADE AT NYAIKURO STAGE NYCG/Q017/2015-2016 | [6 empty] | MAGOMBO |  | Land & Housing | Land & Housing | Digital Const. ltd |  | 2016-12-04 | 24/5/2016 |  | 189787 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
505 | MOTOR CYCLE SHADE AT SIRONGA STAGE NYCG/Q019/2015-2016 | [6 empty] | BOGICHORA |  | Land & Housing | Land & Housing | Demar Ent. Ltd |  | 21/3/2016 | 2016-02-05 |  | 191458 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
506 | MOTOR CYCLE SHADE AT MOSOBETI MKT NYCG/Q020/2015-2016 | [6 empty] | BOSAMARO |  | Land & Housing | Land & Housing | Samalic Communications |  | 23/3/2016 | 2016-04-05 |  | 173362 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
507 | MOTOR CYCLE SHADE AT TOMBE MKT NYCG/Q021/2015-2016 | [6 empty] | MANGA |  | Land & Housing | Land & Housing | Matuta Const. Ltd |  | 21/3/2016 | 2016-02-05 |  | 192850 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
508 | MOTOR CYCLE SHADE AT MANGA NYCG/Q021/2015-2016 | [6 empty] | MANGA |  | Land & Housing | Land & Housing | Joy Const. Ltd |  |  |  |  | 189787.6 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
509 | MOTOR CYCLE SHADE AT RIGOMA MKT NYCG/Q024/2015-2016 | [6 empty] | RIGOMA |  | Land & Housing | Land & Housing | Nivate Investment Limited |  | 23/3/2016 | 2016-04-05 |  | 181366 | 181366 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
510 | MOTOR CYCLE SHADE AT IBENCHO NYCG/Q025/2015-2016 | [6 empty] | MAGWAGWA |  | Land & Housing | Land & Housing | Wycrow Contractors Ltd |  | 21/3/2016 | 2016-02-05 |  | 194938 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
511 | MOTOR CYCLE SHADE AT MIRUKA STAGE NYCG/Q026/2015-2016 | [6 empty] | NYAMAIYA |  | Land & Housing | Land & Housing | Valar Adhesive Limited |  | 22.3.2016 | 2016-03-05 |  | 198603 | 198603 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
512 | MOTOR CYCLE SHADE AT KEBIRIGO MKT NYCG/Q027/2015-2016 (Ujamaa) | [6 empty] | BONYAMATUTA |  | Land & Housing | Land & Housing | Ujamaa Co. Ltd |  | 23/3/2016 | 2016-04-05 |  | 180000 | 180000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
513 | MOTOR CYCLE SHADE AT OMOSARIA NYCG/Q028/2015-2016 | [6 empty] | BOKEIRA |  | Land & Housing | Land & Housing | Kebirigo Const. & Gen Supplies |  | 21/3/2016 | 2016-02-05 |  | 195402 | 195402 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
514 | OPENING OF IKONGE ROAD (LAOUR BASED METHOD) | [8 empty] | Land & Housing | Land & Housing | RICHARD ONDIEKI MARERI |  |  |  |  | 2500000 | 2500000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
515 | COMPLETION OF NYABITE RETAIL MARKET CGN/T061/2015 -2016 | [6 empty] | TOWNSHIP |  | Land & Housing | Land & Housing | MIYAGI CONST. CO. LTD |  | 25/5/2016 | 20/7/2016 |  | 4515300 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
516 | CONSTRUCTION OF CAR PARKING LOTS IN NYAMIRA TOWN CGN/T062/2015-2016 | [6 empty] | TOWNSHIP |  | Land & Housing | Land & Housing | BOFLOS ENT. LTD |  | 2016-09-05 | 2016-05-09 |  | 15400308.48 | 8913486.39 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
517 | REFURBISHMENT OF HOSPITAL STAFF QUARTERS IN NYAMIRA HOSPITAL NYCG/Q081/2015-2016 | [6 empty] | TOWNSHIP |  | Land & Housing | Land & Housing | MARANI HOLDINGS LTD. |  | 2016-09-05 | 13/6/2016 |  | 1433866.72 | 1433866.72 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
518 | CONSTRUCTION OF 6 NUMBER PIT LATRINE AT TINGA MKT NYCG/Q105/2015-2016 | [8 empty] | Land & Housing | Land & Housing | Zantium Tech. |  |  |  |  | 779206.8 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
519 | CONSTRUCTION OF 6 NUMBER PIT LATRINE AT MANGA ENSOKO NYCG/Q106/2015-2016 | [8 empty] | Land & Housing | Land & Housing | MWAMOGUSII BUILDING CONT. LTD |  |  |  |  | 799265.69 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
520 | CONSTRUCTION OF 6 NUMBER PIT LATRINE AT MANGA ESABA NYCG/Q108/2015-2016 | [8 empty] | Land & Housing | Land & Housing | NYABIS GEN. CONST. WRKS LTD. |  |  |  |  | 785631.81 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
521 | CONSTRUCTION OF 6 NUMBER PIT LATRINE AT MOTURUMESI NYCG/Q109/2015-2016 | [8 empty] | Land & Housing | Land & Housing | MOKIA E. A LTD |  |  |  |  | 723601.04 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
522 | CONSTRUCTION OF 6 NUMBER PIT LATRINE AT ITIBO NYCG/Q110/2015-2016 | [6 empty] | ITIBO |  | Land & Housing | Land & Housing | Dap-Del Chefta |  |  |  |  | 726390 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
523 | CONSTRUCTION OF 6 NUMBER PIT LATRINE AT KEMERA NYCG/Q111/2015-2016 | [8 empty] | Land & Housing | Land & Housing | REGAN SOLUTIONS LTD. |  |  |  |  | 795423.6 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
524 | CONSTRUCTION OF 6 NUMBER PIT LATRINE AT CHEBILAT NYCG/Q112/2015-2016 | [8 empty] | Land & Housing | Land & Housing | DAMIKO BUILDING & CONST. |  |  |  |  | 792360 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
525 | CONSTRUCTION OF 6 NUMBER PIT LATRINE AT METAMAYWA MKT NYCG/Q113/2015-2016 | [6 empty] | RIGOMA |  | Land & Housing | Land & Housing | AGITECH LOGISTICS LTD |  |  |  |  | 843099.6 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
526 | CONSTRUCTION OF MIRUKA BUS PARK NYCG/Q216/2015-2016. | [6 empty] | NYAMAIYA |  | Land & Housing | Land & Housing | Eighteen Sixty Communication Ltd |  | 2016-09-06 | 2016-04-08 |  | 2489070 | 2310956 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
527 | REFURBISHMENT OF NYANSIONGO TOWN ADMINISTRATION OFFICES NYCG/Q229/2015-2016 | [6 empty] | NYANSIONGO |  | Land & Housing | Land & Housing | Damiko Building & Construction |  | 2016-09-06 | 14/7/2016 |  | 1321770 | 1321770 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
528 | PROPOSED CONSTRUCTION OF CAR PARKING LOTS BETWEEN NYAMIRA LEVEL 5 HOSPITAL AND HUDUMA CENTRE IN NYAMIRA TOWN (LOT-2) CGN/T08/2016-2017 | [6 empty] | TOWNSHIP |  | Land & Housing | Land & Housing | RODZ LIMITED |  | 30/11/2016 | 31/5/2017 |  | 12996483.4 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
529 | PROPOSED CONSTRUCTION OF CAR PARKING LOTS BETWEEN PUBLIC WORKS AND CO-OP BANK IN NYAMIRA TOWN (LOT-1) CGN/T09/2016-2017 | [6 empty] | TOWNSHIP |  | Land & Housing | Land & Housing | BREMA CONSTRUCTION CO. LTD |  | 30/11/2016 | 31/5/2017 |  | 29267022.2 | 15376187 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
530 | EXPRESSION OF INTEREST FOR PURCHASE OF LAND WITHIN KEROKA TOWN ( 2 ACRES) CGN/EOI/1/2016-2017 | [6 empty] | RIGOMA |  | Land & Housing | Land & Housing | FRANCIS ABUYA KUNYORIA |  | 30/11/2016 | 28/2/2017 |  | 3800000 | 3800000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
531 | EXPRESSION OF INTEREST FOR PURCHASE OF LAND WITHIN KIABONYORU WARD ( 2 ACRES) CGN/EOI/1/2016-2017 | [6 empty] | KIABONYORU |  | Land & Housing | Land & Housing | WILFRED NYAUMA BANGIRI |  | 30/11/2016 | 28/2/2017 |  | 3600000 | 3600000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
532 | STREET LIGHTING | [6 empty] | COUNTY-WIDE |  | Envirinment and Natural Resources | Envirinment and Natural Resources | RURAL DEVELOPMENT SOLUTIONS |  | 26/6/2014 | 2014-09-10 |  | 25000000 | 25000000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
533 | BAMBOO CONSULTANCY | [8 empty] | Envirinment and Natural Resources | Envirinment and Natural Resources |  |  | 2014-10-06 | 23/7/2014 |  | 2264320 | 2264320 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
534 | STREET LIGHTING | [6 empty] | VARIOUS |  | Envirinment and Natural Resources | Envirinment and Natural Resources | RURAL DEVELOPMENT SOLUTIONS |  | 2015-06-04 | 15/4/2015 |  | 5000000 | 5000000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
535 | ASSORTED SEEDLING | [6 empty] | VARIOUS |  | Envirinment and Natural Resources | Envirinment and Natural Resources | BRAMON |  | 2014-10-06 | 15/7/2014 |  | 1220000 | 1200000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
536 | G.I.S CONSULTANCY SERVICES | [8 empty] | Envirinment and Natural Resources | Envirinment and Natural Resources | GEO ENVIAGRO SOLUTIONS INTERNATIONAL |  | 15/5/2014 | 19/6/2014 |  | 4865910 | 4865910 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
537 | DEVELOPMENT OF GRID CONNECTED AND OFF GRID SOLAR POWER PLANTS (EOI) CGN/T042/2014-2015 | [8 empty] | Envirinment and Natural Resources | Envirinment and Natural Resources | VATEKI INTERNATIONAL HOLDINGS LTD |  | 21/10/2015 |  |  | 10000000 | 10000000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
538 | OMORARE BOREHOLE CGN/T038/2014-2015 | [6 empty] | EKERENYO |  | Envirinment and Natural Resources | Envirinment and Natural Resources | TOSACO HOLDINGS |  | 24/2/2016 | 30/6/2016 |  | 4022775 | 3744375 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
539 | NYARIACHO BOREHOLE CGN/T039/2014-2015 | [6 empty] | GACHUBA |  | Envirinment and Natural Resources | Envirinment and Natural Resources | EXPORT HYDRO PUMP SERVICES LTD |  | 25/2/2016 | 30/6/2016 |  | 3611080 | 2524276 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
540 | NYANCHONORIA BOREHOLE CGN/T040/2014-2015 | [6 empty] | RIGOMA |  | Envirinment and Natural Resources | Envirinment and Natural Resources | EXPORT HYDRO PUMP SERVICES LTD |  | 25/2/2016 | 30/6/2016 |  | 2583320 | 2583320 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
541 | NYANDOCHE IBERE B/HOLE CGN/T041/2014-2015 | [6 empty] | NYANSIONGO |  | Envirinment and Natural Resources | Envirinment and Natural Resources | WOTECH KENYA LIMITED |  | 23/2/2016 | 29/6/2016 |  | 4508572 | 2457460 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
542 | CONSULTANCY SERVICES FOR SOLID WASTE MANAGEMENT CGN/T016/2014-2015 | [8 empty] | Envirinment and Natural Resources | Envirinment and Natural Resources | CALSAMS AND GIDKEMTONS CONSULTANCY LTD |  |  |  |  | 7500000 | 7500000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
543 | SOLAR POWERED STREET LIGHTING CGN/T017/2015-2016 (Biomax Africa) | [8 empty] | Envirinment and Natural Resources | Envirinment and Natural Resources | Biomax Africa |  | 2016-10-03 |  |  | 63904500 | 63904500 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
544 | CONSTRUCTION OF BOMWAGAMO NYAMUSI WATER SUPPLY CGN/T063/2015 - 2016 | [6 empty] | BOMWAGAMO |  | Envirinment and Natural Resources | Envirinment and Natural Resources | BREMA CONST. CO. LTD |  | 2016-10-06 | 2016-10-09 |  | 11851263.9 | 10757296.79 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
545 | DRILLING OF ENCHORO BOREHOLE CGN/T064/2015 - 2016 | [6 empty] | BOSAMARO |  | Envirinment and Natural Resources | Envirinment and Natural Resources | KWANYA INTERGLOBAL LTD |  | 20/6/2016 | 20/9/2016 |  | 5759687.4 | 3150188.8 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
546 | CONSTRUCTION OF KEMASARE WATER PROJECT CGN/T065/2015 - 2016 | [6 empty] | NYAMAIYA |  | Envirinment and Natural Resources | Envirinment and Natural Resources | SAUMO ENT. LTD |  | 2016-10-06 | 2016-10-09 |  | 22084014.8 | 18598687 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
547 | CONSTRUCTION OF KITARU EMBOYE WATER PROJECT CGN/T066/2015 - 2016 | [6 empty] | KIABONYORU/MEKENENE |  | Envirinment and Natural Resources | Envirinment and Natural Resources | VIMARCON LTD |  | 2016-07-06 | 2016-07-09 |  | 7102375.8 | 3906100 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
548 | CONSTRUCTION OF NYABISIMBA WATER SUPPLY CGN/T067/2015 - 2016 | [6 empty] | BONYAMATUTA |  | Envirinment and Natural Resources | Envirinment and Natural Resources | ALDAN INTERNATIONAL LTD |  | 2016-07-06 | 2016-07-09 |  | 5562240.6 | 2779462.5 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
549 | CONSTRUCTION OF NYANSIONGO GEKONGE WATER SUPPLY CGN/T068/2015 - 2016 | [6 empty] | BOKEIRA |  | Envirinment and Natural Resources | Envirinment and Natural Resources | MANKONE CONST. CO LTD |  | 2016-07-06 | 2016-07-09 |  | 7073475 | 7073475 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
550 | CONSTRUCTION OF RAITIGO WATER SUPPLY CGN/T069/2015 - 2016 | [6 empty] | ESISE |  | Envirinment and Natural Resources | Envirinment and Natural Resources | DAVKEN INVESTMENT |  | 2016-06-06 | 2016-06-09 |  | 8862588.2 | 8441316 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
551 | CONSTRUCTION OF RITIBO WATER SUPPLY CGN/T070/2015 - 2016 | [6 empty] | GESIMA |  | Envirinment and Natural Resources | Envirinment and Natural Resources | DEXTEREOUS LIMITED |  |  |  |  | 4563588.2 | 2649966.95 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
552 | PROPOSED HOME SOLAR LIGHTING CGN/T071/2015 - 2016 | [6 empty] | COUNTY-WIDE |  | Envirinment and Natural Resources | Envirinment and Natural Resources | BIOLITE LTD |  |  |  |  | 7349600 | 7349600 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
553 | PROPOSED CONST. OF KEMASARE II WATER SUPPLY CGN/T020/2016-2017 | [6 empty] | NYAMAIYA |  | Envirinment and Natural Resources | Envirinment and Natural Resources | ZIPCO HOLDINGS |  | 20/4/2017 | 20/7/2017 |  | 4748286 | 2500000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
554 | PROPOSED CONST. OF NYAMBARIA I WATER PROJECT CGN/T021/2016-2017 | [6 empty] | MAGOMBO |  | Envirinment and Natural Resources | Envirinment and Natural Resources | GIACHE INVESTMENT |  | 20/4/2017 | 20/7/2017 |  | 13214137 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
555 | PROPOSED DRILLING OF BOSIANGO BOREHOLECGN/T022/2016-2017 | [6 empty] | BOGICHORA |  | Envirinment and Natural Resources | Envirinment and Natural Resources | BARIZE CONSTRUCTION |  | 20/4/2017 | 20/7/2017 |  | 3949336 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
556 | PROPOSED CONST. OF ERONGE PRIMARY WATER SUPPLY CGN/T023/2016-2017 | [6 empty] | ESISE |  | Envirinment and Natural Resources | Envirinment and Natural Resources | MATRIX CONSULTANCY |  | 20/4/2017 | 20/7/2017 |  | 2317367 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
557 | PROPOSED DRILLING OF GESURE BOREHOLE CGN/T024/2016-2017 | [6 empty] | MANGA |  | Envirinment and Natural Resources | Envirinment and Natural Resources | GESURE BUILDING |  | 20/4/2017 | 20/7/2017 |  | 3254960 | 3254960 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
558 | PROPOSED DRILLING OF RIOMEGO BOREHOLE CGN/T025/2016-2017 | [6 empty] | MAGWAGWA |  | Envirinment and Natural Resources | Envirinment and Natural Resources |  |  | 20/4/2017 | 20/7/2017 |  |  | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
559 | PROPOSED CONST. OF NYANSIONGO GEKONGE II WATER SUPPLY CGN/T026/2016-2017 | [6 empty] | MAGWAGWA |  | Envirinment and Natural Resources | Envirinment and Natural Resources | SONJE INVESTMENT |  | 20/4/2017 | 20/7/2017 |  | 3283374 | 1500000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
560 | PROPOSED CONST. OF RAITIGO II WATER SUPPLY CGN/T027/2016-2017 | [6 empty] | ESISE |  | Envirinment and Natural Resources | Envirinment and Natural Resources | STRATEGY ENGINEERING CO. LTD |  | 20/4/2017 | 20/7/2017 |  | 8439327.12 | 3000000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
561 | PROPOSED CONST. OF KIABONYORU WATER SUPPLY CGN/T028/2016-2017 | [6 empty] | KIABONYORU |  | Envirinment and Natural Resources | Envirinment and Natural Resources | BREMA CONSTRUCTION CO. LTD |  | 20/4/2017 | 20/7/2017 |  | 22181629 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
562 | PROPOSED CONST. OF NYANCHONORIA WATER SUPPLY CGN/T029/2016-2017 | [6 empty] | RIGOMA |  | Envirinment and Natural Resources | Envirinment and Natural Resources | KEGIMA CONCRETE |  | 20/4/2017 | 20/7/2017 |  | 4791994.8 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
563 | PROPOSED CONST. OF NYANDOCHE IBERE WATER SUPPLY CGN/T030/2016-2017 | [6 empty] | NYANSIONGO |  | Envirinment and Natural Resources | Envirinment and Natural Resources | OBIMORA CONSTRUCTION |  | 20/4/2017 | 20/7/2017 |  | 4290109.2 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
564 | PROPOSED CONST. OF NYARIACH WATER SUPPLY CGN/T031/2016-2017 | [6 empty] | GACHUBA |  | Envirinment and Natural Resources | Envirinment and Natural Resources | GETARE GETS |  | 20/4/2017 | 20/7/2017 |  | 4221429 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
565 | PROPOSED CONST. OF OMORARE WATER SUPPLY CGN/T032/2016-2017 | [6 empty] | EKERENYO |  | Envirinment and Natural Resources | Envirinment and Natural Resources | HONET COMPANY LTD |  | 20/4/2017 | 20/7/2017 |  | 3313725.6 | 2500000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
566 | PROPOSED CONST. OF TINGA/EKORO WATER SUPPLY CGN/T033/2016-2017 | [6 empty] | MAGOMBO/ BOSAMARO |  | Envirinment and Natural Resources | Envirinment and Natural Resources | ALDAN INTERNATIONAL |  | 20/4/2017 | 20/7/2017 |  | 6814051.2 | NIL |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
567 | SUPPLY, DELIVERY, INSTALLATION, COMMISSIONING AND MAINTENANCE OF 42 POLES SOLAR POWERED STREET LIGHTING PROJECT IN NYAMIRA COUNTY CGN/T057/2016-2017 | [8 empty] | Envirinment and Natural Resources | Envirinment and Natural Resources | BIOMAX AFRICA LTD |  | 25/5/2017 | 25/8/2017 |  | 10980040 | 8783932 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
568 | NYABITE MARKET | [6 empty] | TOWNSHIP |  | Trade & Tourism | Trade & Tourism | ZAFO CONSTRUCTION |  | 20/05/2014 | 2014-09-09 |  | 11900416.8 | 11900416.4 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
569 | KEROKA MARKET | [6 empty] | RIGOMA |  | Trade & Tourism | Trade & Tourism | GIANCE INVESTMENT |  | 20/05/2014 | 2014-09-09 |  | 24099139 | 24099139 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
570 | GIRANGO MARKET | [6 empty] | GACHUBA |  | Trade & Tourism | Trade & Tourism | ARCAD LTD |  | 20/05/2014 | 2014-09-09 |  | 11701642 | 11230686.5 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
571 | KIOGE MKT TOILET | [8 empty] | Trade & Tourism | Trade & Tourism | TOSACO HOLDINGS |  | 15/6/2015 | 14/9/2015 |  | 804170 | 804170 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
572 | NYAMUSI MKT TOILET | [6 empty] | BOKEIRA |  | Trade & Tourism | Trade & Tourism | HONET LTD |  | 2015-10-06 | 2015-10-09 |  | 801096 | 739123 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
573 | ITIBO MKT TOILET | [6 empty] | ITIBO |  | Trade & Tourism | Trade & Tourism | SACHEM E. A LTD |  | 2015-10-06 | 2015-10-09 |  | 726531.2 | 726531.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
574 | MAKAIRO MKT TOILET | [6 empty] | BOGICHORA |  | Trade & Tourism | Trade & Tourism | FIBRE BUSINESS SYSTEMS |  | 15/4/2015 | 15/6/2015 |  | 807165 | 739964 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
575 | TOMBE MKT TOILET | [6 empty] | MANGA |  | Trade & Tourism | Trade & Tourism | MEDKEN INTERNAL LTD |  | 2015-05-05 | 2015-04-08 |  | 765036 | 765036 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
576 | NYARAMBA MKT TOILET | [8 empty] | Trade & Tourism | Trade & Tourism | GLEAMING SERVICES |  |  |  |  | 727389.6 |  |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
577 | KEGOGI MKT TOILET | [6 empty] | KIABONYORU |  | Trade & Tourism | Trade & Tourism | MASHABLE LTD |  | 29/5/2015 | 30/8/2015 |  | 726973.2 | 726973.2 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
578 | NYARONDE MKT TOILET | [6 empty] | NYANSIONGO |  | Trade & Tourism | Trade & Tourism | ZAMORI GEN. CONTRACTORS |  | 27/5/2015 | 30/8/2015 |  | 726512.64 | 726512.64 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
579 | MOCHENWA MKT TOILET | [6 empty] | GESIMA |  | Trade & Tourism | Trade & Tourism | LUCK-WILL LTD |  | 13/4/2015 | 2015-08-06 |  | 727612.6 | 727612.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
580 | BONYUNYU MKT TOILET | [6 empty] | NYAMAIYA |  | Trade & Tourism | Trade & Tourism | ORCHARDS YOUTH ENT |  |  |  |  | 748870 | 748870 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
581 | GESIMA MKT TOILET | [6 empty] | GESIMA |  | Trade & Tourism | Trade & Tourism | LILA CREATIVE DESIGN |  | 24/6/2015 | 23/9/2015 |  | 769901 | 769901 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
582 | MIRUKA MKT TOILET | [6 empty] | NYAMAIYA |  | Trade & Tourism | Trade & Tourism | AFRO-GLOBE HOLDINGS |  | 15/4/2015 | 15/6/2015 |  | 826256.4 | 826256.4 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
583 | PROPOSED CONST. AND COMPLETION OF MANGA FENCE NYCG/Q339/2016-2017 | [6 empty] | Manga |  | Trade & Tourism | Trade & Tourism | INTERSTATE COMPANY LTD |  | 26/5/2017 |  |  | 2571383 | 2571383 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
584 | PROPOSED CONST. AND COMPLETION OF MOKOMONI MARKET FENCE NYCG/Q340/2016-2017 | [6 empty] | MEKENENE |  | Trade & Tourism | Trade & Tourism | KEANGI ENTERPRISES |  | 26/5/2017 |  |  | 2084847.7 | 2084847.7 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
585 | PROPOSED CONST. AND COMPLETION OF MAGWAGWA MARKET FENCE NYCG/Q341/2016-2017 | [6 empty] | MAGWAGWA |  | Trade & Tourism | Trade & Tourism | KEBSAN |  | 26/5/2017 |  |  | 2099890 | 2099890 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
586 | INTERNET & INTERCOM CONNECTIVITY | [6 empty] | TOWNSHIP |  | Finance & Economic Planning | Finance & Economic Planning | TELECOVER COMMUNICATIONS |  | 15/5/2014 | 19/6/2014 |  | 1856649.6 | 1856649.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
587 | REFURBISHMENT TO ECM FINANCE'S OFFICE NYCG/Q065/2014-2015 | [6 empty] | TOWNSHIP |  | Finance & Economic Planning | Finance & Economic Planning |  |  | 2015-04-05 | 2015-04-06 |  | 3757530 | 3757530 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2025
588 | TISSUE CULTURE BANANAS (Agroplant) | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | AGRO PLANT TECHNOLOGY |  | 2014-10-04 | 15/5/2014 |  | 5396000 | 5396000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
589 | FISH POND SEINE NETS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | LAVAMANCE INVESTMENT |  | 21/3/2014 | 26/04/2014 |  | 630000 | 630000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
590 | MIXED SEX FISH FINGERLINGS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | RIVERSIDE INTERNATIONAL |  | 24/3/2014 | 31/4/2014 |  | 800000 | 800000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
591 | FISH POND LINERS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | MASTER PIECE INVESTMENT |  | 28/3/2014 | 2014-02-05 |  | 1327200 | 1327200 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
592 | TISSUE CULTURE BANANAS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES |  |  | 2014-10-04 | 15/5/2014 |  | 5396000 | 5396000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
593 | TISSUE CULTURE BANANAS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | KISII ATC |  |  |  |  | 280000 | 280000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
594 | FISH(MONOSEX) FINGERLINGS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | JEWLET ENTERPRISE |  | 28/3/2015 | 2014-02-05 |  | 2600000 | 2600000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
595 | GREEN HOUSES | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | JUSTINPOX ENTERPRISES |  | 2014-09-05 | 13/6/2014 |  | 25248000 | 25248000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
596 | VETERINARY A.I | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | LOWER KABETE |  | 31/3/2014 | 2014-05-05 |  | 2338700 | 2338700 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
597 | AQUARIUM & FISH EQUIPMENT | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | RIVERSIDE HATCHERIES |  | 23/6/2014 | 28/7/2014 |  | 280200 | 280200 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
598 | DAIRY GOATS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | NYAKAMBE GEN, SUPPLIERS |  |  |  |  | 6486000 | 6486000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
599 | APIARY SET UP KITS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | M/S THE HIVE LIMITED |  | 23/6/2014 | 28/7/2014 |  | 3700000 | 3700000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
600 | LIVESTOCK FEED MIXER, PELLETISER & PULVERISER | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | GESEBE SUPPLIERS |  | 27/1/2014 | 2014-03-03 |  | 1420000 | 1420000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
601 | VETERINARY DRUG | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | SAMJOY AGROVET |  | 22/1/2014 | 26/2/2014 |  | 8491750 | 8491750 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
602 | PASSION FRUITS (Okosambu) | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | OKOSAMBO |  |  |  |  | 800000 | 800000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2013/2014
603 | DAIRY GOATS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | MERU GOAT BREEDERS |  | 2015-04-05 | 2015-08-06 |  | 9000000 | 9000000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
604 | SUPPLY OF FISH MATERIALS AND EQUIPMENT | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | EARGE LIMITED |  | 15/5/2015 | 19/6/2015 |  | 835000 | 835000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
605 | FISH POND NETS, LINERS AND WEIGHING SCALES | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | MANKONE CONSTRUCTION |  | 13/5/2015 | 17/6/2015 |  | 1388470 | 1388470 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
606 | FISH PELLETS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | GETARE GETS JOINT SUPPLY |  | 18/5/2015 | 22/6/2015 |  | 1998000 | 1998000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
607 | FISH FINGERLINGS/ SEEDS (MONOSEX) | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | JEWLET ENT. |  | 14/5/2015 | 25/6/2015 |  | 1980000 | 1980000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
608 | FISH FINGERLINGS/SEEDS (MIXED SEX) | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | JEWLET ENT. |  | 14/5/2015 | 25/6/2015 |  | 1825560 | 1825560 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
609 | FISH FEEDS AND FERTILIZERS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | MAPEX MERCHANTS |  | 15/5/2015 | 19/6/2015 |  | 1003600 | 1003600 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
610 | POULTRY EGG INCUBATORS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | ECHOCHICKS KENYA LTD |  | 17/6/2015 | 22/7/2015 |  | 575000 | 575000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
611 | SWEET POTATO VINE CUTTINGS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES |  |  | 17/6/2015 | 22/7/2015 |  | 900000 | 900000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
612 | LOCAL CHIKEN, CHICK AND DUCK MASH | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | COUNTY CENTRE SUPPLIES |  | 17/6/2015 | 22/7/2015 |  | 3350000 | 3350000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
613 | TISSUE CULTURE BANANA PLANTLETS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES |  |  | 18/6/2015 | 23/7/2015 |  | 700,00 | 700,00 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
614 | FARM INPUTS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES |  |  | 16/6/2015 | 21/7/2015 |  | 337000 | 337000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
615 | GREEN HOUSES | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES |  |  | 17/6/2015 | 22/7/2015 |  | 6452000 | 6452000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2014/2015
616 | APIARY KITS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | HIVE LIMITED |  | 2016-11-02 |  |  | 19500000 | 19500000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
617 | SUPPLY OF SEEDS & FERTILIZERS CGN/T016/2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | AMIRAN (K) LTD |  | 22/04/2016 | 23/5/2016 |  | 47596800 | 47596800 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
618 | SUPPLY OF SOLAR DRIERS NYCG/Q047/2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | COLISTER GENERAL WORKS LTD |  | 25/04/2016 | 25/5/2016 |  | 1600000 | 1600000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
619 | SUPPLY OF BANANA SEEDLINGS NYCG/Q053/2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | MASAMARO YOUTH GROUP |  | 25/4/2016 | 25/5/2016 |  | 1995000 | 1995000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
620 | SUPPLY OF ACARICIDES AND STABLIZERS FOR DIPS REVIVAL NYCG/Q155/2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | IKOBEX CO. LTD |  | 30/5/2016 |  |  | 1665000 | 1665000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
621 | SUPPLY OF VETERINARY DRUGS NYCG/Q221 /2015-2016. | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | PRECISION DESIGNERS |  | 2016-02-06 |  |  | 945000 | 945000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
622 | SUPPLY OF MATERIALS FOR TRAINING AND FOR DEMONSTRATION NYCG/Q226/ 2015-2016. | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | DAP DEL CHEFTER KENYA LIMITED |  | 2016-02-06 |  |  | 1086000 | 1086000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
623 | SUPPLY OF LOCAL VEGETABLE PLANTING MATERIALS NYCG/Q227/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | THREE ZISTERS LTD |  | 2016-02-06 |  |  | 1900000 | 1900000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
624 | SUPPLY OF AGRO CHEMICALS NYCG/Q228/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | ENCOUNTER QUALITY SERVICES |  | 2016-02-06 |  |  | 1000000 | 1000000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
625 | FOR SUPPLY OF VETERINARY DRUGS NYCG/Q238/ 2015-2016. | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | BETTER KENYA GROUP |  | 2016-07-06 |  |  | 385000 | 385000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
626 | SUPPLY OF TISSUE CULTURE BANANA PLANTLETS NYCG/Q240/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | STABILIAN LIMITED |  | 2016-02-06 |  |  | 1484000 | 1484000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
627 | SUPPLY OF CHICKEN FEEDS AND OTHER MATERIALS NYCG/Q241/2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | ISSACHEM YOUTH GENERAL SUPPLIERS |  | 2016-02-06 |  |  | 1592000 | 1592000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
628 | SUPPLY OF CERTIFIED SEEDS NYCG/Q242/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | EARGE LIMITED |  | 2016-02-06 |  |  | 1900000 | 1900000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
629 | SUPPLY OF VETERINARY MATERIALS NYCG/Q243/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | LIDOM TRANSMISSION |  | 2016-02-06 |  |  | 527300 | 527300 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
630 | SUPPLY OF 8 WEEKS IMPROVED POULTRY BIRDS NYCG/Q267/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | NACROB GENERAL SUPPLIES |  | 2016-07-06 |  |  | 1920000 | 1920000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
631 | SUPPLY OF VETERINARY VACCINES NYCG/Q289/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | RIOMUSENDA COMPANY LIMITED |  | 15/6/2016 |  |  | 1500000 | 1500000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
632 | SUPPLY OF 3NO. INCUBATORS NYCG/Q290/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | MIRUKA GENERAL STORES |  | 2016-09-06 |  |  | 450000 | 450000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
633 | SUPPLY OF DAIRY PRODUCTION MATERIALS NYCG/Q298/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | BOOMAGE ENTERPRISE |  |  |  |  | 1975500 | 1975500 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
634 | SUPPLY OF VETERINARY MATERIALS NYCG/Q299/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | JAGETA ENTERPRISES |  | 2016-10-06 |  |  | 596720 | 596720 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
635 | SUPPLY OF CALF REARING MATERILAS NYCG/Q300/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | STABILIAN LIMITED |  | 2016-10-06 |  |  | 1770000 | 1770000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
636 | SUPPLY OF RICE PROMOTIONAL MATERIALS NYCG/Q301/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | LIDOM TRANSMISSION |  | 2016-10-06 |  |  | 1477000 | 1477000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
637 | SUPPLY OF HIGH QUALITY BREEDING BIRDS NYCG/Q302/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | LIGLAS INVESTMENT |  | 2016-03-06 |  |  | 1750000 | 1750000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
638 | SUPPLY OF FARM INPUTS FOR DEMONSTRATION AND TRAINING NYCG/Q303/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | LIGLAS ENTERPRISES |  | 16/6/2016 |  |  | 237000 | 237000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
639 | SUPPLY OF HORTICULTURAL PRODUCTION MATERIALS NYCG/Q308/ 2015-2016 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | CARSON HOLDINGS LTD |  | 13/6/2016 |  |  | 1896000 | 1896000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
640 | SUPPLY OF A.I EQUIPMENT, SEMEN & LIQUID NITROGEN | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | KENYA ANIMAL GENETIC RESOURCE CENTRE |  |  |  |  | 3352000 | 3352000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
641 | SUPPLY OF FIELD DEMONISTRATION MATERIALS NYCG/Q133/2016-2017 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | TGEN WORLD INTERNATIONAL |  |  |  |  | 1917500 | 1917500 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
642 | SUPPLY OF DEEP FREEZERS NYCG/Q135/2016-2017 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | SANYA KENYA LTD |  |  |  |  | 1698000 | 1698000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
643 | SUPPLY AND DELIVERY OF LOCAL VEGETABLE SEEDS NYCG/Q179/2016-2017 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | IKOBEX COMPANY LIMITED |  |  |  |  | 1602000 | 1602000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
644 | SUPPLY OF AMITRAC AND STABILIZERS NYCG/Q241/2016-2017 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | BOISABI INVESTMENTS |  |  |  |  | 1920000 | 1920000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
645 | SUPPLY OF INSECTICIDES & HERBICIDES NYCG/Q262/2016-2017 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | ANCHORION LIMITED |  |  |  |  | 1620000 | 1620000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
646 | SUPPLY OF DEMONISTRATION MATERIALS | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | ELIZAM AUTO INVESTMENTS |  |  |  |  | 1692000 | 1692000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
647 | SUPPLY OF FISH FINGERLINGS (CAT FISH) NYCG/Q299/2016-2017 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | JEWLET ENTERPRISES |  |  |  |  | 1062000 | 1062000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
648 | SUPPLY OF POND SENE NETS NYCG/Q301/2016-2017 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | KAKA INTERNATIONAL |  |  |  |  | 1584000 | 1584000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
649 | SUPPLY OF TILAPIA BROODNS NYCG/Q302/2016-2017 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | GLOBELAND LIMITED |  |  |  |  | 1250000 | 1250000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
650 | SUPPLY OF POND LINENS NYCG/Q344/2016-2017 | [6 empty] | VARIOUS |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | NKORA INVESTMENT |  |  |  |  | 1206000 | 1206000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
651 | RENOVATION OF KITCHEN AND DINING HALL AT KIENDEGE HIGH SCHOOL NYCG/Q124/2015-2016 | [6 empty] | KEMERA |  | GENDER, YOUTH, SPORTS, CULTURE & SOCIAL SERVICES | GENDER, YOUTH, SPORTS, CULTURE & SOCIAL SERVICES | LIVIVE CONST. CO. LTD |  | 26/4/2016 | 31/5/2016 |  | 1394633 | 1394633 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
652 | RENOVATION OF BOYS DORMITORY, GIRLS DORMITORY AND 8NO. CLASSROOMS AT KIENDEGE HIGH SCHOOL NYCG/Q125/2015-2016 | [6 empty] | KEMERA |  | GENDER, YOUTH, SPORTS, CULTURE & SOCIAL SERVICES | GENDER, YOUTH, SPORTS, CULTURE & SOCIAL SERVICES | GESISI ENT. LTD |  | 22/4/2016 | 27/5/2016 |  | 2219207.6 | 2219207.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
653 | SUPPLY OF TOOLS AND EQUIPMENTS NYCG/Q210/2015-2016 | [6 empty] | KEMERA |  | GENDER, YOUTH, SPORTS, CULTURE & SOCIAL SERVICES | GENDER, YOUTH, SPORTS, CULTURE & SOCIAL SERVICES | VIRMACON LIMITED |  | 2016-03-06 | 2016-03-07 |  | 1635000 | 1635000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
654 | RENOVATION OF HRM OFFICE/ REGISTRY OFFICE WING NYCG/Q083/ 2015 - 2016 | [6 empty] | TOWNSHIP |  | Public Service Management | Public Service Management | KEYRAM CO. LTD |  | 2016-10-05 | 14/6/2016 |  | 1199629 | 1199629 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2015/2016
655 | RENOVATIONOF PACDU OFFICE COUNTY HEADQUARTERS | [6 empty] | TOWNSHIP |  | Public Service Management | Public Service Management | GLAPET COMPANY LTD |  | 2016-11-07 | 15/08/2017 |  | 2218511.6 | 2218511.6 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
656 | RENOVATION OF CHIEF'S CAMP | [6 empty] | TOWNSHIP |  | Public Service Management | Public Service Management | NORMU RURAL LTD |  | 2016-11-07 | 15/08/2017 |  | 3699020 | 3699020 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
657 | RENOVATION OF DEPUTY COMMISIONER'S OFFICE | [6 empty] | TOWNSHIP |  | Public Service Management | Public Service Management | CALENO ENTERPRISES LTD |  | 2016-11-07 | 15/08/2017 |  | 1200832 | 1200832 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
658 | CONSTRUCTION OF STORE AND TOILET BLOCK | [6 empty] | TOWNSHIP |  | Public Service Management | Public Service Management | JEFF CONSTRUCTION GEN. LTD |  | 2016-11-07 | 15/08/2017 |  | 3944098.4 | 3944098.4 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2016/2017
659 | Construction of Nyamusi market Material recovery facility | [5 empty] | Nyamira North | Bokera |  | Envirinment and Natural Resources | Envirinment and Natural Resources | Tononta Enterprises |  |  |  |  | 1250000 | 1249544.75 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2025/2026
660 | Proposed Rehabilitation of Kenyerere Borehole | [5 empty] | Nyamira North | Magwagwa |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | Ndubi Holdings Limited |  |  |  |  | 1143528 | 1142942.78 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2025/2026
661 | Proposed Rehabilitation of Marani Borehole | [5 empty] | Nyamira South | Bosamaro |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | Thosar (K) Ltd |  |  |  |  | 1500000 | 1405181.4 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2025/2026
662 | Proposed Construction and Protection of Water Springs | [5 empty] | Nyamira North & Nyamira South | Bokeira, Nyamaiya & Magwagwa |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | Nanogram Limited |  |  |  |  | 1250000 | 1249694.8 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2025/2026
663 | Proposed Construction and Protection of Water Springs | [5 empty] | Nyamira North | Bosamaro, Bogichora & Bonyamatuta |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | Cheming’na Enterprises |  |  |  |  | 1250000 | 1249500 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2025/2026
664 | Promotion of Avacado project - Promotion of avacado as a livelihood improvement | [8 empty] | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | Kemmyhub Resources Limited |  |  |  |  | 1135666 | 1125618.08 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2025/2026
665 | Promotion of tissue culture bananas project | [8 empty] | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | Gelinnah Limited |  |  |  |  | 1084626 | 1079732.82 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2025/2026
666 | Supporting resilience of women and youth through Bee keeping project as an alternative means of livelihood | [8 empty] | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | Bengal Logistics Limited |  |  |  |  | 1022207.8 | 998299.4 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2025/2026
667 | Promotion of chicken for Women and youth resilience project as an alternative means of livelihood | [8 empty] | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | Next Switch Limited |  |  |  |  | 1287691 | 1279535.75 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2025/2026
668 | Supporting Artificial Insemination for Climate Adaptive Livestock Breeds - Promotion of Artificial Insermination for climate adaptive livestock for breeds improvement | [8 empty] | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | Max Tana Ltd |  |  |  |  | 594833.4 | 588336.45 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2025/2026
669 | Solar Powered Milk Aggregation and Value Addition Units - Used to purchase Milk Test Kits | [8 empty] | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | Bromax Investment Ltd |  |  |  |  | 1379615.2 | 1354906.35 |  | GOK | [8 empty] | ONGOING | [16 empty] | 2025/2026
670 | Restoration of Suguta Wetland | CGN/FLLoCA/T010/ 2024 - 2025 |  |  |  |  | Nyamira North | Magwagwa |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 9000000 | 8066986 |  | GOK | [8 empty] | Completed | [16 empty] | 2024/2025
671 | Restoration of Gesebei dam | 1713096 - 2024/2025 |  |  |  |  | Borabu | Nyansiongo |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 4500000 | 4496928.67 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
672 | Restoration of Kenyerere public land | CGN/FLLoCA/T011/ 2024 - 2025 |  |  |  |  | Masaba North | Rigoma |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 5000000 | 4087906 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
673 | Construction of Kebirigo market Material recovery facility | 1713104 - 2024/2025 |  |  |  |  | Nyamira South | Bonyamatuta |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 1250000 | 1248998.39 |  | GOK | [8 empty] | Completed | [16 empty] | 2024/2025
674 | Construction of Keroka Material recovery facility | 1713105 - 2024/2025 |  |  |  |  | Masaba North | Rigoma |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 1250000 | 1240412.01 |  | GOK | [8 empty] | Completed | [16 empty] | 2024/2025
675 | Construction of Ikonge market Material recovery facility | 1713106- 2024/2025 |  |  |  |  | Nyamira North | Ekerenyo |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 1250000 | 1249956.38 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
676 | Construction of Nyansiongo business centre Material recovery facility | 1713103- 2024/2025 |  |  |  |  | Borabu | Nyansiongo |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 1250000 | 1245152.74 |  | GOK | [8 empty] | Completed | [16 empty] | 2024/2025
677 | Construction of Miruka market Material recovery facility | 1713107 - 2024/2025 |  |  |  |  | Nyamira South | Nyamaiya |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 1250000 | 1249860.56 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
678 | Construction of Kemera market Material recovery facility | 1713108 - 2024/2025 |  |  |  |  | Manga | Kemera |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 1250000 | 1201412.72 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
679 | Establishment of Nyamira North sub county indigenous tree nursery | 1713097 - 2024/2025 |  |  |  |  | Nyamira North | Ekerenyo |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2990147.17 |  | GOK | [8 empty] | Completed | [16 empty] | 2024/2025
680 | Establishment of Nyamira South sub county indigenous tree nursery | 1713098 - 2024/2025 |  |  |  |  | Nyamira South | Township |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2998397 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
681 | Establishment of Borabu sub county indigenous tree nursery | 1713099 - 2024/2025 |  |  |  |  | Borabu | Nyansiongo |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2998803.37 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
682 | Establishment of Masaba North sub county indigenous tree nursery | 1713100 - 2024/2025 |  |  |  |  | Masaba North | Rigoma |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2998397 |  | GOK | [8 empty] | Completed | [16 empty] | 2024/2025
683 | Establishment of Manga sub county indigenous tree nursery | 1713102 - 2024/2025 |  |  |  |  | Manga | Manga |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2999116.66 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
684 | Biticha Borehole water drilling, equiping and distribution project | CGN/FLLoCA/T005/ 2024 - 2025 |  |  |  |  | Masaba North | Rigoma |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 6218000 | 5442633.7 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
685 | Egechini Borehole Water drilling, equipping and distribution project | CGN/FLLoCA/T004/ 2024 - 2025 |  |  |  |  | Nyamira North | Itibo |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 6130000 | 5412559.28 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
686 | Ikonge girls borehole water drilling, equipping and distribution project | CGN/FLLoCA/T002/ 2024-2025 |  |  |  |  | Nyamira North | Ekerenyo |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 6205000 | 5345583.99 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
687 | Keginga borehole water drilling, equipping and distribution project. | CGN/FLLoCA/T003/ 2024 - 2025 |  |  |  |  | Borabu | Nyansiongo |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 6200000 | 5433746.53 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
688 | Ekegoro Borehole Water drilling and Casing project. | 1713094 - 2024/2025 |  |  |  |  | Nyamira North | Magwagwa |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 2405000 | 2404970 |  | GOK | [8 empty] | Completed | [16 empty] | 2024/2025
689 | Rionguti Borehole water drilling, equipping and distribution project. | CGN/FLLoCA/T006/ 2024 - 2025 |  |  |  |  | Manga Sub County | Magombo |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 6100200 | 5663513 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
690 | Nyameru Borehole Water drilling, equipping and distribution Project. | CGN/FLLoCA/T007/ 2024 - 2025 |  |  |  |  | Nyamira South | Bogichora |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 6210000 | 5276856.24 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
691 | Moruga Borehole Water drilling, equipping and distribution Project . | CGN/FLLoCA/T008/ 2024 - 2025 |  |  |  |  | Nyamira South | Bosamaro |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 6150000 | 5968699.23 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
692 | Raitigo water dam desilting supply project - | CGN/FLLoCA/T009/ 2024 - 2025 |  |  |  |  | Borabu | Esise |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 10000000 | 9090651.77 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
693 | Protection of Water Springs | 1713083 - 2024/2025 |  |  |  |  | Manga & Masaba North | Magombo & Gesima |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 1740000 | 1735805.42 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
694 | Protection of Water Springs | 1713084 - 2024/2025 |  |  |  |  | Masaba North | Gachuba & Rigoma |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 1740000 | 1738665.44 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
695 | Protection of Water Springs | 1713085 - 2024/2025 |  |  |  |  | Manga | Kemera & Manga |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 1740000 | 1734849.6 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
696 | Protection of Water Springs | 1713086 - 2024/2025 |  |  |  |  | Nyamira South & Nyamira North | Nyamaiya & Bomwagamo |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 1740000 | 1735230.8 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
697 | Protection of Water Springs | 1713087 - 2024/2025 |  |  |  |  | Nyamira North | Bokeira & Magwagwa |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 1740000 | 1734371.68 |  | GOK | [8 empty] | Completed | [16 empty] | 2024/2025
698 | Protection of Water Springs | 1713088 - 2024/2025 |  |  |  |  | Nyamira North | Ekerenyo & Itibo |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 1740000 | 1739593.84 |  | GOK | [8 empty] | Completed | [16 empty] | 2024/2025
699 | Protection of Water Springs | 1796507- 2024/2025 |  |  |  |  | Nyamira South | Bosamaro & Bogichora |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 1740000 | 1739872.21 |  | GOK | [8 empty] | Completed | [16 empty] | 2024/2025
700 | Protection of Water Springs | 1713091- 2024/2025 |  |  |  |  | Nyamira South | Township & Bonyamatuta |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 1740000 | 1723812.92 |  | GOK | [8 empty] | Completed | [16 empty] | 2024/2025
701 | Protection of Water Springs | 1713092 - 2024/2025 |  |  |  |  | Borabu | Kiabonyoru & Mekenene |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 1740000 | 1739965.3 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
702 | Protection of Water Springs | 1713093 - 2024/2025 |  |  |  |  | Borabu | Esise & Nyansiongo |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 1740000 | 1736520.8 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
703 | Equipping and Distribution of Ekegoro Borehole Project | 1713095 - 2024/2025 |  |  |  |  | Nyamira North | Magwagwa |  | Water, Sanitation and Irrigation | Water, Sanitation and Irrigation | [5 empty] | 4000000 | 3999680 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
704 | Promotion of Avacado project Nyamira North | 1713124 - 2024/2025 |  |  |  |  | Nyamira North | Bomwagamo & Bokeira |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2928283 |  | GOK | [8 empty] | Delivered | [16 empty] | 2024/2025
705 | Promotion of Avacado project Borabu | 1713125-2024/2025 |  |  |  |  | Borabu | Bokeira & Esise |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2936051 |  | GOK | [8 empty] | Delivered | [16 empty] | 2024/2025
706 | Promotion of tissue culture bananas project | 1713130 - 2024/2025 |  |  |  |  | Borabu | Esise |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2957687.04 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
707 | Promotion of tissue culture bananas project | 1713131-2024/2025 |  |  |  |  | Nyamira South | Bogichora |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2957687 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
708 | Bee keeping project Nyamira North and South | 1713128 -2024/2025 |  |  |  |  | Nyamira North & South, Manga | Bokeira & Nyamaiya, Manga |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2982894 |  | GOK | [8 empty] | Delivered | [16 empty] | 2024/2025
709 | Bee keeping project Borabu, Masaba and Manga | 1713129 - 2024/2025 |  |  |  |  | Borabu, Masaba North, Manga | Nyansiongo, Rigoma & Manga |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2994898.2 |  | GOK | [8 empty] | Delivered | [16 empty] | 2024/2025
710 | Promotion of chicken at Nyamira North and South, Manga | 1713126-2024/2025 |  |  |  |  | Nyamira North & South, Manga | Bokeira & Nyamaiya, Manga |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2801185 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
711 | Promotion of chicken at Borabu, Masaba | 1713127-2024/2025 |  |  |  |  | Borabu, Masaba North, Manga | Nyansiongo, Rigoma & Manga |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2911123.75 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
712 | Artificial Insemination project Magwagwa and Bomwagamo) | 1713122-2024/2025 |  |  |  |  | Nyamira North Sub County | (Magwagwa, Bomwagamo) |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2966970 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2024/2025
713 | Artificial Insemination project Bogichora and Bosamaro | 1713123 - 2024/2025 |  |  |  |  | Nyamira South Sub County | Nyamira South (Bogichora, Bosamaro) |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2958000 |  | GOK | [8 empty] | COMPLETE | [16 empty] | 2024/2025
714 | Artificial Insemination project Manga Kemera | 1713121 - 2024/2025 |  |  |  |  | Manga Sub County | (Manga, Kemera |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 3000000 | 2996198.6 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025
715 | Solar Powered Milk Aggregation and Value Addition Units - Value addition should come out stronger and post value losses | CGN/FLLoCA/T012/ 2024-2025 |  |  |  |  | Nyamira North, Nyamira South, Manga & Masaba North | Itibo, Bogichora, Manga & Gesima |  | AGRICULTURE, LIVESTOCK & FISHERIES | AGRICULTURE, LIVESTOCK & FISHERIES | [5 empty] | 16000000 | 14620384.8 |  | GOK | [8 empty] | Ongoing | [16 empty] | 2024/2025